## 1 Instructions
Sample Safety Risk Register
What is a Safety Risk Register?
A Safety Risk Register is an information management tool you may choose to use to document your transit agency's Safety Risk Management and Safety Assurance activities. It records the hazards identified by the transit agency, the potential consequences associated with these hazards, initial safety risk ratings, new mitigations implemented to eliminate or minimize the risk associated with the hazard, revised safety risk rating, and mitigation monitoring measures and activities to ensure the implementation and effectiveness of mitigations.
The Sample Safety Risk Register provided here is presented in two parts: Safety Risk Assessment (tab 3, discussed below) and Safety Risk Mitigation (tab 4, discussed below).
What is its purpose?
The Safety Risk Register serves a dual purpose:
1. It provides managers with an on-going, up-to-date picture of (a) the overarching safety concerns that the agency faces during transit service delivery and supporting operations, and (b) the controls (safety risk mitigations) put in place to address them; and
2. It allows personnel involved in the agency’s Safety Management System (SMS) to (a) formally document hazards, potential consequences of the hazards, safety risk assessment results, and anticipated safety risk mitigations; and (b) track the status of implemented safety risk mitigations.
Description of FTA's Sample Safety Risk Register
This register is illustrative only; each transit agency may determine the tool or method that best suits its SMS documentation and tracking needs.
The Sample Safety Risk Register is comprised of five (5) separate tabs. Tabs 1 (this tab) and 2 provide instructions on how to use this Sample Safety Risk Register and definitions of the terms used within the Register. Tab 5 provides a sample safety risk assessment matrix and likelihood and severity tables, which are used to develop the examples provided in Tabs 3 and 4. Tabs 3 and 4 are the actual Sample Safety Risk Register as a transit agency could choose to use them. Specifically, the tabs include:
1. Instructions: This tab describes the Sample Safety Risk Register and how to use it.
2. Definitions: This tab lists the columns used in the Safety Risk Management Register tab and the Safety Risk Mitigation tab and provides definitions and/or an explanation of what information is collected under each column.
3. Safety Risk Assessment: This tab is the first half of the sample safety risk register. It provides a few examples of how an agency might use the safety risk register. The tab collects information about hazards and their analyses, including:
• Description of the hazard,
• Type of hazard,
• Date the hazard was identified,
• How the hazard was identified (source),
• Date analysis was performed,
• Potential consequences associated with the hazard (worst possible, worst credible, or most common),
• What mitigations are currently in place to address potential consequences associated with hazard,
• Initial safety risk rating, as defined by the severity of the consequences and likelihood of the consequences taking into account existing safety risk mitigations only,
• Revised safety risk index (risk rating with additional safety risk mitigations implemented),
• Department responsible for implementing the safety risk mitigations,
• Estimated due date for the safety risk mitigations to be implemented, and
• Contact person.
4. Safety Risk Mitigation: This tab is the second half of the sample safety risk register. It provides a few examples of how an agency might use the safety risk register. This tab collects information for status tracking and monitoring the effectiveness of implemented safety risk mitigations, including:
• Safety risk mitigation monitoring parameters (safety performance indicator(s) and target(s)),
• Associated timeframe,
• Monitoring activities, and
• Responsibilities for monitoring.
5. Safety Risk Matrix and Tables: This tab provides illustrative tables to estimate the likelihood of occurrence and the severity of potential consequences, as well as the safety risk tolerability matrix. FTA has developed separate voluntary guidance on how to develop safety risk assessment matrixes.
FTA's Sample Safety Risk Register contains three (3) illustrative hazards to demonstrate how to populate the Safety Risk Assessment and Safety Risk Mitigation tabs.
Version 1.1, April 2020
The Federal Transit Administration’s (FTA) Sample Safety Risk Register and Guide are tools designed to support implementation of SMS in the public transportation industry. The guidance in this document is not legally binding in its own right and will not be relied upon by FTA as a separate basis for affirmative enforcement action or other administrative penalty. Use of this tool is voluntary only, and noncompliance will not affect rights and obligations under existing statutes and regulations.

## 2 Definitions
Safety Risk Assessment |  |  |  | Safety Risk Mitigation
Safety Risk Assessment includes 16 columns, or data points, for each hazard entry. These columns are subdivided into 5 categories (shown at the top of the table): |  |  |  | Safety Risk Mitigation includes 8 columns, or data points, for each potential consequence entry. These columns are subdivided into 4 categories (shown at the top of the table):
1. Identification: Basic information about the hazard. |  |  |  | 1. Potential Consequence(s): The potential consequence the agency is addressing.
2. Initial Safety Risk Rating: The safety risk rating based on currently implemented mitigations, if any. |  |  |  | 2. Safety Performance Monitoring: What metrics the agency will use to measure how effectively the mitigation(s) address the potential conseuquence(s) of the hazard.
3. Further Mitigation Action: The mitigation(s) the agency intends to put into place if the initial safety risk rating is "higher" or less desireable than the agency is willing to accept. |  |  |  | 3. Timeframe and Mitigation(s) to Be Implemented: The mitigation(s) the agency intends to put into place and timeframe for implementation.
4. Revised Safety Risk Index: The safety risk rating once the mitigation(s) is/are implemented, if necessary. |  |  |  | 4. Mitigation Monitoring Activities and Responsible Department: The activities the agency will conduct to monitor the effectiveness of their mitigations and the department resonsible for those activites.
5. Mitigation Owner: Information on the department responsible for implementing the mitigation(s), the point of contact within that department, and the date by which the additional mitigation(s), if any, is/are to be impelemented.
Column Definitions |  |  |  | Column Definitions
Category | Column | Column Title | Description | Category | Column | Column Title | Description
Identification | A | Hazard | Any real or potential condition that can cause injury, illness, or death; damage to or loss of the facilities, equipment, rolling stock, or infrastructure of a public transportation system; or damage to the environment (49 C.F.R. § 673.5). | Potential Consequence(s) | A | Worst Possible, Worst Credible, or Most Common Potential Consequence(s) | This is carried over from Column F, Worst Possible, Worst Credible, or Most Common Potenital Consequence(s), of Part 1 Safety Risk Assessment. The worst possible, worst credible, or most common potential consequences. Potential consequences is here defined as the effect of a hazard involving injury, illness, or death; damage to or loss of the facilities, equipment, rolling stock, or infrastructure of a public transportation system; or damage to the environment (extrapolated from the definition of "hazard" in 49 C.F.R. § 673.5).
| B | Hazard Type | Classification used to help organize identified hazards to support an agency’s data management and hazard prioritization activities. In this sample, the agency decides to categorize three main types of hazards include Organizational (shortcomings in the organizational processes), Technical (the condition of equipment, facilities, infrastructure, and operating conditions and practices), and Environmental (the natural environment). | Safety Performance Monitoring | B | Safety Performance Indicator (SPI) | Parameter selected to monitor and measure the effectiveness of the mitigation(s) incorporated to address the potential consequence(s) of the hazard.
| C | Identification Date | The date the agency identified the hazard. This information can be used for evaluating the effectiveness of safety risk management activities by providing a starting point to see how long the agency takes to analyze and mitigate the hazard. |  | C | SPI Value | Quantification of the parameter selected to monitor and measure the effectiveness of the mitigation(s) incorporated to address the potential consequence(s) of the hazard (ex.: the number of instances over a specific period of time).
| D | Identification Source | How the hazard was identified. This information can provide insight into the effectiveness of the safety data sources available to the agency and can help identify items for improvement. |  | D | Safety Performance Target | Projected improvement beyond the SPI value resulting from the mitigation(s) incorporated to address the potential consequence(s) of the hazard (ex.: reduce the number of instances by a certain percent over a specific period of time). Note, this is different than a Safety Performance Target as established in the National Safety Plan.
| E | Analysis Date | The date the hazard was analyzed. This information can be used for evaluating the efficiency of the analysis process and determine if certain hazards are more challenging to analyze than others. | Timeframe and Mitigations to be Implemented | E | Timeframe | How long it will take the agency to implement the selected mitigation.
| F | Worst Possible, Worst Credible, or Most Common Potential Consequence(s) | The worst possible, worst credible, or most common potential consequences. Potential consequences is here defined as the effect of a hazard involving injury, illness, or death; damage to or loss of the facilities, equipment, rolling stock, or infrastructure of a public transportation system; or damage to the environment (extrapolated from the definition of "hazard" in 49 C.F.R. § 673.5). |  | F | Mitigations | This is carried over from Column K, Further Mitigation Action, of Part 1 Safety Risk Assessment. Additional mitigations the agency needs to incorporate to address the potential consequence(s) of the hazard if the safety risk index exceeds tolerability criteria (i.e. what mitigations the agency needs to implement in order to reduce the severity and/or likelihood of the potential consequences so that the corresponding tolerability is reduced to an acceptable level).
| G | Existing Mitigation(s) | The activity, process, program, or other mechanism already existing within the agency to mitigate, or to eliminate or reduce the effects (the potential consequence(s)) of the hazard (49 C.F.R. § 673.5). | Mitigation Monitoring Activities and Responsible Department | G | Monitoring Means | Activities the agency will carry out in order to monitor and measure the effectiveness of the mitigation(s) incorporated to address the potential consequence(s) of the hazard.
Initial Safety Risk Rating | H | Severity of Consequences | Quantified effect of the potential consequence(s) of the hazard in the delivery of transit services and/or supporting activities, taking into account existing mitigations. |  | H | Department Responsible for Monitoring Mitigation Effectiveness | Agency department primarily tasked with monitoring and measuring the effectiveness of the mitigation(s) incorporated to address the potential consequence(s) of the hazard.
| I | Likelihood of Consequences | Quantified probability that the potential consequence(s) of the hazard will occur, taking into account existing mitigations. Calendar days, weeks, months, years, or decades are often used as time periods to support assessments of likelihood in safety risk assessment.
| J | Safety Risk Index | The composite of the predicted severity and likelihood of the potential consequence of the hazard (49 C.F.R. 673.5) and the tolerability of the potential consequence(s) of the hazard taking into account existing mitigations. The tolerability is defined by the individual agency. Tab 5 provides the charts this Sample Safety Risk Register uses to determine tolerability.
Further Mitigation Action | K | Further Mitigation Action | Additional mitigations the agency needs to incorporate to address the potential consequence(s) of the hazard if the safety risk index exceeds tolerability criteria (i.e. what mitigations the agency needs to implement in order to reduce the severity and/or likelihood of the potential consequences so that the corresponding tolerability is reduced to an acceptable level).
Revised Safety Risk Index | L | Revised Safety Risk Index | Safety risk index after implementing additional mitigations that meets the tolerability criteria.
| M | Revised Safety Risk Index Date | The date the revised safety index was determined. This information can be used to evaluate the efficiency of the analysis process and determine if certain hazards are more challenging to analyze than others.
Mitigation Owner | N | Department Responsible for Mitigation | Agency department primarily tasked with mitigation implementation.
| O | Estimated Implementation Date | The date the mitigation(s) are expected to be implemented. This information is used to track the completion of mitigations and identify any potential resource or other concerns.
| P | Contact Person | Primary point of contact within the department responsible for mitigation.

## 3 Safety Risk Assessment
Sample Safety Risk Assessment Register
Identification | [6 empty] | Initial Safety Risk Rating |  |  | Further Mitigation Action | Revised Safety Risk Index |  | Mitigation Owner and Implementation Date
Hazard | Hazard Type | Identification Date | Identification Source | Analysis Date | Worst Possible, Worst Credible, or Most Common Potential Consequence(s) | Existing Mitigation(s) | Severity of Consequences | Likelihood of Consequences | Safety Risk Index | Further Mitigation Action | Revised Safety Risk Index | Revised Safety Risk Index Date | Department Responsible for Mitigation | Estimated Implementation Date | Contact Person
Buses misaligned over pits. | Technical - Maintenance | Date | Employee safety reporting | Date | Bus falling into pit resulting in worker fatality. | 1. Training in aligning the bus properly over pit. 2. SOP and rule book provided with training. | 1 (Catastrophic) | C (Occasional) | 1C (Unacceptable under the existing circumstances) | 1. Revise SOP and Rulebook to require a second worker to watch and signal for bus placement. 2. Establish speed restrictions moving in and out of shop. 3. Stripe lines around pits with high visibility fluorescent paint. 4. Revise SOPs to ensure pit is not occupied during bus movements over pit. 5. Install bus tire guides on pit edge. | 1D (Acceptable based upon mitigations) | Date | Bus Vehicle Maintenance | Date | Name
Near side bus stop in Blue Route at the intersection of First and Main. | Technical - Operational | Date | Inspection report | Date | Car turning right in front and colliding with the bus as the bus pulls out of the stop. | 1. Operator training. 2. SOP and rule book provided with training. | 2 (Critical) | B (Probable) | 2B (Unacceptable under the existing circumstances) | 1. Issue alert bulletin to Blue Line operators. 2. Install an alerting signal at the bus stop. | 2C (Acceptable based upon mitigations) | Date | Operations | Date | Name
Placement of XYZ model buses inspection panels. | Technical - Design | Date | Employee safety reporting | Date | Inspection panels in XYZ model buses difficult to access by maintenance personnel. | 1.Maintenance training. 2. SOP and rule book provided with training. | 3 (Negligible) | B (Probable) | 3B (Acceptable based upon mitigations) | N/A | N/A | N/A | N/A | N/A | N/A

## 4 Safety Risk Mitigation
Sample Safety Risk Mitigation Register
Potential Consequence(s) | Safety Performance Monitoring |  |  | Timeframe and Mitigation(s) to be Implemented |  | Mitigation Monitoring Activities and Responsible Department
Worst Possible, Worst Credible, or Most Common Potential Consequence(s) | Safety Performance Indicator (SPI) | SPI Value | Safety Performance Target | Timeframe | Mitigations | Monitoring Means | Department Responsible for Monitoring Mitigation Effectiveness
Bus falling into pit resulting in worker fatality. | Bus alignment over pit. | [Number] events of bus misalignment over pit per [time unit]. | Reduce the number events of bus misalignment over pit per [time unit] by [%] by [date]. | 180 days | 1. Revised SOP and Rulebook to require a second worker to watch and signal for bus placement. | 1. Employee safety reporting. | Safety Department
[6 empty] | 2. Inspections. | Safety Department
[6 empty] | 3. Workplace observations. | Safety Department
|  |  |  | 180 days | 2. Establish speed restrictions moving in and out of shop. | 1. Employee safety reporting. | Safety Department
[6 empty] | 2. Inspections. | Safety Department
[6 empty] | 3. Workplace observations. | Safety Department
|  |  |  | 180 days | 3. Stripe lines around pits with high visibility fluorescent paint. | 1. Inspections. | Safety Department
|  |  |  | 180 days | 4. Revise SOPs to ensure pit is not occupied during bus movements over pit. | 1. Employee safety reporting. | Safety Department
[6 empty] | 2. Workplace observations. | Safety Department
|  |  |  | 180 days | 5. Install bus tire guides on pit edge. | 1. Inspections. | Safety Department
Car turning right in front and colliding with the bus as the bus pulls out of the stop. | Bus pulling of the stop while a car turns in front. | [Number] events of bus pulling of the stop while a car turns in front per [time unit]. | Reduce the number events of bus pulling of the stop while a car turn in front per [time unit] by [%] by [date]. | 120 days | 1. Issue alert bulletin to Blue Line operators. | 1. Workplace observations. | Safety Department
[6 empty] | 2. Employee safety reporting. | Safety Department
|  |  |  | 120 days | 2. Install an alerting signal at the bus stop. | 1. Workplace observations. | Safety Department
[6 empty] | 2. Employee safety reporting. | Safety Department
Inspection panels in XYZ model buses difficult to access by maintenance personnel. | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## 5 Safety Risk Matrix and Tables
Sample Safety Risk Matrix and Likelihood and Severity Tables
Likelihood of Occurrence of the Consequence |  |  | Risk Assessment Matrix
Qualitative Definition | Meaning | Value | Likelihood | Severity
Frequent | Likely to Occur Frequently (>10-1) | A |  | 1 (Catastrophic) | 2 (Critical) | 3 (Marginal) | 4 (Negligible)
Probable | Likely to Occur Several Times (<10-1 but >10-3) | B | A (Frequent) | 1A | 2A | 3A | 4A
Occasional | Likely to Occur Sometime (<10-3 but >10-6) | C | B (Probable) | 1B | 2B | 3B | 4B
Remote | Very Unlikely to Occur (<10-6 but >10-8) | D | C (Occasional) | 1C | 2C | 3C | 4C
Improbable | Almost inconceivable that the event will occur (<10-8) | E | D (Remote) | 1D | 2D | 3D | 4D
|  |  | E (Improbable) | 1E | 2E | 3E | 4E
Severity of the Consequence
Definition Category | Meaning | Value |  | Risk Assessment Matrix Color Code
Catastrophic | Could result in one or more of the following: death, permanent total disability, irreversible significant environmental impact or monetary loss equal to or exceeding $10M. | 1 |  | "Tolerability" based on identified severity and likelihood.
Unacceptable under the existing circumstances.
Critical | Could result in one or more of the following: permanent partial disability, injuries or occupational illness that may result in hospitalization of at least three personnel, reversible significant environmental impact, or monetary loss equal to or exceeding $1M but less than $10M. | 2 |  |  | Acceptable based upon mitigations.
Acceptable with senior management approval.
Marginal | Could result in one or more of the following: injury or occupational illness resulting in one or more lost work day(s), reversible moderate environmental impact, or monetary loss equal to or exceeding $100K but less than $1M. | 3
Negligible | Could result in one or more of the following: injury or occupational illness not resulting in a lost work day, minimal environmental impact, or monetary loss less than $100K. | 4
*Numbers provided for illustrative purposes only