## Risk Workbook Overview
Risk Model Version Number
5.16b
Tab (worksheet) color scheme
Workbook overview
1) Project Background
2) Sponsor original data
3) PMOC cost basis analysis
4) PMOC risk analysis
5) Reportable risk analysis
Appendices: Risk factoring standards
Cell color scheme
PMOC Input
Data transferred from other worksheets
Values calculated within worksheet
Cautionary information
Headings
Instructional
General Instructions:
This workbook is based upon principles described in FTA Oversight Procedure (OP) 40 - Risk and Contingency Review. A thorough understanding of the cost-risk analysis procedures and reporting requirements described therein are necessary in order to provide context to the processes contained within this workbook. This workbook provides information necessary for the Risk Report described in the OP40. The OP40 Risk report shall include a description of the factors and judgments that have caused adjustments made in this cost-risk analysis.
The purpose of this workbook is to establish a common basis for FTA project cost-risk assessments. This workbook may be augmented by the insertion of additional worksheets that may help clarify or create a holistic view of the resulting risk analysis. Additional inserting worksheets may include such items as a listing of important risks that affect the risk analysis, calculations of revised Beta factors, or other calculations or considerations that are material to the assessments herein.
The assessment is achieved in 5 steps:
1- Gather general information about the project and document understanding of the overall project conditions.
2- Obtain Sponsor's baseline cost and risk information; document the Sponsor cost baseline from the FTA SCC Workbook, in terms of Base Year (BY) and Year of Expenditure (YOE) values.
3- Determine PMOC adjustments to the Sponsor's base costs, time-based expected costs over time, and inflation rates; establish SABCE.
4- Account for uncertainty and project-specific risk. Establish the general level of project uncertainty based on the project's progression, and establish risk-specific uncertainty based on project-specific risks.
5- Review and report on the resulting levels of project cost outcome based on the above analysis.
This 5-step process is structured through sets of consecutive worksheets (workbook tabs) within this model. Instructions for completing the worksheets are provided throughout. When completed for a project, this workbook is to be saved under a unique name and should be archived as the basis for the PMOC project risk report. Completing each tab thoroughly provides for a history of the risk analysis. See color scheme of the Tabs to the right.
This workbook establishes basic fundamentals regarding:
* Inputs required
* Basis of project risk calculations
* Interpretation of results.
See also detailed discussions of this process in the FTA OP 40. An simplified overview of the overall process of FTA cost risk calculations is included as the last tab of this workbook.
Cells that are highlighted in yellow (or very light gray if in grayscale mode) indicate PMOC input. Other cells are calculated or informational, and are protected from change (see color scheme to the right). The cells are protected by a password.
It is recognized that individual transit projects are unique and each project may find it necessary to customize certain sections of this workbook, or may wish to insert additional worksheets to improve clarity of the results or to document additional analyses. Nothing contained here is intended to restrict such amplification; it is the purpose here, however, to establish fundamentals within a common platform of risk assessment across all projects.
Send comments and suggestions for improvement are encouraged to FTA. If any errors are found, please notify the FTA.
Care must be taken if revising any of the enclosed worksheets to appropriately copy and paste formulas, especially when introducing additional rows of information. Substantial experience with Microsoft Excel and the fundamentals of the calculations herein is required to properly expand any worksheets, to move or copy formulas, or to introduce additional sheets and appropriately reference cells. If uncertain about the process of modification of this workbook, contact the FTA for assistance.
A workbook developed for a particular project is a companion to the reports required by the various FTA Oversight Procedures; the reports should contain full explanations of workbook development and of any assumptions or concerns regarding establishment of workbook values, including analysis and recommendations resulting from calculations provided within the workbook. Note that the results of this risk model are based on model standards and PMOC inputs and judgments. The results herein should not be used without appropriate professional judgment to interpret or adjust the results based on factors that are not capable of being modeled here.
If conflict is noted between this model workbook and direction provided within the Oversight Procedures (especially OP40) or if the PMOC purposefully proceeds in a manner that varies from this basic model, seek concurrence and assistance from the FTA and note assumptions and actions made in the written report.
Instructions contained herein are intended to illustrate important elements of this workbook model, but assume a thorough working knowledge of principles of professional cost estimating and risk assessment. Therefore, not all calculations are indicated in detail.

## Table of Contents
Table of Contents: Worksheets
Overview
Risk Workbook Overview
Table of Contents: Worksheets (this worksheet)
STEP ONE
Sponsor Project Background
Project Background Instructions
Project Background
STEP TWO
Sponsor Data
Sponsor Baseline Instructions
Sponsor SCC Main Worksheet
Sponsor SCC Inflation Calculations
STEP THREE
PMOC Adjustments to Stripped Sponsor Base
PMOC Baseline Adjustments Instructions
--Risk Profiles
Risk Profile Descriptions
Risk Profile Values Breakdown
---Base Year Adjustments
PMOC Adjustments to Sponsor Base Year Values
---Year of Expenditure (YOE) Adjustments
PMOC Global adjustments to Sponsor inflation
PMOC Inflation adjustments by profile and calculation of PMOC- Inflated, Adjusted, Stripped Estimate
STEP FOUR
PMOC Risk Assessment
Risk Assessment Instructions
---Assign Project Base Uncertainty and Specific Risk
Assign Project Uncertainty (Beta values) Instruction
Project-specific Risk Instruction
PMOC Risk Profile 1 Assessment
PMOC Risk Profile 2 Assessment
PMOC Risk Profile 3 Assessment
PMOC Risk Profile 4 Assessment
Summary additional Profiles from addendum workbook
---Risk Assessment Total
PMOC Risk Profile Total Assessment
STEP FIVE
PMOC Project Risk Analysis
Risk Assessment Analysis Instructions
Risk Assessment Analysis
Reporting Graphic
Appendices
Beta Factor Standards
Standards Instruction
DBB / CMGC Beta Uncertainty Standard
DBB Beta Drawdown Graphs
Beta factor tools
Project-specific Risk Calculations
SCC 10-50 Beta Calculations
SCC 60 / 70 Beta Calculations
SCC 80 Beta Calculations
Other Helpful Tools and Information
Inflation / Deflation Calculator
Cost Risk Calculations Schema

## 1 - Proj Background Instr
Project Background Instructions:
The project risk assessment depends upon the general status of the project. The FTA top-down risk assessment process is based upon patterns of risk that vary depending upon the following factors:
* Sponsor organization and experience managing capital projects
* Project design progression
* Project complexity
* Scope
* Schedule
* Cost estimate
* Project delivery method(s)
* Key identified risks
* Other factors identified as important to the analysis.
While the OP40 report should contain significant detail regarding these elements, the purpose of this Section 1 is to provide a summary of the most influential among the above factors. Complete each identified section, and in the "notes" box, include factors that provide any reviewer of the workbook substantive background information, especially related to those factors that are influential to the risk analysis contained in this workbook.
Key sources of this information are OP2X and OP3X (and other) reports that necessarily precede this risk analysis. It may be useful to copy key summary information from these prior reports.

## PMOC Project Background
Project name
Project Name
Sponsor
Sponsor name
FTA review milestone
Milestone
Project delivery method(s)
ProjDelMthd
Date of review
ReviewDate
Version 5.16b Primary Workbook or Addendum #
Primary Workbook
Notes
Assumptions Write key risk analysis assumptions here
Primary risks narrative General description of key areas of risk.
Project Description Include here a synopsis of the project. May be taken from Scope report.

## 2 - Sponsor Baseline Instr
Documenting the Sponsor Baseline
The purpose of the Section 2 worksheets is to transfer Sponsor cost data from Sponsor-provided documents into this Risk Assessment Workbook in a format that provides for further conditioning and analysis in Section 3. Much of this information is obtained from earlier Oversight Procedure (OP) assessments, including and especially OP 33 Capital Cost Estimate Review.
Values are generally derived from the Sponsor's FTA SCC Workbook; transfer the Sponsor cost information as values, not as formulas.
A worksheet is included that allows for copying and pasting summary-level Sponsor Risk Register information, indicating key, influential Sponsor risks.
The steps involve:
* Obtain and transfer the Base Year (BY) and Year of Expenditure (YOE) estimated values from the SCC Main worksheet of the FTA SCC Workbook
* Ensure that the project base year and inflation values on the "Sponsor SCC Inflation" worksheet match the value shown in the FTA SCC Workbook Inflation worksheet.

## Sponsor SCC Main
Copy values only from Sponsor SCC Main into yellow areas of this worksheet. Carefully verify values.
M A I N W O R K S H E E T - B U I L D A L T E R N A T I V E
Transit Agency | [6 empty] | SCC Main Date |  | Date
Project Name | [6 empty] | Yr of Base Year $ |  | Year
Review milestone | [6 empty] | Yr of Revenue Ops |  | Year
|  | Quantity | Base Year Dollars w/o Contingency (X000) | Base Year Dollars Allocated Contingency (X000) | Base Year Dollars TOTAL (X000) | Base Year Dollars Unit Cost (X000) | Base Year Dollars Percentage of Construction Cost | Base Year Dollars Percentage of Total Project Cost | YOE Dollars Total (X000) | Inflation factor | Sponsor YOE SCC 10-80 Contingency | Sponsor YOE SCC 10-80 Stripped Estimate
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 0 | 0 | 0 | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0
10.01 | Guideway: At-grade exclusive right-of-way |  |  |  | 0 |  |  |  | 0
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) |  |  |  | 0 |  |  |  | 0
10.03 | Guideway: At-grade in mixed traffic |  |  |  | 0 |  |  |  | 0
10.04 | Guideway: Aerial structure |  |  |  | 0 |  |  |  | 0
10.05 | Guideway: Built-up fill |  |  |  | 0 |  |  |  | 0
10.06 | Guideway: Underground cut & cover |  |  |  | 0 |  |  |  | 0
10.07 | Guideway: Underground tunnel |  |  |  | 0 |  |  |  | 0
10.08 | Guideway: Retained cut or fill |  |  |  | 0 |  |  |  | 0
10.09 | Track: Direct fixation |  |  |  | 0 |  |  |  | 0
10.1 | Track: Embedded |  |  |  | 0 |  |  |  | 0
10.11 | Track: Ballasted |  |  |  | 0 |  |  |  | 0
10.12 | Track: Special (switches, turnouts) |  |  |  | 0 |  |  |  | 0
10.13 | Track: Vibration and noise dampening |  |  |  | 0 |  |  |  | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 0 | 0 | 0 | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0
20.01 | At-grade station, stop, shelter, mall, terminal, platform |  |  |  | 0 |  |  |  | 0
20.02 | Aerial station, stop, shelter, mall, terminal, platform |  |  |  | 0 |  |  |  | 0
20.03 | Underground station, stop, shelter, mall, terminal, platform |  |  |  | 0 |  |  |  | 0
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. |  |  |  | 0 |  |  |  | 0
20.05 | Joint development |  |  |  | 0 |  |  |  | 0
20.06 | Automobile parking multi-story structure |  |  |  | 0 |  |  |  | 0
20.07 | Elevators, escalators |  |  |  | 0 |  |  |  | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  | 0 | 0 | 0 | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0
30.01 | Administration Building: Office, sales, storage, revenue counting |  |  |  | 0 |  |  |  | 0
30.02 | Light Maintenance Facility |  |  |  | 0 |  |  |  | 0
30.03 | Heavy Maintenance Facility |  |  |  | 0 |  |  |  | 0
30.04 | Storage or Maintenance of Way Building |  |  |  | 0 |  |  |  | 0
30.05 | Yard and Yard Track |  |  |  | 0 |  |  |  | 0
40 SITEWORK & SPECIAL CONDITIONS |  | 0 | 0 | 0 | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0
40.01 | Demolition, Clearing, Earthwork |  |  |  | 0 |  |  |  | 0
40.02 | Site Utilities, Utility Relocation |  |  |  | 0 |  |  |  | 0
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments |  |  |  | 0 |  |  |  | 0
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks |  |  |  | 0 |  |  |  | 0
40.05 | Site structures including retaining walls, sound walls |  |  |  | 0 |  |  |  | 0
40.06 | Pedestrian / bike access and accommodation, landscaping |  |  |  | 0 |  |  |  | 0
40.07 | Automobile, bus, van accessways including roads, parking lots |  |  |  | 0 |  |  |  | 0
40.08 | Temporary Facilities and other indirect costs during construction |  |  |  | 0 |  |  |  | 0
50 SYSTEMS |  | 0 | 0 | 0 | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0
50.01 | Train control and signals |  |  |  | 0 |  |  |  | 0
50.02 | Traffic signals and crossing protection |  |  |  | 0 |  |  |  | 0
50.03 | Traction power supply: substations |  |  |  | 0 |  |  |  | 0
50.04 | Traction power distribution: catenary and third rail |  |  |  | 0 |  |  |  | 0
50.05 | Communications |  |  |  | 0 |  |  |  | 0
50.06 | Fare collection system and equipment |  |  |  | 0 |  |  |  | 0
50.07 | Central Control |  |  |  | 0 |  |  |  | 0
Construction Subtotal (10 - 50) |  | 0 | 0 | 0 | 0 |  | #DIV/0! | #DIV/0! | 0 |  | 0 | 0
60 ROW, LAND, EXISTING IMPROVEMENTS |  | 0 | 0 | 0 | 0 |  |  | #DIV/0! | 0 | 0 | 0 | 0
60.01 | Purchase or lease of real estate |  |  |  | 0 |  |  |  | 0
60.02 | Relocation of existing households and businesses |  |  |  | 0 |  |  |  | 0
70 VEHICLES (number) |  | 0 | 0 | 0 | 0 |  |  | #DIV/0! | 0 | 0 | 0 | 0
70.01 | Light Rail |  |  |  | 0 |  |  |  | 0
70.02 | Heavy Rail |  |  |  | 0 |  |  |  | 0
70.03 | Commuter Rail |  |  |  | 0 |  |  |  | 0
70.04 | Bus |  |  |  | 0 |  |  |  | 0
70.05 | Other |  |  |  | 0 |  |  |  | 0
70.06 | Non-revenue vehicles |  |  |  | 0 |  |  |  | 0
70.07 | Spare parts |  |  |  | 0 |  |  |  | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) |  | 0 | 0 | 0 | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0
80.01 | Project Development |  |  |  | 0 |  |  |  | 0
80.02 | Engineering (not applicable to Small Starts) |  |  |  | 0 |  |  |  | 0
80.03 | Project Management for Design and Construction |  |  |  | 0 |  |  |  | 0
80.04 | Construction Administration & Management |  |  |  | 0 |  |  |  | 0
80.05 | Professional Liability and other Non-Construction Insurance |  |  |  | 0 |  |  |  | 0
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. |  |  |  | 0 |  |  |  | 0
80.07 | Surveys, Testing, Investigation, Inspection |  |  |  | 0 |  |  |  | 0
80.08 | Start up |  |  |  | 0 |  |  |  | 0
Subtotal (10 - 80) |  | 0 | 0 | 0 | 0 |  |  | #DIV/0! | 0 |  | 0 | 0
90 UNALLOCATED CONTINGENCY | [7 empty] | #DIV/0! | 0 | 0
Subtotal (10 - 90) |  | 0 |  |  | 0 |  |  | #DIV/0! | 0
100 FINANCE CHARGES | [7 empty] | #DIV/0! | 0 | 0
Total Project Cost (10 - 100) |  | 0 |  |  | 0 |  |  | #DIV/0! | 0 | 0
Allocated Contingency as % of Base Yr Dollars w/o Contingency |  |  |  |  | #DIV/0!
Unallocated Contingency as % of Base Yr Dollars w/o Contingency |  |  |  |  | #DIV/0!
Total Contingency as % of Base Yr Dollars w/o Contingency |  |  |  |  | #DIV/0!
Unallocated Contingency as % of Subtotal (10 - 80) |  |  |  |  | #DIV/0!
YOE Construction Cost per Mile (X000) | [8 empty] | #DIV/0!
YOE Total Project Cost per Mile Not Including Vehicles (X000) | [8 empty] | #DIV/0!
YOE Total Project Cost per Mile (X000) | [8 empty] | #DIV/0!

## Sponsor SCC Inflation
1) Sponsor values are derived from Sponsor SCC Main worksheet in this workbook. 2) Verify that values correspond to Sponsor SCC Workbook, Inflation worksheet. If not, investigate as to cause and correct.
BASE YEAR DOLLARS (X$000) | Base Yr Dollars
10 GUIDEWAY & TRACK ELEMENTS | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 0
40 SITEWORK & SPECIAL CONDITIONS | 0
50 SYSTEMS | 0
60 ROW, LAND, EXISTING IMPROVEMENTS | 0
70 VEHICLES | 0
80 PROFESSIONAL SERVICES | 0
90 UNALLOCATED CONTINGENCY | 0
100 FINANCE CHARGES | 0
Total Project Cost (10 - 100) | 0
YEAR OF EXPENDITURE DOLLARS (X$000) | YOE Dollars
10 GUIDEWAY & TRACK ELEMENTS | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 0
40 SITEWORK & SPECIAL CONDITIONS | 0
50 SYSTEMS | 0
60 ROW, LAND, EXISTING IMPROVEMENTS | 0
70 VEHICLES | 0
80 PROFESSIONAL SERVICES | 0
90 UNALLOCATED CONTINGENCY | 0
100 FINANCE CHARGES | 0
Total Project Cost (10 - 100) | 0
Inflation factor
10 GUIDEWAY & TRACK ELEMENTS | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 0
40 SITEWORK & SPECIAL CONDITIONS | 0
50 SYSTEMS | 0
60 ROW, LAND, EXISTING IMPROVEMENTS | 0
70 VEHICLES | 0
80 PROFESSIONAL SERVICES | 0
90 UNALLOCATED CONTINGENCY | 0
100 FINANCE CHARGES | 0
Total Project Cost (10 - 100) | 0

## 3 - Baseline Adjustments Instr
Instructions for:
Adjusted BY & YOE Estimate
These adjustments are based on principles outlined in OP40, with which the analyst should be familiar.
The purpose of this section is to adjust Sponsor cost data from Sponsor documents as provided in the prior section of this workbook. Adjustments include determining whether the project should be broken into Risk Profiles (see below), making PMOC adjustments to the Sponsor's Base Year estimated values, and making PMOC adjustments to the Sponsor's inflation calculations.
Risk Profiles The workbook allows for distinct portions of any given project to be segregated for easier assessment. These portions would typically be those which have distinct risk profiles; for example, if a project has a portion for which contracts have already been received, and a portion for which contracts are still under design, then these two portions may very well have differing risk profiles. The same may occur for projects that are in different stages of construction, or for which differing project delivery systems have been developed. Built within the workbook is the ability to have 4 distinct risk profiles; each distinct portion is then aggregated on a "weighted" basis to provide a holistic view of the risk for the whole project.
Risk Profiles Expansion Additional profiles (beyond 4) may be added by transferring results from an additional "addendum" risk workbook. Sections 1 (project background) and 2 (Sponsor SCC workbook values) of the addendum risk workbook are completed using the same information as, and may be copied from, the prime workbook. Sections 3 (PMOC adjustments) and 4 (Risk factoring) are completed using values and factors that are unique to the additional risk profile(s).
The Section 4 Risk Assessment Total worksheet results from the addendum risk workbook are transferred to the prime risk workbook into the highlighted cells in the Section 4 Additional Profiles worksheet. Section 5 Risk Assessment Analysis addendum worksheet Overall results are transferred into the Section 5 Risk Assessment Analysis prime worksheet Additional Profiles highlighted cells.
Note that when addendum risk workbooks are used, the error checking column in the "PMOC BY Risk Profile Values" tab will not function.
Segregating the project's cost estimate into different profiles must be carefully done, and the sum of the profiles should be checked against the total estimate provided in the Sponsor FTA SCC Workbook.
File names for prime and addendum risk workbooks should carry the same name, with either "prime" or "addendum" included to distinguish between them.
Instructions for:
Adjusted BY & YOE Estimate
Determine whether the project should be divided into risk profiles:
If risk profiles are not used:
-- indicate so on the risk profile description tab,
-- verify that the Sponsor BY cost estimate has been automatically properly transferred to the PMOC Base Year Adjustments tab.
If up to four risk profiles are used:
-- describe those risk profiles on the risk profile description tab,
-- develop a PMOC workbook that segregates the Sponsor cost estimate by risk profile,
-- transfer this information to the PMOC Base Year Adjustments tab.
-- More than four risk profiles may be used, see instruction at bottom.
* Develop and apply adjustments to the Sponsor's Base year values in the PMOC BY Adj worksheet. Three categories of adjustments are provided: Direct cost adjustments, time-related direct cost adjustments, and latent contingency adjustments. It is helpful to record brief reasons for any such adjustments.
-- Time-related adjustments include such items as direct costs for construction overhead due to anticipated extended project duration or for Sponsor staffing extension direct costs. Not included in the PMOC BY Adj worksheet are inflation cost adjustments due to anticipated changes to the Sponsor annual cash flow or expected changes to the Sponsor infaltion values; those changes are accounted for in the PMOC Globl Infl Adjst and PMOC Profl Infl Adj worksheets.
* Based upon results from the OP34 schedule and OP40 schedule risk analysis and other schedule-related information, if necessary amend a copy of the Sponsor SCC Workbook Inflation worksheet to establish revised cash flow values or inflation values. Input the summary values into the PMOC Inflation Adjustment tab; if no PMOC adjustments, input the original Sponsor values. Such revised rates may be calculated using a copy of the Sponsor SCC Workbook or may require a separately-documented spreadsheet analysis.
* The above information is transferred to the PMOC YOE Adjustments worksheet. The adjusted inflation rates for each SCC category are transferred to each risk profile. If further definition of PMOC inflation rates is desired, enter those rates in the PMOC YOE Adjustments worksheet.
The Adjusted YOE Estimate that results from these worksheets will form the basis for the Lower Bound for the risk assessment on the subsequent worksheets. It is important that these values are well-established before proceeding with the analysis. Among the important considerations is ensuring that all efforts have been made to strip the original estimate of the contingency; failure to do so will in effect cause a "double-counting" of amounts recommended to be added to the base estimate to protect against risk.
* If more than four risk profiles are required:
-- complete an additional "addendum" risk workbook for up to four more risk profiles using the instructions to the left,
-- transfer results to the Section 4 "Additional Profiles" tab and the Section 5 "Risk Assessment Analysis" tab.
-- Each addendum may, in turn, include a "chained" sub-addendum workbook to achieve even further risk profile expansion.

## PMOC Risk Profile Descr
Risk Profile 1 Short Name
Transit project
Risk Profile 2 Short Name
Not Used
Risk Profile 3 Short Name
Not Used
Risk Profile 4 Short Name
Not used
Risk Profile 1 Description
Place notes here.
Risk Profile 2 Description
Place notes here.
Risk Profile 3 Description
Place notes here.
Risk Profile 4 Description

## PMOC BY Risk Profile Values
List values by Risk Profile. At bottom of sheet in text box, name of any source file(s) used to complete this worksheet. NOTE: If only one risk profile, copy base year values directly from the Spsonor SCC Main Worksheet in this model. Ensure totals match Sponsor SCC workbook totals (See "CHECK" column M.) Check column does not function when addendum risk workbooks are used to expand risk profiles. | [12 empty] | Stripped YOE values with neither PMOC cost nor inflation adjustments
|  | Profile (1) |  | Profile (2) |  | Profile (3) |  | Profile (4) |  | Total | SCC | CHECK: See Errors below | Profile (1) | Profile (2) | Profile (3) | Profile (4)
Risk Profile Values |  | Base Year Dollars w/o Contingency (X000) | Note | Base Year Dollars w/o Contingency (X000) | Note | Base Year Dollars w/o Contingency (X000) | Note | Base Year Dollars w/o Contingency (X000) | Note | All Base Year Dollars w/o Contingency (X000 | Sponsor Base Year Dollars from SCC Main |  | Sponsor Base Year Dollars w/o contingency x Inflation Factor | Sponsor Base Year Dollars w/o contingency x Inflation Factor | Sponsor Base Year Dollars w/o contingency x Inflation Factor | Sponsor Base Year Dollars w/o contingency x Inflation Factor
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0
10.01 | Guideway: At-grade exclusive right-of-way | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
10.03 | Guideway: At-grade in mixed traffic | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
10.04 | Guideway: Aerial structure | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
10.05 | Guideway: Built-up fill | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
10.06 | Guideway: Underground cut & cover | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
10.07 | Guideway: Underground tunnel | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
10.08 | Guideway: Retained cut or fill | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
10.09 | Track: Direct fixation | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
10.1 | Track: Embedded | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
10.11 | Track: Ballasted | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
10.12 | Track: Special (switches, turnouts) | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
10.13 | Track: Vibration and noise dampening | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
20.02 | Aerial station, stop, shelter, mall, terminal, platform | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
20.03 | Underground station, stop, shelter, mall, terminal, platform | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
20.05 | Joint development | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
20.06 | Automobile parking multi-story structure | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
20.07 | Elevators, escalators | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0
30.01 | Administration Building: Office, sales, storage, revenue counting | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
30.02 | Light Maintenance Facility | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
30.03 | Heavy Maintenance Facility | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
30.04 | Storage or Maintenance of Way Building | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
30.05 | Yard and Yard Track | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
40 SITEWORK & SPECIAL CONDITIONS |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0
40.01 | Demolition, Clearing, Earthwork | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
40.02 | Site Utilities, Utility Relocation | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
40.05 | Site structures including retaining walls, sound walls | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
40.06 | Pedestrian / bike access and accommodation, landscaping | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
40.07 | Automobile, bus, van accessways including roads, parking lots | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
40.08 | Temporary Facilities and other indirect costs during construction | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
50 SYSTEMS |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0
50.01 | Train control and signals | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
50.02 | Traffic signals and crossing protection | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
50.03 | Traction power supply: substations | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
50.04 | Traction power distribution: catenary and third rail | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
50.05 | Communications | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
50.06 | Fare collection system and equipment | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
50.07 | Central Control | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
Construction Subtotal (10 - 50) |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0
60 ROW, LAND, EXISTING IMPROVEMENTS |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0
60.01 | Purchase or lease of real estate | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
60.02 | Relocation of existing households and businesses | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
70 VEHICLES (number) |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0
70.01 | Light Rail | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
70.02 | Heavy Rail | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
70.03 | Commuter Rail | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
70.04 | Bus | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
70.05 | Other | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
70.06 | Non-revenue vehicles | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
70.07 | Spare parts | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0
80.01 | Project Development | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
80.02 | Engineering (not applicable to Small Starts) | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
80.03 | Project Management for Design and Construction | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
80.04 | Construction Administration & Management | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
80.05 | Professional Liability and other Non-Construction Insurance | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
80.07 | Surveys, Testing, Investigation, Inspection | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
80.08 | Start up | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | OK | 0 | 0 | 0 | 0
Subtotal (10 - 80) |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0
Source files used
Place notes here.

## PMOC BY Adj
Enter these adjustments as suggested from OP33 review. List PMOC adjustments to base year estimate. Include note regarding the reason for the PMOC adjustment. Indicate source document and analysis for these adjustments at bottom of sheet. n.b. Latent contingency values are entered as negative.
|  | Risk Profile (1) BY | [5 empty] | Note | Risk Profile (2) BY | [5 empty] | Note | Risk Profile (3) BY | [5 empty] | Note | Risk Profile (4) BY | [5 empty] | Note | Project Totals
|  | Sponsor SCC Values | Direct cost adjustments | Time-related direct cost adjustments (not inflation) | Latent Contingency Deductions (negative) | Total adjustment | PMOC Adjusted Estimate |  | Sponsor SCC Values | Direct cost adjustments | Time-related direct cost adjustments (not inflation) | Latent Contingency Deductions (negative) | Total adjustment | PMOC Adjusted Estimate |  | Sponsor SCC Values | Direct cost adjustments | Time-related direct cost adjustments (not inflation) | Latent Contingency Deductions (negative) | Total adjustment | PMOC Adjusted Estimate |  | Sponsor SCC Values | Direct cost adjustments | Time-related direct cost adjustments (not inflation) | Latent Contingency Deductions (negative) | Total adjustment | PMOC Adjusted Estimate |  | Sponsor SCC Values | Direct cost adjustments | Time-related direct cost adjustments (not inflation) | Latent Contingency Deductions (negative) | Total adjustment | PMOC Adjusted Estimate
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
10.01 | Guideway: At-grade exclusive right-of-way | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
10.03 | Guideway: At-grade in mixed traffic | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
10.04 | Guideway: Aerial structure | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
10.05 | Guideway: Built-up fill | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
10.06 | Guideway: Underground cut & cover | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
10.07 | Guideway: Underground tunnel | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
10.08 | Guideway: Retained cut or fill | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
10.09 | Track: Direct fixation | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
10.1 | Track: Embedded | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
10.11 | Track: Ballasted | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
10.12 | Track: Special (switches, turnouts) | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
10.13 | Track: Vibration and noise dampening | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
20.02 | Aerial station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
20.03 | Underground station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
20.05 | Joint development | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
20.06 | Automobile parking multi-story structure | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
20.07 | Elevators, escalators | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
30.01 | Administration Building: Office, sales, storage, revenue counting | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
30.02 | Light Maintenance Facility | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
30.03 | Heavy Maintenance Facility | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
30.04 | Storage or Maintenance of Way Building | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
30.05 | Yard and Yard Track | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
40 SITEWORK & SPECIAL CONDITIONS |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
40.01 | Demolition, Clearing, Earthwork | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
40.02 | Site Utilities, Utility Relocation | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
40.05 | Site structures including retaining walls, sound walls | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
40.06 | Pedestrian / bike access and accommodation, landscaping | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
40.07 | Automobile, bus, van accessways including roads, parking lots | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
40.08 | Temporary Facilities and other indirect costs during construction | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
50 SYSTEMS |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
50.01 | Train control and signals | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
50.02 | Traffic signals and crossing protection | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
50.03 | Traction power supply: substations | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
50.04 | Traction power distribution: catenary and third rail | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
50.05 | Communications | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
50.06 | Fare collection system and equipment | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
50.07 | Central Control | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Construction Subtotal (10 - 50) |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
60 ROW, LAND, EXISTING IMPROVEMENTS |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
60.01 | Purchase or lease of real estate | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
60.02 | Relocation of existing households and businesses | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
70 VEHICLES (number) |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
70.01 | Light Rail | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
70.02 | Heavy Rail | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
70.03 | Commuter Rail | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
70.04 | Bus | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
70.05 | Other | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
70.06 | Non-revenue vehicles | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
70.07 | Spare parts | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
80.01 | Project Development | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
80.02 | Engineering (not applicable to Small Starts) | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
80.03 | Project Management for Design and Construction | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
80.04 | Construction Administration & Management | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
80.05 | Professional Liability and other Non-Construction Insurance | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
80.07 | Surveys, Testing, Investigation, Inspection | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
80.08 | Start up | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Subtotal (10 - 80) |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Source files used
Place notes here.

## PMOC Globl Infl Adjst
This worksheet provides for adjustment to Sponsor cash flow or inflation rates. Original non-adjusted sponsor Base Year (BY) and Year of Expenditure (YOE) values from Sponsor SCC Workbook are pre-loaded in this worksheetin Column C. ** If no adjustment from Sponsor values is indicated, then copy and paste "Sponsor YOE Dollars" values into yellow cells. No further action is required. ** If there is a significant expected difference in Sponsor projected cash flow, or a significant expected difference in Sponsor future year inflation rates, then a global inflation adjustment may be required. Follow Steps 1-4. 1) Obtain original Sponsor SCC workbook. Without making adjustment to Sponsor future Base Year values, if necessary re-spread Sponsor base year expenditures from original Sponsor SCC workbook across time, based on PMOC analysis of schedule and schedule risk. Rename and keep adjusted Sponsor SCC workbook to document changes made. Adjustments to Sponsor base year direct cost are made separately in the PMOC BY Adj worksheet. 2) Within the same adjusted Sponsor SCC workbook as in Step 1, above, if necessary adjust inflation rates based on PMOC analysis. 3) Copy summary adjusted YOE SCC values obtained from the analysis in Steps 1 & 2, above, into the yellow cells of this worksheet. The PMOC inflation adjustment factors are automatically calculated. 4) Capture notes herein regarding rationale behind the PMOC changes, and name of PMOC-adjusted SCC workbook. Include those notes in the PMOC report.
Sponsor Base Yr Dollars
10 GUIDEWAY & TRACK ELEMENTS | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 0
40 SITEWORK & SPECIAL CONDITIONS | 0
50 SYSTEMS | 0
60 ROW, LAND, EXISTING IMPROVEMENTS | 0
70 VEHICLES | 0
80 PROFESSIONAL SERVICES | 0
90 UNALLOCATED CONTINGENCY | 0
100 FINANCE CHARGES | 0
Total Project Cost (10 - 100) | 0
YEAR OF EXPENDITURE DOLLARS (X$000) | Sponsor YOE Dollars | PMOC YOE Dollars
10 GUIDEWAY & TRACK ELEMENTS | 0 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL | 0 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 0 | 0
40 SITEWORK & SPECIAL CONDITIONS | 0 | 0
50 SYSTEMS | 0 | 0
60 ROW, LAND, EXISTING IMPROVEMENTS | 0 | 0
70 VEHICLES | 0 | 0
80 PROFESSIONAL SERVICES | 0 | 0
90 UNALLOCATED CONTINGENCY | 0 | 0
100 FINANCE CHARGES | 0 | 0
Total Project Cost (10 - 100) | 0 | 0
Inflation factor | Sponsor | PMOC | Infl Adjst
10 GUIDEWAY & TRACK ELEMENTS | 0 | 0 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL | 0 | 0 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 0 | 0 | 0
40 SITEWORK & SPECIAL CONDITIONS | 0 | 0 | 0
50 SYSTEMS | 0 | 0 | 0
60 ROW, LAND, EXISTING IMPROVEMENTS | 0 | 0 | 0
70 VEHICLES | 0 | 0 | 0
80 PROFESSIONAL SERVICES | 0 | 0 | 0
90 UNALLOCATED CONTINGENCY | 0 | 0 | 0
100 FINANCE CHARGES | 0 | 0 | 0
Total Project Cost (10 - 100) | 0 | 0 | 0
PMOC notes:
Place notes here.

## PMOC Profl Infl Adj
Project-wide inflation values are pre-loaded in the yellow cells from PMOC Global Infl Adj worksheet. * If only one Profile, any adjustments may be made in the PMOC Global Inflation adjustments tab. * If multiple risk profiles and if needed, change values to risk-profile specific inflation values; any such changes may likely require profile-specific inflation values across all risk profiles used. Note any file name used to calculate these values.
|  |  | Risk Profile (1) YOE | [6 empty] | Risk Profile (2) YOE | Risk Profile (2) | [5 empty] | Risk Profile (3) YOE | Risk Profile (3) | [5 empty] | Risk Profile (4) YOE | Risk Profile (4) | [5 empty] | Project Totals
|  | PMOC Adjusted project-wide inflation | PMOC Adjusted Risk Profile Inflation | Sponsor SCC Values | Direct cost adjustments | Time-related direct cost adjustments (not inflation) | Latent Contingency Deductions (negative) | Total adjustment | PMOC Adjusted Estimate | PMOC Adjusted Risk Profile Inflation | Sponsor SCC Values | Direct cost adjustments | Time-related direct cost adjustments (not inflation) | Latent Contingency Deductions (negative) | Total adjustment | PMOC Adjusted Estimate | PMOC Adjusted Risk Profile Inflation | Sponsor SCC Values | Direct cost adjustments | Time-related direct cost adjustments (not inflation) | Latent Contingency Deductions (negative) | Total adjustment | PMOC Adjusted Estimate | PMOC Adjusted Risk Profile Inflation | Sponsor SCC Values | Direct cost adjustments | Time-related direct cost adjustments (not inflation) | Latent Contingency Deductions (negative) | Total adjustment | PMOC Adjusted Estimate | Sponsor SCC Values | Direct cost adjustments | Duration adjustments (non-inflation) | Latent Contingency Adjustments Insert as negative value to subtract | Total adjustment | PMOC Adjusted YOE Estimate
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.01 | Guideway: At-grade exclusive right-of-way | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.03 | Guideway: At-grade in mixed traffic | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.04 | Guideway: Aerial structure | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.05 | Guideway: Built-up fill | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.06 | Guideway: Underground cut & cover | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.07 | Guideway: Underground tunnel | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.08 | Guideway: Retained cut or fill | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.09 | Track: Direct fixation | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.1 | Track: Embedded | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.11 | Track: Ballasted | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.12 | Track: Special (switches, turnouts) | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.13 | Track: Vibration and noise dampening | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20.02 | Aerial station, stop, shelter, mall, terminal, platform | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20.03 | Underground station, stop, shelter, mall, terminal, platform | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20.05 | Joint development | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20.06 | Automobile parking multi-story structure | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20.07 | Elevators, escalators | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30.01 | Administration Building: Office, sales, storage, revenue counting | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30.02 | Light Maintenance Facility | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30.03 | Heavy Maintenance Facility | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30.04 | Storage or Maintenance of Way Building | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30.05 | Yard and Yard Track | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 SITEWORK & SPECIAL CONDITIONS |  | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40.01 | Demolition, Clearing, Earthwork | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40.02 | Site Utilities, Utility Relocation | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40.05 | Site structures including retaining walls, sound walls | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40.06 | Pedestrian / bike access and accommodation, landscaping | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40.07 | Automobile, bus, van accessways including roads, parking lots | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40.08 | Temporary Facilities and other indirect costs during construction | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 SYSTEMS |  | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50.01 | Train control and signals | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50.02 | Traffic signals and crossing protection | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50.03 | Traction power supply: substations | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50.04 | Traction power distribution: catenary and third rail | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50.05 | Communications | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50.06 | Fare collection system and equipment | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50.07 | Central Control | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Subtotal (10 - 50) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 ROW, LAND, EXISTING IMPROVEMENTS |  | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60.01 | Purchase or lease of real estate | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60.02 | Relocation of existing households and businesses | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 VEHICLES (number) |  | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70.01 | Light Rail | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70.02 | Heavy Rail | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70.03 | Commuter Rail | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70.04 | Bus | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70.05 | Other | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70.06 | Non-revenue vehicles | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70.07 | Spare parts | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) |  | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80.01 | Project Development | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80.02 | Engineering (not applicable to Small Starts) | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80.03 | Project Management for Design and Construction | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80.04 | Construction Administration & Management | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80.05 | Professional Liability and other Non-Construction Insurance | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80.07 | Surveys, Testing, Investigation, Inspection | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80.08 | Start up | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal (10 - 80) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Place any notes here

## 4 - Risk A'ssment Instr
Beta Distribution Link - Click here.
Beta distribution function values
Risk curve parameter a= | 1.5
Risk curve parameter b= | 5.1
The above should not be changed without FTA approval
Instructions for:
Risk Assessment Worksheets:
The purpose of this section is to establish the range of risk for each of the SCC estimate line items developed in the previous PMOC YOE Adjustments worksheet.
The concept of this risk analysis is based upon an assumption that transit projects share a common pattern of uncertainty at various stages of project completion, which must be modified by the addition or decrease levels of risk due to project-specific circumstance or identified risk events. This analysis infers this uncertainty onto current projects, based upon discovered patterns of historic transit uncertainty. This methodology--based on a suite of historic projects--is termed a top-down risk analysis. The historic pattern of risk is described by a probability density function (see description to the right) that contains several factors; the key factor that varies is termed the Beta factor. In simple terms, the risk analyst must assign appropriate Beta factors to the project to represent this underlying uncertainty and the presence of project-specific conditions and risk.
Direction is provided in this risk analysis section for assignment of the appropriate Beta factors. Further direction is also provided in OP 40 and Beta factor assignment standards are provided in the appendix section at the end of this workbook. Care should be taken to assign values appropriately; particularly in reference to the SCC 60, 70, and 80 Beta amounts, which generally differ from those in SCC 10-50.
Four separate Risk Assessment worksheets are provided in order to assess the ranges of risk by Risk Profiles, determined the earlier estimate adjustments worksheets. If all four risk profiles have not been used, the Risk Assessment tabs for unused profiles may be hidden, to simplify this workbook.
The key steps for this section are:
* Set the cost basis:
--Ensure Lower Bound values (from the PMOC YOE Adjustments tab) have been properly transferred from the PMOC Adjusted Estimate tab to the Risk Assessment tabs.
* Establish base uncertainty level
--Account for general project uncertainty by populating the Beta factor fields for each SCC line item from standards in the workbook. Refer to the Beta Selections Instruction tab for a discussion of establishing these standard values for all SCCs by risk profile in this workbook.
* Account for project-specific conditions and risks
--Adjust for project-specific conditions and specific risks by assessing and adjusting the uncertainty Beta factor values for each SCC line item and risk type. Refer to the Project-specific Beta Instruction tab for a discussion of establishing these values for all SCCs by risk type in this workbook.
--Assess and input project-specific SCC 10-50 global adjustments for each risk category of Requirements, Design, Market, and Construction, based on project-specific conditions and specific risks. Refer to the Project-specific Beta Instruction tab for a discussion of making these adjustments.
* Repeat the process for each risk profile (if multiple risk profiles).
These risk adjustments by risk profile are consolidated in the project-level Risk Assessment Total tab.
The tabs in the appendix worksheets section at the end of this workbook provide data for use in the risk assessment portions of the model. Three sets of tabs are included:
* Design-Bid-Build Beta standard for SCC 10-80,
* Project-specific risk event partial Beta calculations, and
* Separate tabs for customized SCC 10-50, SCC 60-70, and SCC 80 Beta calculations.
The use of these tabs are described in the Base Uncertainty and Project-specific Risk instructions that follow.
The Beta Distribution
The Probability Density Function used in the FTA risk model is based on the generalized Beta Distribution. This distribution is described in the online NIST Engineering Statistics Handbook (link below) and elsewhere.
There are four parameters involved, the Lower Bound and Upper Bound and two shape parameters, a & b.
The width of the curve is defined by the lower and upper bound values:
--Lower Bound = Sponsor estimate, stripped of contingencies and amended by PMOC adjustments, and
--Upper Bound = Lower Bound * Beta value.
The shape of the curve is defined by two shape parameters, a & b. These shape parameters have been established to mimic the historic distribution of risk on FTA transit projects. The values of these parameters are indicated below.

## Base Uncertainty Instructions
Instructions for Establishing Base Uncertainty:
Note: Establishing total risk is a two-step process: 1) Determing a base level of historic uncertainty for a "typical" similar project, and 2) Determing adjustments to that base, evaluated using consideration of a projects risk increase or decrease as understood through evaluation of the project specifics.
The next worksheet contains instructions regarding establishing Beta factors for project-specific risk.
The appendix section at the end of this workbook contains worksheet tables and calculators that are used in the process of establishing the project's base uncertainty:
* DBB CMGC Beta Uncertainty Standards for SCC 10-80, and
* Separate tabs for customized SCC 10-50, SCC 60-70, and SCC 80 Beta Calculations.
Beta choices in the appendices:
Beta drawdown tables, graphs, and calculation models are provided for assistance in evaluating a Total Beta value for a variety of SCC prime- and sub-categories.
Total Beta is the sum of partial Beta values for types of project risk (for SCC 10-50, those types are: Requirements, Design, Market, Construction and Post-construction). The Beta tables, graphs, and calculation models provide a means to establish the partial Beta values for a particular SCC at a particular phase of development. The Beta values are based on historic records of cost uncertainty on projects.
Beta value determinations are made in four general categories of project scope, with related historic levels of uncertainty:
* Civil and Systems (SCC 10-50),
* Real Estate (SCC 60),
* Vehicles (SCC70), and
* Professional Services (SCC 80).
It is intended that the initial assignment of Beta values establishes the general level of uncertainty for a particular project for a category of scope, as outlined above. The OP40 guidance provides additional detailed information regarding the application of Beta values for the various scope categories and for situations of differing project delivery methods and for large "mega" projects.
For projects that occur in multiple risk profiles (distinct phases, or segments, etc.), these Beta value assignments should thoughtfully occur independently for each risk profile.
DBB CMGC Beta Standards worksheet:
Design-Bid-Build (DBB) projects are often similar to Construction Manager-General Contractor (CMGC) projects, in that the project design is separately, fully developed by an independent designer and the construction pricing is based on these fully designed documents. For discussion of potential differences between the two forms of project delivery, see OP40. The DBB CMGC Beta Standards worksheet provides a starting point for evaluation of projects of these delivery types. A table is provided that indicates which Beta values to apply for each scope category at several key phases of project development. The Beta values represent uncertainty that is retained by the Sponsor at the various stages of project development. The table presumes a standard level of progression for SCCs 60-80 in concert with the design, market, or construction progression of the SCC 10-50 elements.
These Beta values are valid starting points, based on historical values for DBB and CMGC projects. They are also potential starting points for other project types, such as Design-build (and similar) when the project is in its earliest phases, before finalizing a contract with the Design-Builder. As indicated in the OP40 guidance, these values are to be amended appropriately based upon a reasonable evaluation of the specific project's conditions and risks.
Once the appropriate levels of partial Betas is determined, the risk analyst should transfer the values to the appropriate Risk Assessment tab, repeating for each risk profile used.
This step is followed by amending these uncertainty levels base on project-specific risks and conditions. The following Project-specific Risk Instructions tab provides guidance for this step.
SCC 10-50, SCC 60-70, and SCC 80 Beta worksheets:
While the DBB CMGC Beta Standards tab provides a starting point for many projects, some projects may exist in multiple risk profiles with sequencing that does not follow a "typical" pattern of design-bid-build progression, or which may progress real estate or vehicles acquisition, or professional services progressions that do not follow the pattern indicated in the DBB CMGC Beta Standards tab tables.
In this case, the SCC 10-50, SCC 60-70, and SCC 80 Beta worksheets are provided that allow for customization of the uncertainty partial Betas by progression of the various SCC 10-50, SCC 60-70, and SCC 80 segments of the project. These evaluations are made by indicating levels of progression for each of these SCC segments in the appropriate tab, and then transferring the partial Betas to the Risk Assessment tabs for the risk profile under evaluation.
It is worthy of note that a combination of using results from the DBB CMGC Beta Standards worksheet and the SCC 10-50, SCC 60-70, and SCC 80 Beta worksheets may be appropriate. For example, the SCC 10-50, SCC 60, and SCC 80 Betas and may be chosen from the DBB CMGC Beta Standards tab, while the SCC 70 Betas may be uniquely chosen from the SCC 60-70 Beta Calculations tab, if it is determined that the Vehicle segment does not follow a "typical" pattern related to the progression of the rest of the work.
Once the appropriate levels of partial Betas is determined, the risk analyst should transfer the values to the appropriate Risk Assessment tab, repeating for each risk profile used.
This step is followed by amending these uncertainty levels base on project-specific risks and conditions. The following Project-specific Risk Instructions worksheet provides guidance for this step.
Applying Beta values for non-DBB projects--Non-DBB/CMGC projects such as Design-Build (DB), Public Private Partnerships (PPPs), etc. require adjustment from the standards provided in the Beta DBB CMGC Standards tab. Identified historic patterns of Beta values are not currently available, so each evaluator must judge the appropriate adjustment. OP40 provides guidance on considerations for the various project delivery methods.
The following worksheets are provided for detailed consideration of risk in non-standard DBB/CMGC projects; these tools may be helpful in creating more complex contracting circumstances:
* SCC10-50 Beta calculations
* SCC60-70 Beta calculations
* SCC80 Beta calculations.
The basis of adjustment revolves around the consideration of risk retained by the Sponsor. The Sponsor retains project risk until risk is contractually transferred and the market value for that contractual transfer is included within the project estimate.
In the case of DBB, design risk is transferred to some degree to the designer at the point of contracting with the designer, and construction risk is transferred to some degree at the point of contracting with the constructor; standard contractual clauses do not fully transfer all risk and some risk continues to remain with the Sponsor in either case. The DBB tables are correlated with the timing of those transfers and the remainder of risk retained by the Sponsor. Further, the Sponsor retains the risks associated with either constructor or designer claiming error on behalf of the other--claims that pass through the Sponsor and result in risk to the Sponsor within the DBB system.
CM contracting will generally maintain similar risk drawdown characteristics as with DBB, since the timing of design contracts and of construction contracts are similar; even though the constructor may be contracted during the design phase for professional services, construction risk may not be transferred until the constructor prices and contracts for the actual construction work. The likelihood of concurrent design and construction activity occurs with the CM process, thus the potential for multiple risk profiles exists.
In both DB and PPP contracts, it is often the case that some amount of construction risk is transferred at an earlier phase of project development than in DBB, since construction is priced and contracted during the design phase. Further, in these project styles the Sponsor is sheltered from risks associated with claims related to harm caused to designer or constructor by each other. In both DB and PPP, it should be considered that risk is not actually transferred (and thus Beta values reduced) until the DB or PPP contract has been priced and included in the estimate. Until the risk is transferred through the establishment of a market bid that is contractible and included in the estimate, the sponsor continues to retain the cost risk and therefore the values included in the DBB Standards tables, adjusted for project conditions, should be used. However, once the market-base bid prices are incorporated into the project estimate, then the DBB Beta values should be appropriately discounted.
Discounting the Beta values depends considerably on the contractual provisions included in the DB or PPP contract. Care should be taken to scrutinize the proposed contract to expose those areas where the Sponsor remains at risk. An example may be that a Sponsor retains the risk for unexpected discovery of contaminated soils. Where the Sponsor retains such risks, the Beta values must continue to reflect the Sponsor's retained risk. Since many of the risks that a Sponsor may retain are commonly retained under a typical DBB contract, there may be little reason to significantly reduce the DBB Standard Beta values.
Discounting the Beta values also depends upon the relationship between the designers and the constructors in either a DB or a PPP relationship. In this case, it is quite common that a Sponsor would be significantly shielded from errors that affect either party in the designer-constructor relationship. Therefore, some reasonable reduction in the Design Beta value may be called for. However, the Sponsor may continue to retain Design risk due to risk that is carried in the preliminary design documents that are provided to the DB contracting entity as the basis of the contract bids. Such documents may contain assumptions, errors, or other issues that result in contract adjustments to the design builder--in effect creating cost risk for the Sponsor. Therefore, in most circumstances it would be likely that the design risk could not be completely removed.

## Project-specific Risk Inst
Instructions for:
Project-specific Partial Beta Adjustments
Note: Establishing total risk is a two-step process: 1) Determing a base level of historic uncertainty for a "typical" similar project, and 2) Determing adjustments to that base, evaluated using consideration of a projects risk increase or decrease as understood through evaluation of the project specifics.
The prior worksheet contains instructions regarding establishing Beta factors for project uncertainty.
Once the general levels of project uncertainty have been established by risk profile through the process described in the Beta Uncertainty Instructions worksheet, the uncertainty Betas must be adjusted to reflect specific project conditions that are not covered by the uncertainty Beta assignments with adjustments (increases or decreases) based upon knowledge gained regarding the specific circumstances and expected risks on the project.
This is accomplished by evaluating conditions based on understanding of specific project risks or other project-specific factors that adds or deducts partial Beta factor values to the previously established uncertainty partial Beta values. A calculator for establishing Beta factor adjustments is provided in the Project-Specific Risk Calculations worksheet in the appendices portion at the end of this workbook; other calculations may be developed outside of this workbook. In the circmstance that a specific Beta adjustment should be made, the calculated Beta adjustment should be recorded in the appropriate column of the Risk Assessment (x) worksheets.
Global Beta Adjustments
Further, it has been found that many project-specific conditions or risks adjustments may apply globally across all of the SCC 10-50 categories. The SCC 10-50 Beta Calculations worksheet provides a means to spread these adjustments across those SCC categories. These adjustments may be calculated using the Project-Specific Risk Calculations worksheet .
Other bases for partial Beta values may be used by the risk analyst. If so, these calculations should be documented. Such alternative calculations may be inserted in this risk workbook as a new worksheet.
Instructions are provided in the Project-specifics Risk Calculations worksheet for determining these values.
Where project-specific adjustments are made in the Risk Assessment worksheet(s), a short comment regarding the reasoning for the change should be documented as indicated on the Risk Assessment worksheet(s).
When the Beta assignments and adjustments have been completed for each project profile, the Risk Assessment Total worksheet provides summary information for the project as a whole.

## Risk Assessment (1)
Risk Assessment (1): Refer to Base Uncertainty and Project-specific Instructions worksheets and OP40 before completing this worksheet; 1) Enter uncertainty Beta values from addenda in the workbook, based on risk profile progress; 2) Enter Specific Risk Beta changes to individual SCC/Risk Types, by assessing Beta values using the Project-Specific Risk worksheet or other method; 3) Note reasons for changes in the Adjustment comments column
Transit project |  |  | Requirements |  |  | Design |  |  | Market |  |  | Construction |  |  | Post-construction
SCC | Category | Lower bound | Uncer- tainty | Spec. risk | Adj Req'ts Beta | Uncer- tainty | Spec. risk | Adj Dsgn Beta | Uncer- tainty | Spec. risk | Adj Dsgn Beta | Uncer- tainty | Spec. risk | Adj Constr Beta | Uncer- tainty | Spec. risk | Adj Post Beta | Adjustment comments | Total Beta | Upper bound | Categorical median | Categorical mean | Likelihood | Modeled cost |  | Modeled cost | Cum % | Incr %
10 GUIDEWAY & TRACK ELEMENTS (route miles) | [22 empty] | 0% | 0 |  | 0 | #NUM! | #NUM!
10.01 | Guideway: At-grade exclusive right-of-way | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 10% | 0 |  | 0 | #NUM! | #NUM!
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 20% | 0 |  | 0 | #NUM! | #NUM!
10.03 | Guideway: At-grade in mixed traffic | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 30% | 0 |  | 0 | #NUM! | #NUM!
10.04 | Guideway: Aerial structure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 40% | 0 |  | 0 | #NUM! | #NUM!
10.05 | Guideway: Built-up fill | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 50% | 0 |  | 0 | #NUM! | #NUM!
10.06 | Guideway: Underground cut & cover | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 60% | 0 |  | 0 | #NUM! | #NUM!
10.07 | Guideway: Underground tunnel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 65% | 0 |  | 0 | #NUM! | #NUM!
10.08 | Guideway: Retained cut or fill | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 70% | 0 |  | 0 | #NUM! | #NUM!
10.09 | Track: Direct fixation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 80% | 0 |  | 0 | #NUM! | #NUM!
10.1 | Track: Embedded | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 90% | 0 |  | 0 | #NUM! | #NUM!
10.11 | Track: Ballasted | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 100% | 0
10.12 | Track: Special (switches, turnouts) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
10.13 | Track: Vibration and noise dampening | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 40% | 0 | <<< Lower reporting range
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 65% | 0 | <<< Contingency target
20.02 | Aerial station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 80% | 0 | <<< Upper reporting range
20.03 | Underground station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
20.05 | Joint development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
20.06 | Automobile parking multi-story structure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
20.07 | Elevators, escalators | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30.01 | Administration Building: Office, sales, storage, revenue counting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
30.02 | Light Maintenance Facility | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
30.03 | Heavy Maintenance Facility | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
30.04 | Storage or Maintenance of Way Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
30.05 | Yard and Yard Track | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
40 SITEWORK & SPECIAL CONDITIONS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40.01 | Demolition, Clearing, Earthwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
40.02 | Site Utilities, Utility Relocation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
40.05 | Site structures including retaining walls, sound walls | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
40.06 | Pedestrian / bike access and accommodation, landscaping | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
40.07 | Automobile, bus, van accessways including roads, parking lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
40.08 | Temporary Facilities and other indirect costs during construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
50 SYSTEMS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50.01 | Train control and signals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
50.02 | Traffic signals and crossing protection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
50.03 | Traction power supply: substations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
50.04 | Traction power distribution: catenary and third rail | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
50.05 | Communications | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
50.06 | Fare collection system and equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
50.07 | Central Control | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
/\ /\ /\ Global adjustment are applied above /\ /\ /\
60 ROW, LAND, EXISTING IMPROVEMENTS |  |  | \/ \/ \/ Global adjustments are not applied below \/ \/ \/
60.01 | Purchase or lease of real estate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
60.02 | Relocation of existing households and businesses | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
70 VEHICLES (number)
70.01 | Light Rail | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
70.02 | Heavy Rail | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
70.03 | Commuter Rail | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
70.04 | Bus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
70.05 | Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
70.06 | Non-revenue vehicles | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
70.07 | Spare parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50)
80.01 | Project Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
80.02 | Engineering (not applicable to Small Starts) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
80.03 | Project Management for Design and Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
80.04 | Construction Administration & Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
80.05 | Professional Liability and other Non-Construction Insurance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
80.07 | Surveys, Testing, Investigation, Inspection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
80.08 | Start up | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
| Project values>>>> | 0 | [16 empty] | 0 | 0 | 0 | 0
|  | Lwrbnd | [16 empty] | Beta | Uprbnd | Median | Mean
| Global SCC10-50 Req'ts Beta adjustment>>>> |  |  |  | 0
| Global SCC10-50 Dsgn Beta adjustment>>>> | [6 empty] | 0
| Global SCC10-50 Mkt Beta adjustment>>>> | [9 empty] | 0
| Global SCC10-50 Constr Beta adjustment>>>> | [12 empty] | 0
0

## Risk Assessment (2)
Risk Assessment (2): Refer to Base Uncertainty and Project-specific Instructions worksheets and OP40 before completing this worksheet; 1) Enter uncertainty Beta values from addenda in the workbook, based on risk profile progress; 2) Enter Specific Risk Beta changes to individual SCC/Risk Types, by assessing Beta values using the Project-Specific Risk worksheet or other method; 3) Note reasons for changes in the Adjustment comments column
Not Used |  |  | Requirements |  |  | Design |  |  | Market |  |  | Construction |  |  | Post-construction
SCC | Category | Lower bound | Uncer- tainty | Spec. risk | Adj Req'ts Beta | Uncer- tainty | Spec. risk | Adj Dsgn Beta | Uncer- tainty | Spec. risk | Adj Dsgn Beta | Uncer- tainty | Spec. risk | Adj Constr Beta | Uncer- tainty | Spec. risk | Adj Post Beta | Adjustment comments | Total Beta | Upper bound | Categorical median | Categorical mean | Likelihood | Modeled cost |  | Modeled cost | Cum % | Incr %
10 GUIDEWAY & TRACK ELEMENTS (route miles) | [22 empty] | 0% | 0 |  | 0 | #NUM! | #NUM!
10.01 | Guideway: At-grade exclusive right-of-way | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 10% | 0 |  | 0 | #NUM! | #NUM!
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 20% | 0 |  | 0 | #NUM! | #NUM!
10.03 | Guideway: At-grade in mixed traffic | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 30% | 0 |  | 0 | #NUM! | #NUM!
10.04 | Guideway: Aerial structure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 40% | 0 |  | 0 | #NUM! | #NUM!
10.05 | Guideway: Built-up fill | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 50% | 0 |  | 0 | #NUM! | #NUM!
10.06 | Guideway: Underground cut & cover | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 60% | 0 |  | 0 | #NUM! | #NUM!
10.07 | Guideway: Underground tunnel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 65% | 0 |  | 0 | #NUM! | #NUM!
10.08 | Guideway: Retained cut or fill | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 70% | 0 |  | 0 | #NUM! | #NUM!
10.09 | Track: Direct fixation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 80% | 0 |  | 0 | #NUM! | #NUM!
10.1 | Track: Embedded | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 90% | 0 |  | 0 | #NUM! | #NUM!
10.11 | Track: Ballasted | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 100% | 0
10.12 | Track: Special (switches, turnouts) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
10.13 | Track: Vibration and noise dampening | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 40% | 0 | <<< Lower reporting range
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 65% | 0 | <<< Contingency target
20.02 | Aerial station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 80% | 0 | <<< Upper reporting range
20.03 | Underground station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
20.05 | Joint development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
20.06 | Automobile parking multi-story structure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
20.07 | Elevators, escalators | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30.01 | Administration Building: Office, sales, storage, revenue counting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
30.02 | Light Maintenance Facility | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
30.03 | Heavy Maintenance Facility | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
30.04 | Storage or Maintenance of Way Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
30.05 | Yard and Yard Track | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
40 SITEWORK & SPECIAL CONDITIONS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40.01 | Demolition, Clearing, Earthwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
40.02 | Site Utilities, Utility Relocation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
40.05 | Site structures including retaining walls, sound walls | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
40.06 | Pedestrian / bike access and accommodation, landscaping | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
40.07 | Automobile, bus, van accessways including roads, parking lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
40.08 | Temporary Facilities and other indirect costs during construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
50 SYSTEMS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50.01 | Train control and signals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
50.02 | Traffic signals and crossing protection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
50.03 | Traction power supply: substations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
50.04 | Traction power distribution: catenary and third rail | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
50.05 | Communications | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
50.06 | Fare collection system and equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
50.07 | Central Control | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
/\ /\ /\ Global adjustment are applied above /\ /\ /\
60 ROW, LAND, EXISTING IMPROVEMENTS |  |  | \/ \/ \/ Global adjustments are not applied below \/ \/ \/
60.01 | Purchase or lease of real estate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
60.02 | Relocation of existing households and businesses | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
70 VEHICLES (number)
70.01 | Light Rail | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
70.02 | Heavy Rail | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
70.03 | Commuter Rail | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
70.04 | Bus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
70.05 | Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
70.06 | Non-revenue vehicles | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
70.07 | Spare parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50)
80.01 | Project Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
80.02 | Engineering (not applicable to Small Starts) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
80.03 | Project Management for Design and Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
80.04 | Construction Administration & Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
80.05 | Professional Liability and other Non-Construction Insurance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
80.07 | Surveys, Testing, Investigation, Inspection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
80.08 | Start up | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
| Project values>>>> | 0 | [16 empty] | 0 | 0 | 0 | 0
|  | Lwrbnd | [16 empty] | Beta | Uprbnd | Median | Mean
| Global SCC10-50 Req'ts Beta adjustment>>>> |  |  |  | 0
| Global SCC10-50 Dsgn Beta adjustment>>>> | [6 empty] | 0
| Global SCC10-50 Mkt Beta adjustment>>>> | [9 empty] | 0
| Global SCC10-50 Constr Beta adjustment>>>> | [12 empty] | 0

## Risk Assessment (3)
Risk Assessment (3): Refer to Base Uncertainty and Project-specific Instructions worksheets and OP40 before completing this worksheet; 1) Enter uncertainty Beta values from addenda in the workbook, based on risk profile progress; 2) Enter Specific Risk Beta changes to individual SCC/Risk Types, by assessing Beta values using the Project-Specific Risk worksheet or other method; 3) Note reasons for changes in the Adjustment comments column
Not Used |  |  | Requirements |  |  | Design |  |  | Market |  |  | Construction |  |  | Post-construction
SCC | Category | Lower bound | Uncer- tainty | Spec. risk | Adj Req'ts Beta | Uncer- tainty | Spec. risk | Adj Dsgn Beta | Uncer- tainty | Spec. risk | Adj Dsgn Beta | Uncer- tainty | Spec. risk | Adj Constr Beta | Uncer- tainty | Spec. risk | Adj Post Beta | Adjustment comments | Total Beta | Upper bound | Categorical median | Categorical mean | Likelihood | Modeled cost |  | Modeled cost | Cum % | Incr %
10 GUIDEWAY & TRACK ELEMENTS (route miles) | [22 empty] | 0% | 0 |  | 0 | #NUM! | #NUM!
10.01 | Guideway: At-grade exclusive right-of-way | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 10% | 0 |  | 0 | #NUM! | #NUM!
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 20% | 0 |  | 0 | #NUM! | #NUM!
10.03 | Guideway: At-grade in mixed traffic | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 30% | 0 |  | 0 | #NUM! | #NUM!
10.04 | Guideway: Aerial structure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 40% | 0 |  | 0 | #NUM! | #NUM!
10.05 | Guideway: Built-up fill | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 50% | 0 |  | 0 | #NUM! | #NUM!
10.06 | Guideway: Underground cut & cover | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 60% | 0 |  | 0 | #NUM! | #NUM!
10.07 | Guideway: Underground tunnel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 65% | 0 |  | 0 | #NUM! | #NUM!
10.08 | Guideway: Retained cut or fill | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 70% | 0 |  | 0 | #NUM! | #NUM!
10.09 | Track: Direct fixation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 80% | 0 |  | 0 | #NUM! | #NUM!
10.1 | Track: Embedded | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 90% | 0 |  | 0 | #NUM! | #NUM!
10.11 | Track: Ballasted | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 100% | 0
10.12 | Track: Special (switches, turnouts) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
10.13 | Track: Vibration and noise dampening | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 40% | 0 | <<< Lower reporting range
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 65% | 0 | <<< Contingency target
20.02 | Aerial station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 80% | 0 | <<< Upper reporting range
20.03 | Underground station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
20.05 | Joint development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
20.06 | Automobile parking multi-story structure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
20.07 | Elevators, escalators | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30.01 | Administration Building: Office, sales, storage, revenue counting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
30.02 | Light Maintenance Facility | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
30.03 | Heavy Maintenance Facility | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
30.04 | Storage or Maintenance of Way Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
30.05 | Yard and Yard Track | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
40 SITEWORK & SPECIAL CONDITIONS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40.01 | Demolition, Clearing, Earthwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
40.02 | Site Utilities, Utility Relocation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
40.05 | Site structures including retaining walls, sound walls | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
40.06 | Pedestrian / bike access and accommodation, landscaping | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
40.07 | Automobile, bus, van accessways including roads, parking lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
40.08 | Temporary Facilities and other indirect costs during construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
50 SYSTEMS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50.01 | Train control and signals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
50.02 | Traffic signals and crossing protection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
50.03 | Traction power supply: substations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
50.04 | Traction power distribution: catenary and third rail | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
50.05 | Communications | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
50.06 | Fare collection system and equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
50.07 | Central Control | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
/\ /\ /\ Global adjustment are applied above /\ /\ /\
60 ROW, LAND, EXISTING IMPROVEMENTS |  |  | \/ \/ \/ Global adjustments are not applied below \/ \/ \/
60.01 | Purchase or lease of real estate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
60.02 | Relocation of existing households and businesses | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
70 VEHICLES (number)
70.01 | Light Rail | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
70.02 | Heavy Rail | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
70.03 | Commuter Rail | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
70.04 | Bus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
70.05 | Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
70.06 | Non-revenue vehicles | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
70.07 | Spare parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50)
80.01 | Project Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
80.02 | Engineering (not applicable to Small Starts) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
80.03 | Project Management for Design and Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
80.04 | Construction Administration & Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
80.05 | Professional Liability and other Non-Construction Insurance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
80.07 | Surveys, Testing, Investigation, Inspection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
80.08 | Start up | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
| Project values>>>> | 0 | [16 empty] | 0 | 0 | 0 | 0
|  | Lwrbnd | [16 empty] | Beta | Uprbnd | Median | Mean
| Global SCC10-50 Req'ts Beta adjustment>>>> |  |  |  | 0
| Global SCC10-50 Dsgn Beta adjustment>>>> | [6 empty] | 0
| Global SCC10-50 Mkt Beta adjustment>>>> | [9 empty] | 0
| Global SCC10-50 Constr Beta adjustment>>>> | [12 empty] | 0

## Risk Assessment (4)
Risk Assessment (4): Refer to Base Uncertainty and Project-specific Instructions worksheets and OP40 before completing this worksheet; 1) Enter uncertainty Beta values from addenda in the workbook, based on risk profile progress; 2) Enter Specific Risk Beta changes to individual SCC/Risk Types, by assessing Beta values using the Project-Specific Risk worksheet or other method; 3) Note reasons for changes in the Adjustment comments column
Not used |  |  | Requirements |  |  | Design |  |  | Market |  |  | Construction |  |  | Post-construction
SCC | Category | Lower bound | Uncer- tainty | Spec. risk | Adj Req'ts Beta | Uncer- tainty | Spec. risk | Adj Dsgn Beta | Uncer- tainty | Spec. risk | Adj Dsgn Beta | Uncer- tainty | Spec. risk | Adj Constr Beta | Uncer- tainty | Spec. risk | Adj Post Beta | Adjustment comments | Total Beta | Upper bound | Categorical median | Categorical mean | Likelihood | Modeled cost |  | Modeled cost | Cum % | Incr %
10 GUIDEWAY & TRACK ELEMENTS (route miles) | [22 empty] | 0% | 0 |  | 0 | #NUM! | #NUM!
10.01 | Guideway: At-grade exclusive right-of-way | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 10% | 0 |  | 0 | #NUM! | #NUM!
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 20% | 0 |  | 0 | #NUM! | #NUM!
10.03 | Guideway: At-grade in mixed traffic | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 30% | 0 |  | 0 | #NUM! | #NUM!
10.04 | Guideway: Aerial structure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 40% | 0 |  | 0 | #NUM! | #NUM!
10.05 | Guideway: Built-up fill | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 50% | 0 |  | 0 | #NUM! | #NUM!
10.06 | Guideway: Underground cut & cover | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 60% | 0 |  | 0 | #NUM! | #NUM!
10.07 | Guideway: Underground tunnel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 65% | 0 |  | 0 | #NUM! | #NUM!
10.08 | Guideway: Retained cut or fill | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 70% | 0 |  | 0 | #NUM! | #NUM!
10.09 | Track: Direct fixation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 80% | 0 |  | 0 | #NUM! | #NUM!
10.1 | Track: Embedded | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 90% | 0 |  | 0 | #NUM! | #NUM!
10.11 | Track: Ballasted | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 100% | 0
10.12 | Track: Special (switches, turnouts) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
10.13 | Track: Vibration and noise dampening | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 40% | 0 | <<< Lower reporting range
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 65% | 0 | <<< Contingency target
20.02 | Aerial station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 80% | 0 | <<< Upper reporting range
20.03 | Underground station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
20.05 | Joint development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
20.06 | Automobile parking multi-story structure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
20.07 | Elevators, escalators | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30.01 | Administration Building: Office, sales, storage, revenue counting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
30.02 | Light Maintenance Facility | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
30.03 | Heavy Maintenance Facility | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
30.04 | Storage or Maintenance of Way Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
30.05 | Yard and Yard Track | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
40 SITEWORK & SPECIAL CONDITIONS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40.01 | Demolition, Clearing, Earthwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
40.02 | Site Utilities, Utility Relocation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
40.05 | Site structures including retaining walls, sound walls | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
40.06 | Pedestrian / bike access and accommodation, landscaping | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
40.07 | Automobile, bus, van accessways including roads, parking lots | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
40.08 | Temporary Facilities and other indirect costs during construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
50 SYSTEMS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50.01 | Train control and signals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
50.02 | Traffic signals and crossing protection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
50.03 | Traction power supply: substations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
50.04 | Traction power distribution: catenary and third rail | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
50.05 | Communications | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
50.06 | Fare collection system and equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
50.07 | Central Control | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
/\ /\ /\ Global adjustment are applied above /\ /\ /\
60 ROW, LAND, EXISTING IMPROVEMENTS |  |  | \/ \/ \/ Global adjustments are not applied below \/ \/ \/
60.01 | Purchase or lease of real estate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
60.02 | Relocation of existing households and businesses | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
70 VEHICLES (number)
70.01 | Light Rail | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
70.02 | Heavy Rail | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
70.03 | Commuter Rail | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
70.04 | Bus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
70.05 | Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
70.06 | Non-revenue vehicles | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
70.07 | Spare parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50)
80.01 | Project Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
80.02 | Engineering (not applicable to Small Starts) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
80.03 | Project Management for Design and Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
80.04 | Construction Administration & Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
80.05 | Professional Liability and other Non-Construction Insurance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
80.07 | Surveys, Testing, Investigation, Inspection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
80.08 | Start up | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0
| Project values>>>> | 0 | [16 empty] | 0 | 0 | 0 | 0
|  | Lwrbnd | [16 empty] | Beta | Uprbnd | Median | Mean
| Global SCC10-50 Req'ts Beta adjustment>>>> |  |  |  | 0
| Global SCC10-50 Dsgn Beta adjustment>>>> | [6 empty] | 0
| Global SCC10-50 Mkt Beta adjustment>>>> | [9 empty] | 0
| Global SCC10-50 Constr Beta adjustment>>>> | [12 empty] | 0

## Additional Profiles
Additional Profiles: This worksheet is provided to expand beyond the prime workbook profiles 1-4. Additional profiles may be added by deriving values using an addendum risk workbook, and including results on this and the 'Risk Assessment Analysis' tabs. Instructions are provided in the Baseline Adjustments Instr worksheet. It is the responsibility of the risk modeler to ensure that all final totals match the entire project. Note that the values transferred from the addendum risk workbook already include any global risk factor adjustmentsand are not explicitly shown here.
Insert values only in yellow highlighted cells from 'Risk Assessment Totals' tab of addendum risk workbook.
SCC | Category | Lower bound | Adj Req'ts Beta | Adj Dsgn Beta | Adj Mkt Beta | Adj Constr Beta | Post Constr Beta
10 GUIDEWAY & TRACK ELEMENTS (route miles)
10.01 | Guideway: At-grade exclusive right-of-way | 0 | 0 | 0 | 0 | 0 | 0
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | 0 | 0 | 0 | 0 | 0 | 0
10.03 | Guideway: At-grade in mixed traffic | 0 | 0 | 0 | 0 | 0 | 0
10.04 | Guideway: Aerial structure | 0 | 0 | 0 | 0 | 0 | 0
10.05 | Guideway: Built-up fill | 0 | 0 | 0 | 0 | 0 | 0
10.06 | Guideway: Underground cut & cover | 0 | 0 | 0 | 0 | 0 | 0
10.07 | Guideway: Underground tunnel | 0 | 0 | 0 | 0 | 0 | 0
10.08 | Guideway: Retained cut or fill | 0 | 0 | 0 | 0 | 0 | 0
10.09 | Track: Direct fixation | 0 | 0 | 0 | 0 | 0 | 0
10.1 | Track: Embedded | 0 | 0 | 0 | 0 | 0 | 0
10.11 | Track: Ballasted | 0 | 0 | 0 | 0 | 0 | 0
10.12 | Track: Special (switches, turnouts) | 0 | 0 | 0 | 0 | 0 | 0
10.13 | Track: Vibration and noise dampening | 0 | 0 | 0 | 0 | 0 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number)
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 | 0 | 0 | 0
20.02 | Aerial station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 | 0 | 0 | 0
20.03 | Underground station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 | 0 | 0 | 0
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. | 0 | 0 | 0 | 0 | 0 | 0
20.05 | Joint development | 0 | 0 | 0 | 0 | 0 | 0
20.06 | Automobile parking multi-story structure | 0 | 0 | 0 | 0 | 0 | 0
20.07 | Elevators, escalators | 0 | 0 | 0 | 0 | 0 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS
30.01 | Administration Building: Office, sales, storage, revenue counting | 0 | 0 | 0 | 0 | 0 | 0
30.02 | Light Maintenance Facility | 0 | 0 | 0 | 0 | 0 | 0
30.03 | Heavy Maintenance Facility | 0 | 0 | 0 | 0 | 0 | 0
30.04 | Storage or Maintenance of Way Building | 0 | 0 | 0 | 0 | 0 | 0
30.05 | Yard and Yard Track | 0 | 0 | 0 | 0 | 0 | 0
40 SITEWORK & SPECIAL CONDITIONS
40.01 | Demolition, Clearing, Earthwork | 0 | 0 | 0 | 0 | 0 | 0
40.02 | Site Utilities, Utility Relocation | 0 | 0 | 0 | 0 | 0 | 0
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments | 0 | 0 | 0 | 0 | 0 | 0
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks | 0 | 0 | 0 | 0 | 0 | 0
40.05 | Site structures including retaining walls, sound walls | 0 | 0 | 0 | 0 | 0 | 0
40.06 | Pedestrian / bike access and accommodation, landscaping | 0 | 0 | 0 | 0 | 0 | 0
40.07 | Automobile, bus, van accessways including roads, parking lots | 0 | 0 | 0 | 0 | 0 | 0
40.08 | Temporary Facilities and other indirect costs during construction | 0 | 0 | 0 | 0 | 0 | 0
50 SYSTEMS
50.01 | Train control and signals | 0 | 0 | 0 | 0 | 0 | 0
50.02 | Traffic signals and crossing protection | 0 | 0 | 0 | 0 | 0 | 0
50.03 | Traction power supply: substations | 0 | 0 | 0 | 0 | 0 | 0
50.04 | Traction power distribution: catenary and third rail | 0 | 0 | 0 | 0 | 0 | 0
50.05 | Communications | 0 | 0 | 0 | 0 | 0 | 0
50.06 | Fare collection system and equipment | 0 | 0 | 0 | 0 | 0 | 0
50.07 | Central Control | 0 | 0 | 0 | 0 | 0 | 0
60 ROW, LAND, EXISTING IMPROVEMENTS
60.01 | Purchase or lease of real estate | 0 | 0 | 0 | 0 | 0 | 0
60.02 | Relocation of existing households and businesses | 0 | 0 | 0 | 0 | 0 | 0
70 VEHICLES (number)
70.01 | Light Rail | 0 | 0 | 0 | 0 | 0 | 0
70.02 | Heavy Rail | 0 | 0 | 0 | 0 | 0 | 0
70.03 | Commuter Rail | 0 | 0 | 0 | 0 | 0 | 0
70.04 | Bus | 0 | 0 | 0 | 0 | 0 | 0
70.05 | Other | 0 | 0 | 0 | 0 | 0 | 0
70.06 | Non-revenue vehicles | 0 | 0 | 0 | 0 | 0 | 0
70.07 | Spare parts | 0 | 0 | 0 | 0 | 0 | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50)
80.01 | Project Development | 0 | 0 | 0 | 0 | 0 | 0
80.02 | Engineering (not applicable to Small Starts) | 0 | 0 | 0 | 0 | 0 | 0
80.03 | Project Management for Design and Construction | 0 | 0 | 0 | 0 | 0 | 0
80.04 | Construction Administration & Management | 0 | 0 | 0 | 0 | 0 | 0
80.05 | Professional Liability and other Non-Construction Insurance | 0 | 0 | 0 | 0 | 0 | 0
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. | 0 | 0 | 0 | 0 | 0 | 0
80.07 | Surveys, Testing, Investigation, Inspection | 0 | 0 | 0 | 0 | 0 | 0
80.08 | Start up | 0 | 0 | 0 | 0 | 0 | 0
| Additional profile values>>>> | 0
Lwrbnd
| Global SCC10-50 Req'ts Beta adjustment>>>> |  | See risk profile assessment worksheets
| Global SCC10-50 Dsgn Beta adjustment>>>> |  |  | ^^^
| Global SCC10-50 Mkt Beta adjustment>>>> |  |  |  | ^^^
| Global SCC10-50 Constr Beta adjustment>>>> |  |  |  |  | ^^^

## Risk Assessment Total
Risk Assessment Total: This worksheet requires no input (see exception following); it is a totaling of the the active risk profiles. Exception: Analyst may input a particular probability value (in yellow cell AA24) to determine a projected p-value project cost outcome.
All Profiles Combined |  |  | Requirements |  | Design |  | Market |  | Construction |  | Post-construction
SCC | Category | Lower bound |  | Adj Req'ts Beta |  | Adj Dsgn Beta |  | Adj Mkt Beta |  | Adj Constr Beta |  | Adj Post Beta | Total Beta | Upper bound | Categorical median | Categorical mean | Likelihood | Modeled cost |  | Modeled cost | Cum % | Incr %
10 GUIDEWAY & TRACK ELEMENTS (route miles) | [16 empty] | 0% | 0 |  | 0 | #NUM! | #NUM!
10.01 | Guideway: At-grade exclusive right-of-way | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0 | 10% | #NUM! |  | 0 | #NUM! | #NUM!
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0 | 20% | #NUM! |  | 0 | #NUM! | #NUM!
10.03 | Guideway: At-grade in mixed traffic | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0 | 30% | #NUM! |  | 0 | #NUM! | #NUM!
10.04 | Guideway: Aerial structure | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0 | 40% | #NUM! |  | 0 | #NUM! | #NUM!
10.05 | Guideway: Built-up fill | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0 | 50% | #NUM! |  | 0 | #NUM! | #NUM!
10.06 | Guideway: Underground cut & cover | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0 | 60% | #NUM! |  | 0 | #NUM! | #NUM!
10.07 | Guideway: Underground tunnel | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0 | 65% | #NUM! |  | 0 | #NUM! | #NUM!
10.08 | Guideway: Retained cut or fill | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0 | 70% | #NUM! |  | 0 | #NUM! | #NUM!
10.09 | Track: Direct fixation | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0 | 80% | #NUM! |  | 0 | #NUM! | #NUM!
10.1 | Track: Embedded | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0 | 90% | #NUM! |  | 0 | #NUM! | #NUM!
10.11 | Track: Ballasted | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0 | 100% | 0
10.12 | Track: Special (switches, turnouts) | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
10.13 | Track: Vibration and noise dampening | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | [16 empty] | 40% | #NUM! | <<< Lower reporting range
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0 | 65% | #NUM! | <<< Contingency target
20.02 | Aerial station, stop, shelter, mall, terminal, platform | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0 | 80% | #NUM! | <<< Upper reporting range
20.03 | Underground station, stop, shelter, mall, terminal, platform | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0 | 0% | 0 | <<< Sponsor's estimate
20.05 | Joint development | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
20.06 | Automobile parking multi-story structure | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0 | 45% | #NUM! | <<< Percentile test (adjust %value)
20.07 | Elevators, escalators | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS
30.01 | Administration Building: Office, sales, storage, revenue counting | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
30.02 | Light Maintenance Facility | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
30.03 | Heavy Maintenance Facility | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
30.04 | Storage or Maintenance of Way Building | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
30.05 | Yard and Yard Track | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
40 SITEWORK & SPECIAL CONDITIONS
40.01 | Demolition, Clearing, Earthwork | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
40.02 | Site Utilities, Utility Relocation | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
40.05 | Site structures including retaining walls, sound walls | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
40.06 | Pedestrian / bike access and accommodation, landscaping | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
40.07 | Automobile, bus, van accessways including roads, parking lots | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
40.08 | Temporary Facilities and other indirect costs during construction | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
50 SYSTEMS
50.01 | Train control and signals | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
50.02 | Traffic signals and crossing protection | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
50.03 | Traction power supply: substations | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
50.04 | Traction power distribution: catenary and third rail | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
50.05 | Communications | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
50.06 | Fare collection system and equipment | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
50.07 | Central Control | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
/\ /\ /\ Global adjustment are applied above /\ /\ /\
60 ROW, LAND, EXISTING IMPROVEMENTS |  |  | \/ \/ \/ Global adjustments are not applied below \/ \/ \/
60.01 | Purchase or lease of real estate | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
60.02 | Relocation of existing households and businesses | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
70 VEHICLES (number)
70.01 | Light Rail | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
70.02 | Heavy Rail | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
70.03 | Commuter Rail | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
70.04 | Bus | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
70.05 | Other | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
70.06 | Non-revenue vehicles | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
70.07 | Spare parts | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50)
80.01 | Project Development | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
80.02 | Engineering (not applicable to Small Starts) | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
80.03 | Project Management for Design and Construction | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
80.04 | Construction Administration & Management | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
80.05 | Professional Liability and other Non-Construction Insurance | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
80.07 | Surveys, Testing, Investigation, Inspection | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
80.08 | Start up | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 0 | 0 | 0
| Project values>>>> | 0 | [10 empty] | 0 | 0 | 0 | 0
|  | Lwrbnd | [10 empty] | Beta | Uprbnd | Median | Mean
See risk profile assessment worksheets
| Global SCC10-50 Req'ts Beta adjustment>>>> |  |  | ^^^
| Global SCC10-50 Dsgn Beta adjustment>>>> |  |  |  |  | ^^^
| Global SCC10-50 Mkt Beta adjustment>>>> | [6 empty] | ^^^
| Global SCC10-50 Constr Beta adjustment>>>> | [8 empty] | ^^^

## 5 - Project Risk Analysis Instr
FTA Reporting values
FTA target | 65%
Lower report range value= | 40%
Median report range value= | 50%
Upper mid report range value= | 65%
Upper report range value= | 80%
The above should not be changed without FTA approval
Instructions for: Risk assessment Analysis
The purpose of the worksheets in this Section 5 is to create a representation of the potential risk variation of the project, including recommendations for budget, contingency, and secondary mitigation.
Risk summary and analysis:
  Review model results for reasonableness
    Check values for recommended budget and contingency
    Check values for reporting ranges
    Check values for Lower Bound and Upper Bound Range
  Provide a reasoned interpretation of the results in the results
The tables of this worksheet draw information from other worksheets in the model workbook.
The Risk Assessment Analysis worksheet provides overview information about Sponsor baseline and PMOC adjustments, and the Prob Dist Report Graphic worksheet provides a graphic to use for reporting as described in OP40.
Because these worksheets draw information from the various other worksheets, alteration of any other worksheet may change the values here. Therefore, caution must be exercised to ensure that reports that contain information from these two tabs are synchronized with any other changes made.
Guidance regarding interpretation of the results presented in this worksheet is provided elsewhere in OP40 and through the FTA.
These worksheets contain fundamental values that relate to FTA risk targets and which values should be contained within the OP40 Risk Review reports. These values, shown to the right, are intended to provide consistency across all similar reports and should only be changed with written direction from the FTA. It is not intended that these values would vary among projects.
Specific instructions are provided within the two worksheets.

## Risk Assessment Analysis
Values are derived from other tabs. Review for consistency. Unhide columns C-G for multiple risk profiles. |  | If only one profile is used, these columns may be hidden. Hide unused profiles. |  |  |  | Hide if no addendum to this workbook
Project name: | Project Name
FTA review milestone: | Milestone
Sponsor: | Sponsor name
Date of review: | ReviewDate
Version 5.16b Workbook: | Primary Workbook
YOE 10-80 Baseline and Adjustments Summary
Item | Base Evaluation
Estimate
Sponsor Estimate | 0
Sponsor Total Contingency Amount | 0 |  |  |  |  | Copy "Overall" (values only) from separate addendum to this workbook
Sponsor Total Contingency % | #DIV/0!
Sponsor Stripped Estimate | 0
PMOC Inflation Adjust. on Sponsor Estimate | 0
PMOC Direct Cost Adjustments | 0
PMOC Duration Adjustments | 0
PMOC Latent Contingency Deduct | 0
PMOC Adjusted Estimate | 0
Risk Protection on Adjusted Estimate
Total Contingency Amount | 0
Total Contingency % | #DIV/0!
Copy this table within this green border to include in report
YOE Risk Assessment Detail ($,000) |  | Profile 1 | Profile 2 | Profile 3 | Profile 4 | Additional Profiles
Model Version 5.16b
SCC 100 Finance Charges not included
YOE Sponsor values | Overall
Sponsor total estimate (SCC 10-90) (0%ile) | 0 | Transit project | Not Used | Not Used | Not used | Additional Profiles
Sponsor stripped estimate (SCC 10-80) | 0 | 0 | 0 | 0 | 0 | 0
YOE PMOC values
Inflation Adjustment on Sponsor Estimate | 0 | 0 | 0 | 0 | 0 | 0
Direct Cost Adjustments | 0 | 0 | 0 | 0 | 0 | 0
Duration Adjustments | 0 | 0 | 0 | 0 | 0 | 0
Latent contingency Deduct | 0 | 0 | 0 | 0 | 0 | 0
Adjusted, Inflated estimate | 0 | 0 | 0 | 0 | 0 | 0
FTA target (65%ile) | 0 | 0 | 0 | 0 | 0 | 0
Contingency recommendation amount in target | 0 | 0 | 0 | 0 | 0 | 0
Target contingency % | 0% | 0% | 0% | 0% | 0% | 0%
Risk analysis
Lower bound | 0 | 0 | 0 | 0 | 0 | 0
Lower report range value= (40%ile) | 0 | 0 | 0 | 0 | 0 | 0
Median report range value= (50%ile) | 0 | 0 | 0 | 0 | 0 | 0
Upper mid report range value= (65%ile) | 0 | 0 | 0 | 0 | 0 | 0
Upper range reporting amount (80%ile) | 0 | 0 | 0 | 0 | 0 | 0
Upper bound | 0 | 0 | 0 | 0 | 0 | 0
+

## Prob Dist Report Graphic
This graphic derives its data from the risk assessment. Each project requires some adjustment: 1) Adjust the X-axis to span the entire range of $ possibilities, from just below Lower Bound (p0) to just above Upper Bound (p100) (guidance is provided below the graph); 2) Adjust the horizontal and vertical lines for the FTA target and Sponsor Estimate (guidance is provided below the graph); 3) Move the line labels for the lines that show the modeled FTA Target pValue and Sponsor Estimate. These are not automatically graphed, but must be placed in position once the lines are properly adjusted. Guidance is provided below the graph; 4) To copy for placement in report--Select the graphic and the added lines and captions in Excel (Edit>Select All), then Copy, then Paste into Risk Report as a PDF.
Set X-axis range to:
| Minimum just less than Lower Bound (p0): |  | 0
| Maximum just more than Upper Bound (p100): |  | 0
| Move Sponsor Estimate and FTA Target indicator lines: | Y-axis | X-Axis
| Sponsor value (red/small-dotted lines): | 0% | 0
| FTA Target (blue/large-hash lines): | 65% | 0
FTA Target
Sponsor Estimate
Model version:
5.16b

## Appendices - Standards & Tools
Instructions for: Appendices
This section contains worksheets with tables and calculators that provide suggested starting partial Beta values that may be transferred to the Risk Assessment worksheets in the Risk Assessment section of this workbook and other tools that may prove useful for the risk analyst.
Detailed instruction is provided in the various worksheets.
The worksheets in these appendices include:
** Worksheet tables and calculators that are used in the process of establishing the project's base uncertainty:
* DBB CMGC Beta Uncertainty Standards for SCC 10-80, and
* Separate tabs for customized SCC 10-50, SCC 60-70, and SCC 80 Beta Calculations.
**A worksheet calculator that is used in the process of establishing partial Beta adjustments for the project's specific risks and conditions:
* Project-specific Risk Calculations worksheet.
The risk analyst may use other means to determine partial Beta values; if so, the reasoning behind such adjustments should be recorded.
** A calculator that converts costs from Base Year (BY) to Year of Expenditure (YOE) (and the reverse), using the Sponsor inflation values from its SCC Workbook. This calculator may be useful in establishing any BY cost adjustments, especially when any adjustments are recommended in YOE values.
** Further, a worsheet entitled Cost Risk Calcs Schema presents the schematic progression of calculations that are the basis of this workbook.

## DBB CMGC Beta Uncertainty Stdrs
The partial Beta values below are potential general uncertainty starting points for the cost risk analysis for DBB and CMGC project profiles, or other delivery methods in early stages of project progression. The reviewer should use judgment when applying these values and amend for project circumstances. See OP40 for a discussion of amendments for other project delivery methods, such as Design-Build.
Standard SCC categories |  | Beta suggestions at 15% design | [8 empty] | Beta suggestions at 30% design | [8 empty] | Beta suggestions at 60% design | [8 empty] | Beta suggestions at 95% design/Pre-Bid | [8 empty] | Beta suggestions at 100% design/post-bid | [8 empty] | Beta suggestions at 20% constructed | [8 empty] | Beta suggestions at 50% constructed | [8 empty] | Beta suggestions at 75% constructed | [8 empty] | Beta suggestions at RSD
SCC | Category | Req'ts Beta |  | Dsgn Beta |  | Mkt Beta |  | Constr Beta |  | Post Constr Beta | Req'ts Beta |  | Dsgn Beta |  | Mkt Beta |  | Constr Beta |  | Post Constr Beta | Req'ts Beta |  | Dsgn Beta |  | Mkt Beta |  | Constr Beta |  | Post Constr Beta | Req'ts Beta |  | Dsgn Beta |  | Mkt Beta |  | Constr Beta |  | Post Constr Beta | Req'ts Beta |  | Dsgn Beta |  | Mkt Beta |  | Constr Beta |  | Post Constr Beta | Req'ts Beta |  | Dsgn Beta |  | Mkt Beta |  | Constr Beta |  | Post Constr Beta | Req'ts Beta |  | Dsgn Beta |  | Mkt Beta |  | Constr Beta |  | Post Constr Beta | Req'ts Beta |  | Dsgn Beta |  | Mkt Beta |  | Constr Beta |  | Post Constr Beta | Req'ts Beta |  | Dsgn Beta |  | Mkt Beta |  | Constr Beta |  | Post Constr Beta
10 GUIDEWAY & TRACK ELEMENTS (route miles)
10.01 | Guideway: At-grade exclusive right-of-way | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
10.03 | Guideway: At-grade in mixed traffic | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
10.04 | Guideway: Aerial structure | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
10.05 | Guideway: Built-up fill | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
10.06 | Guideway: Underground cut & cover | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
10.07 | Guideway: Underground tunnel | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
10.08 | Guideway: Retained cut or fill | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
10.09 | Track: Direct fixation | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
10.1 | Track: Embedded | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
10.11 | Track: Ballasted | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
10.12 | Track: Special (switches, turnouts) | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
10.13 | Track: Vibration and noise dampening | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number)
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
20.02 | Aerial station, stop, shelter, mall, terminal, platform | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
20.03 | Underground station, stop, shelter, mall, terminal, platform | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
20.05 | Joint development | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
20.06 | Automobile parking multi-story structure | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
20.07 | Elevators, escalators | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS
30.01 | Administration Building: Office, sales, storage, revenue counting | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
30.02 | Light Maintenance Facility | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
30.03 | Heavy Maintenance Facility | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
30.04 | Storage or Maintenance of Way Building | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
30.05 | Yard and Yard Track | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
40 SITEWORK & SPECIAL CONDITIONS
40.01 | Demolition, Clearing, Earthwork | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
40.02 | Site Utilities, Utility Relocation | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
40.05 | Site structures including retaining walls, sound walls | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
40.06 | Pedestrian / bike access and accommodation, landscaping | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
40.07 | Automobile, bus, van accessways including roads, parking lots | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
40.08 | Temporary Facilities and other indirect costs during construction | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
50 SYSTEMS
50.01 | Train control and signals | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
50.02 | Traffic signals and crossing protection | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
50.03 | Traction power supply: substations | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
50.04 | Traction power distribution: catenary and third rail | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
50.05 | Communications | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
50.06 | Fare collection system and equipment | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
50.07 | Central Control | 0.15 |  | 0.6 |  | 0.25 |  | 0.45 |  | 0.05 | 0.1 |  | 0.5 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.3 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0.05 |  | 0.25 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.45 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.3 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.15 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.1 |  | 0.05 | 0 |  | 0 |  | 0 |  | 0.05 |  | 0.05
60 ROW, LAND, EXISTING IMPROVEMENTS
60.01 | Purchase or lease of real estate |  | 0 |  | 1.15 |  | 0.8 |  | 0.25 | 0.05 |  | 0 |  | 1.025 |  | 0.8 |  | 0.25 | 0.05 |  | 0 |  | 0.9 |  | 0.8 |  | 0.25 | 0.05 |  | 0 |  | 0.4 |  | 0.8 |  | 0.25 | 0.05 |  | 0 |  | 0.25 |  | 0.5 |  | 0.25 | 0.05 |  | 0 |  | 0.15 |  | 0.4 |  | 0.2 | 0.05 |  | 0 |  | 0.1 |  | 0.3 |  | 0.15 | 0.05 |  | 0 |  | 0.05 |  | 0.15 |  | 0.1 | 0.05 |  | 0 |  | 0 |  | 0.05 |  | 0.05 | 0.05
60.02 | Relocation of existing households and businesses |  | 0 |  | 1.15 |  | 0.8 |  | 0.25 | 0.05 |  | 0 |  | 1.025 |  | 0.8 |  | 0.25 | 0.05 |  | 0 |  | 0.9 |  | 0.8 |  | 0.25 | 0.05 |  | 0 |  | 0.4 |  | 0.8 |  | 0.25 | 0.05 |  | 0 |  | 0.25 |  | 0.5 |  | 0.25 | 0.05 |  | 0 |  | 0.15 |  | 0.4 |  | 0.2 | 0.05 |  | 0 |  | 0.1 |  | 0.3 |  | 0.15 | 0.05 |  | 0 |  | 0.05 |  | 0.15 |  | 0.1 | 0.05 |  | 0 |  | 0 |  | 0.05 |  | 0.05 | 0.05
70 VEHICLES (number)
70.01 | Light Rail |  | 0 |  | 0.45 |  | 0.25 |  | 0.25 | 0.05 |  | 0 |  | 0.4 |  | 0.25 |  | 0.25 | 0.05 |  | 0 |  | 0.35 |  | 0.25 |  | 0.25 | 0.05 |  | 0 |  | 0.15 |  | 0.15 |  | 0.25 | 0.05 |  | 0 |  | 0.05 |  | 0.15 |  | 0.25 | 0.05 |  | 0 |  | 0 |  | 0.1 |  | 0.25 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0.15 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0.05 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0 | 0.05
70.02 | Heavy Rail |  | 0 |  | 0.45 |  | 0.25 |  | 0.25 | 0.05 |  | 0 |  | 0.4 |  | 0.25 |  | 0.25 | 0.05 |  | 0 |  | 0.35 |  | 0.25 |  | 0.25 | 0.05 |  | 0 |  | 0.15 |  | 0.15 |  | 0.25 | 0.05 |  | 0 |  | 0.05 |  | 0.15 |  | 0.25 | 0.05 |  | 0 |  | 0 |  | 0.1 |  | 0.25 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0.15 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0.05 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0 | 0.05
70.03 | Commuter Rail |  | 0 |  | 0.45 |  | 0.25 |  | 0.25 | 0.05 |  | 0 |  | 0.4 |  | 0.25 |  | 0.25 | 0.05 |  | 0 |  | 0.35 |  | 0.25 |  | 0.25 | 0.05 |  | 0 |  | 0.15 |  | 0.15 |  | 0.25 | 0.05 |  | 0 |  | 0.05 |  | 0.15 |  | 0.25 | 0.05 |  | 0 |  | 0 |  | 0.1 |  | 0.25 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0.15 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0.05 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0 | 0.05
70.04 | Bus |  | 0 |  | 0.45 |  | 0.25 |  | 0.25 | 0.05 |  | 0 |  | 0.4 |  | 0.25 |  | 0.25 | 0.05 |  | 0 |  | 0.35 |  | 0.25 |  | 0.25 | 0.05 |  | 0 |  | 0.15 |  | 0.15 |  | 0.25 | 0.05 |  | 0 |  | 0.05 |  | 0.15 |  | 0.25 | 0.05 |  | 0 |  | 0 |  | 0.1 |  | 0.25 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0.15 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0.05 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0 | 0.05
70.05 | Other |  | 0 |  | 0.45 |  | 0.25 |  | 0.25 | 0.05 |  | 0 |  | 0.4 |  | 0.25 |  | 0.25 | 0.05 |  | 0 |  | 0.35 |  | 0.25 |  | 0.25 | 0.05 |  | 0 |  | 0.15 |  | 0.15 |  | 0.25 | 0.05 |  | 0 |  | 0.05 |  | 0.15 |  | 0.25 | 0.05 |  | 0 |  | 0 |  | 0.1 |  | 0.25 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0.15 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0.05 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0 | 0.05
70.06 | Non-revenue vehicles |  | 0 |  | 0.45 |  | 0.25 |  | 0.25 | 0.05 |  | 0 |  | 0.4 |  | 0.25 |  | 0.25 | 0.05 |  | 0 |  | 0.35 |  | 0.25 |  | 0.25 | 0.05 |  | 0 |  | 0.15 |  | 0.15 |  | 0.25 | 0.05 |  | 0 |  | 0.05 |  | 0.15 |  | 0.25 | 0.05 |  | 0 |  | 0 |  | 0.1 |  | 0.25 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0.15 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0.05 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0 | 0.05
70.07 | Spare parts |  | 0 |  | 0.45 |  | 0.25 |  | 0.25 | 0.05 |  | 0 |  | 0.4 |  | 0.25 |  | 0.25 | 0.05 |  | 0 |  | 0.35 |  | 0.25 |  | 0.25 | 0.05 |  | 0 |  | 0.15 |  | 0.15 |  | 0.25 | 0.05 |  | 0 |  | 0.05 |  | 0.15 |  | 0.25 | 0.05 |  | 0 |  | 0 |  | 0.1 |  | 0.25 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0.15 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0.05 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0 | 0.05
80 PROFESSIONAL SERVICES (applies to Cats. 10-50)
80.01 | Project Development |  | 0 |  | 0.3 |  | 0.25 |  | 0.35 | 0.05 |  | 0 |  | 0 |  | 0.05 |  | 0.2 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0 | 0.05
80.02 | Engineering (not applicable to Small Starts) |  | 0 |  | 0.4 |  | 0.3 |  | 0.35 | 0.05 |  | 0 |  | 0.35 |  | 0.3 |  | 0.35 | 0.05 |  | 0 |  | 0.3 |  | 0.3 |  | 0.35 | 0.05 |  | 0 |  | 0.25 |  | 0.25 |  | 0.1 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0.1 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0 | 0.05
80.03 | Project Management for Design and Construction |  | 0 |  | 0.5 |  | 0.4 |  | 0.35 | 0.05 |  | 0 |  | 0.45 |  | 0.325 |  | 0.3 | 0.05 |  | 0 |  | 0.4 |  | 0.25 |  | 0.25 | 0.05 |  | 0 |  | 0.25 |  | 0.15 |  | 0.2 | 0.05 |  | 0 |  | 0.15 |  | 0.1 |  | 0.2 | 0.05 |  | 0 |  | 0.1 |  | 0.05 |  | 0.2 | 0.05 |  | 0 |  | 0.05 |  | 0.05 |  | 0.15 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0.1 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0.05 | 0.05
80.04 | Construction Administration & Management |  | 0 |  | 0.6 |  | 0.5 |  | 0.35 | 0.05 |  | 0 |  | 0.45 |  | 0.5 |  | 0.35 | 0.05 |  | 0 |  | 0.3 |  | 0.5 |  | 0.35 | 0.05 |  | 0 |  | 0.25 |  | 0.25 |  | 0.35 | 0.05 |  | 0 |  | 0.2 |  | 0.2 |  | 0.35 | 0.05 |  | 0 |  | 0.1 |  | 0.15 |  | 0.3 | 0.05 |  | 0 |  | 0.05 |  | 0.05 |  | 0.25 | 0.05 |  | 0 |  | 0.05 |  | 0.05 |  | 0.2 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0.1 | 0.05
80.05 | Professional Liability and other Non-Construction Insurance |  | 0 |  | 0.3 |  | 0.25 |  | 0.15 | 0.05 |  | 0 |  | 0.225 |  | 0.175 |  | 0.15 | 0.05 |  | 0 |  | 0.15 |  | 0.1 |  | 0.15 | 0.05 |  | 0 |  | 0.05 |  | 0.05 |  | 0.15 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0.15 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0.1 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0.05 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0 | 0.05
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. |  | 0 |  | 0.6 |  | 0.5 |  | 0.25 | 0.05 |  | 0 |  | 0.45 |  | 0.375 |  | 0.225 | 0.05 |  | 0 |  | 0.3 |  | 0.25 |  | 0.2 | 0.05 |  | 0 |  | 0.15 |  | 0.1 |  | 0.15 | 0.05 |  | 0 |  | 0.1 |  | 0.05 |  | 0.15 | 0.05 |  | 0 |  | 0.05 |  | 0 |  | 0.15 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0.1 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0.05 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0 | 0.05
80.07 | Surveys, Testing, Investigation, Inspection |  | 0 |  | 0.4 |  | 0.45 |  | 0.5 | 0.05 |  | 0 |  | 0.3 |  | 0.35 |  | 0.5 | 0.05 |  | 0 |  | 0.2 |  | 0.25 |  | 0.5 | 0.05 |  | 0 |  | 0.2 |  | 0.15 |  | 0.3 | 0.05 |  | 0 |  | 0.1 |  | 0.15 |  | 0.3 | 0.05 |  | 0 |  | 0.1 |  | 0.1 |  | 0.25 | 0.05 |  | 0 |  | 0.05 |  | 0.05 |  | 0.15 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0.15 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0.1 | 0.05
80.08 | Start up |  | 0 |  | 0.6 |  | 0.25 |  | 0.6 | 0.05 |  | 0 |  | 0.6 |  | 0.25 |  | 0.6 | 0.05 |  | 0 |  | 0.6 |  | 0.25 |  | 0.6 | 0.05 |  | 0 |  | 0.4 |  | 0.25 |  | 0.6 | 0.05 |  | 0 |  | 0.4 |  | 0.25 |  | 0.6 | 0.05 |  | 0 |  | 0.2 |  | 0.25 |  | 0.6 | 0.05 |  | 0 |  | 0.15 |  | 0.15 |  | 0.6 | 0.05 |  | 0 |  | 0.1 |  | 0.1 |  | 0.6 | 0.05 |  | 0 |  | 0 |  | 0 |  | 0.4 | 0.05

## DBB Beta drawdown graphs
For informational purposes, the following table and resulting graphs represents the progression of total Beta risk factor draw downs of Beta values for SCC codes, based on typical DBB project progressions. Detailed progression of partial Beta drawdowns for risk types Requirements, Design, Construction, and Post-construction are more fully outlined in other Appendix worksheets and in OP40.
|  | Constr | ROW | Vehicles | Project Development | Engineering | Project Management for Design and Construction | Construction Administration & Management | Professional Liability and other Non-Construction Insurance | Legal; Permits; Review Fees by other agencies, cities, etc. | Surveys, Testing, Investigation, Inspection | Start up
|  | Constr | ROW | Vehcl | ProjDev | Engin'g | ProjMgt | ConAdmin | Insurance | Legal | TechSvcs | StartUp
Start of SCC 10-50 Project Phase: | SCC> | 10-50 | 60 | 70 | 80.01 | 80.02 | 80.03 | 80.04 | 80.05 | 80.06 | 80.07 | 80.08
15% design |  | 2.5 | 3.25 | 2 | 1.95 | 2.1 | 2.3 | 2.5 | 1.75 | 2.4 | 2.4 | 2.5
30% design |  | 2.275 | 3.125 | 1.95 | 1.3 | 2.05 | 2.125 | 2.35 | 1.6 | 2.1 | 2.2 | 2.5
60% design |  | 2.05 | 3 | 1.9 | 1.05 | 2 | 1.95 | 2.2 | 1.45 | 1.8 | 2 | 2.5
Pre-bid |  | 1.8 | 2.5 | 1.6 | 1.05 | 1.65 | 1.65 | 1.9 | 1.3 | 1.45 | 1.7 | 2.3
40% Bid |  | 1.5 | 2.05 | 1.5 | 1.05 | 1.15 | 1.5 | 1.8 | 1.2 | 1.35 | 1.6 | 2.3
20% Constr |  | 1.35 | 1.8 | 1.4 | 1.05 | 1.05 | 1.4 | 1.6 | 1.15 | 1.25 | 1.5 | 2.1
50% Constr |  | 1.2 | 1.6 | 1.2 | 1.05 | 1.05 | 1.3 | 1.4 | 1.1 | 1.15 | 1.3 | 1.95
75% Constr |  | 1.15 | 1.35 | 1.1 | 1.05 | 1.05 | 1.15 | 1.35 | 1.05 | 1.1 | 1.2 | 1.85
90% Constr |  | 1.1 | 1.15 | 1.05 | 1.05 | 1.05 | 1.1 | 1.15 | 1.05 | 1.05 | 1.15 | 1.45

## Project-Specific Risk Calcs
To calculate project-specific risk Beta adjustment to add/subtract to uncertainty Beta (by risk profile): 1) Determine which SCC(s) & Risk Type(s)* are affected for a particular risk. If SCC 10-50, adjustment will be made as a global factor. Use multiple lines for cases of multiple risk types. 2) Determine target cost adjustment (+ or -) as either: a projected contingency amount (C), or as a worst-case cost amount (W) (best case in terms of risk reduction). 3) Enter the appropriate values in the table and read the Beta adjustment factor. 4) Return to the Risk Assessment worksheet and manually add the Beta adjustment factor to the prior-determined uncertainty factor in the "... Beta" column for the appropriate SCC/risk type. * Risk types: R-Requirements, D-Design, M-Market, C-Construction, P-Post-RSD, G-Global 10-50 -- See adjustment notes to the right. --
Project-specific risk for adjustments (not included in uncertainty standard Betas) | Affected Risk Profile | Affected SCC(s) or Global 10-50 | Lower Bound sum for SCC(s) | Affected risk type (R,D,M,C,P,G) | Enter: "C" for contingency target, or "W" for worst-case target | Enter adjustment amount indicated for "C" or "W" | Beta Adjustment to Risk Profile/ SCC(s)/Risk Type (highlight adjusted cell)
C or W ?
C or W ?
C or W ?
C or W ?
C or W ?
C or W ?
C or W ?
C or W ?
C or W ?
C or W ?
C or W ?
C or W ?
C or W ?
C or W ?
C or W ?
C or W ?
C or W ?
C or W ?
C or W ?
C or W ?
C or W ?
C or W ?
C or W ?
C or W ?
C or W ?
C or W ?
C or W ?
C or W ?
C or W ?
C or W ?
C or W ?
C or W ?
C or W ?
C or W ?
C or W ?
C or W ?
C or W ?
C or W ?
Project-specific risk adjustments notes
1) The process to the left should be repeated for each risk profile, if multiple risk profiles are used.
2) When making manual adjustments for project-specific risk, highlight the cell where the adjustment is made with a distinctive color (perhaps orange), and add an Excel "Note" that explains the adjustment.
3) If multiple risk types are involved, calculate a separate line for each risk type by SCC (or global SCC 10-50). Separate the impacts by risk type; don't overlap impacts.

## SCC10-50 Beta calculations
Enter project profile progression values for design, market, construction, and closeout completions. Read the calculated partial Beta values and insert them into the appropriate columns under R, D, M, C, and Post-RSD (closeout).
SCC 10-50 Project Profile Progression |  | Summary results
Dsgn % Complete>> | 15% | SCC | Category | Req'ts Beta | Dsgn Beta | Mkt Beta | Constr Beta | Post-RSD Beta
|  | SCC 10-50 | Civil and Systems
Mkt % Complete>> | 0% |  | Apply these values to all SCC 10-50 level 2 | 0.15 | 0.6 | 0.25 | 0.45 | 0.05
Constr % Complete>> | 0%
Post-RSD % Complete>> | 0%
Detailed calculations, see summary results
SCCs 10-50 ∆Beta general uncertainty drawdown calculations
[9 empty] | Requirements Risk |  |  |  | Requirements ∆Beta is: |  |  | 0.15
[9 empty] | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Start Plus % Drawdown times factor | Equals ∆Beta:
[9 empty] | Dsgn % Compl is between | 15% | 30% | -0.33333 | 0.15 | 0.1 | 0 | 0.15
[9 empty] | Dsgn % Compl is between | 30% | 60% | -0.33333 | 0.1 | 0 | XXX | XXX
[9 empty] | Dsgn % Compl is between | 60% | 100% | 0 | 0 | 0 | XXX | XXX
[9 empty] | Design Risk |  |  |  | Planning ∆Beta is: |  |  | 0.6
[9 empty] | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta:
[9 empty] | Dsgn % Compl is between | 15% | 30% | -0.66667 | 0.6 | 0.5 | 0 | 0.6
[9 empty] | Dsgn % Compl is between | 30% | 60% | -0.66667 | 0.5 | 0.3 | XXX | XXX
[9 empty] | Dsgn % Compl is between | 60% | 95% | -0.71429 | 0.3 | 0.05 | XXX | XXX
[9 empty] | Dsgn % Compl is between | 95% | 100% | -1 | 0.05 | 0 | XXX | XXX
[9 empty] | Market Risk |  |  |  | Acquisition ∆Beta is: |  |  | 0.25
[9 empty] | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta:
[9 empty] | Mkt % Compl is between | 0% | 100% | -0.25 | 0.25 | 0 | 0 | 0.25
[9 empty] | Construction Risk |  |  |  | Construction ∆Beta is: |  |  | 0.45
[9 empty] | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta:
[9 empty] | Constr. % Compl is between | 0% | 20% | -0.75 | 0.45 | 0.3 | 0 | 0.45
[9 empty] | Constr. % Compl is between | 20% | 50% | -0.33333 | 0.3 | 0.2 | XXX | XXX
[9 empty] | Constr. % Compl is between | 50% | 100% | -0.3 | 0.15 | 0 | XXX | XXX
[9 empty] | Closeout Risk |  |  |  | Closeout ∆Beta is: |  |  | 0.05
[9 empty] | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta:
[9 empty] | Post-RSD % Compl is between | 0% | 100% | -0.05 | 0.05 | 0 | 0 | 0.05

## SCC60-70 Beta calculations
Enter project profile progression values for Real Estate and Vehicles completions. Read the partial calculated partial Beta values and insert them into the appropriate columns under R, D, M, C, and Post-RSD (closeout).
SCC 60 Project Profile Progression |  | SCC 70 Project Profile Progression
% RAMP Development | 0% | % Vehicle Design | 0%
% Offers made | 0% | % Vehicle Procurement | 0%
% Closures finalized | 0% | % Vehicle Delivered and Tested | 0%
% Post-Real Closures | 0% | % Post Vehicle Testing | 0%
Summary results
|  |  |  | SCC | Category | Req'ts Beta (R) | RAMP Beta (D) | Offers Beta (M) | Closures Beta (C) | Post-Closures
|  |  |  | SCC 60 | Real Estate
[5 empty] | Apply these values to all level 2 SCC 60 | 0.25 | 0.9 | 0.8 | 0.25 | 0.05
|  |  |  | SCC | Category | Req'ts Beta | Design Beta (D) | Procure Beta (M) | Acceptance Beta (C) | Post-Closures
|  |  |  | SCC 70 | Vehicles
[5 empty] | Apply these values to all level 2 SCC 70 | 0.1 | 0.35 | 0.25 | 0.25 | 0.05
Detailed calculations, see summary results
[11 empty] | SCC 60 ∆Beta general uncertainty drawdown calculations | [7 empty] | SCCs70 ∆Beta general uncertainty drawdown calculations
[11 empty] | Requirements Risk |  |  |  | Requirements ∆Beta is: |  |  | 0.25 | Requirements Risk |  |  |  | Requirements ∆Beta is: |  |  | 0.1
[11 empty] | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Start Plus % Drawdown times factor | Equals ∆Beta: | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Start Plus % Drawdown times factor | Equals ∆Beta:
[11 empty] | Ramp % Compl is between | 0% | 100% | -0.25 | 0.25 | 0 | 0 | 0.25 | VehDsgn % Compl is between | 0% | 100% | -0.1 | 0.1 | 0 | 0 | 0.1
[11 empty] | RAMP(D) Risk |  |  |  | Planning ∆Beta is: |  |  | 0.9 | VehDesign (D) Risk |  |  |  | Planning ∆Beta is: |  |  | 0.35
[11 empty] | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta: | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta:
[11 empty] | Ramp % Compl is between | 0% | 50% | 0 | 0.85 | 0.85 | 0 | 0.85 | VehDsgn % Compl is between | 0% | 100% | -0.2 | 0.3 | 0.1 | 0 | 0.3
[11 empty] | Ramp % Compl is between | 50% | 100% | -1.7 | 0.85 | 0 | XXX | XXX | VehProc % Compl is between | 0% | 100% | 0.05 | 0.05 | 0.1 | 0 | 0.05
[11 empty] | Offers % Compl is between | 0% | 100% | -0.05 | 0.05 | 0 | 0 | 0.05
[11 empty] | Offers(M) Risk |  |  |  | Acquisition ∆Beta is: |  |  | 0.8 | VehProcure (M) Risk |  |  |  | Acquisition ∆Beta is: |  |  | 0.25
[11 empty] | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta: | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta:
[11 empty] | Offers % Compl is between | 0% | 100% | -0.8 | 0.8 | 0 | 0 | 0.8 | VehProc % Compl is between | 0% | 100% | -0.25 | 0.25 | 0 | 0 | 0.25
[11 empty] | Closure(C) Risk |  |  |  | Construction ∆Beta is: |  |  | 0.25 | VehBuild/Accept (C) Risk |  |  |  | Construction ∆Beta is: |  |  | 0.25
[11 empty] | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta: | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta:
[11 empty] | Closures. % Compl is between | 0% | 100% | -0.25 | 0.25 | 0 | 0 | 0.25 | VehAccept % Compl is between | 0% | 100% | -0.25 | 0.25 | 0 | 0 | 0.25
[11 empty] | Post-closure Risk |  |  |  | Closeout ∆Beta is: |  |  | 0.05 | VehPostAccept Risk |  |  |  | Closeout ∆Beta is: |  |  | 0.05
[11 empty] | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta: | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta:
[11 empty] | Post-Closure % Compl is between | 0% | 100% | -0.05 | 0.05 | 0 | 0 | 0.05 | Post-VehAccept % Compl is between | 0% | 100% | -0.05 | 0.05 | 0 | 0 | 0.05

## SCC80 Beta calculations
The method available here to determine SCC 80 partial Betas by sub-SCC is as follows: Establish the partial Betas for the various Civil work progression; This is generally sufficiently if the civil procurement is similar to DBB or CMGC delivery and is not performed in multiple phases. Enter completion values for design, market, construction, and closeout completions for the CIVIL portions of the work in the SCC 10-50 Project Profile Progressions matrix, below. For multiple-phase projects, select a reasonable "average" across all of the phases. Read the partial calculated partial Beta values and insert them into the appropriate columns under R, D, M, C, and Closeout. 2) For non single-phase DBB/CMGC or DB and similar projects, review the results by individual sub-SCC (80.01, 80.02,...) and determine whether any sub-SCC 80 code appears to be more or less risky than indicated. These amounts represent historic uncertainty risk as follows: R - risk in scope of services that may occur due to forces beyond the control of the project; D - risk that results from changes in the current planned scope for the professional service; M - potential changes from the currently expected cost; and C - potential changes that may occur during the course of future delivery of the service. If any of these values are at odds with the understanding of the activity, then a change in the partial Beta value may be estimated using the Project-Specific Risk Calcs tab.
SCC 10-50 Project Profile Progression |  | Summary results
Dsgn % Complete>> | 0% | SCC 80 | Professional services and Agency costs | R | D | M | C | P
If Dsgn<15%, estimate and add R & M Beta |  | 80.01 | Project Development | 0 | 0 | 0 | 0 | 0.05
Mkt % Complete>> | 0% | 80.02 | Engineering | 0 | 0 | 0 | 0.1 | 0.05
|  | 80.03 | Project Management for Design and Construction | 0 | 0.15 | 0.1 | 0.2 | 0.05
Constr % Complete>> | 0% | 80.04 | Construction Administration & Management | 0 | 0.2 | 0.2 | 0.35 | 0.05
|  | 80.05 | Professional Liability and other Non-Construction Insurance | 0 | 0 | 0 | 0.15 | 0.05
Post-RSD % Complete>> | 0% | 80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. | 0 | 0.1 | 0.05 | 0.15 | 0.05
|  | 80.07 | Surveys, Testing, Investigation, Inspection | 0 | 0.1 | 0.15 | 0.3 | 0.05
|  | 80.08 | Start up | 0 | 0.4 | 0.25 | 0.6 | 0.05
Detailed calculations, see summary results
[9 empty] | SCC 80.01 ∆Beta general uncertainty drawdown calculations | [7 empty] | SCC 80.02 ∆Beta general uncertainty drawdown calculations | [7 empty] | SCCs 80.03 ∆Beta general uncertainty drawdown calculations | [7 empty] | SCCs 80.04 ∆Beta general uncertainty drawdown calculations
[9 empty] | Requirements Risk (R) |  |  |  | Requirements (R) ∆Beta is: |  |  | 0 | Requirements Risk |  |  |  | Requirements (R) ∆Beta is: |  |  | 0 | Requirements Risk |  |  |  | Requirements (R) ∆Beta is: |  |  | 0 | Requirements Risk |  |  |  | Requirements (R) ∆Beta is: |  |  | 0
[9 empty] | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta: | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta: | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta: | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta:
[9 empty] | Dsgn % Compl is between | 15% | 100% | 0 | 0 | 0 | XXX | XXX | Dsgn % Compl is between | 0% | 100% | 0 | 0 | 0 | 0 | 0 | Dsgn % Compl is between | 15% | 100% | 0 | 0 | 0 | XXX | XXX | Dsgn % Compl is between | 15% | 100% | 0 | 0 | 0 | XXX | XXX
[9 empty] | Planning Risk (D) |  |  |  | Planning (D) ∆Beta is: |  |  | 0 | Planning Risk |  |  |  | Planning (D) ∆Beta is: |  |  | 0 | Planning Risk |  |  |  | Planning (D) ∆Beta is: |  |  | 0.15 | Planning Risk |  |  |  | Planning (D) ∆Beta is: |  |  | 0.2
[9 empty] | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta: | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta: | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta: | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta:
[9 empty] | Dsgn % Compl is between | 15% | 100% | 0 | 0 | 0 | XXX | XXX | Dsgn % Compl is between | 15% | 30% | -0.33333 | 0.4 | 0.35 | XXX | XXX | Dsgn % Compl is between | 15% | 30% | -0.33333 | 0.35 | 0.3 | XXX | XXX | Dsgn % Compl is between | 15% | 30% | -1 | 0.4 | 0.25 | XXX | XXX
[17 empty] | Dsgn % Compl is between | 30% | 95% | -0.46154 | 0.35 | 0.05 | XXX | XXX | Dsgn % Compl is between | 30% | 60% | -0.16667 | 0.3 | 0.25 | XXX | XXX | Dsgn % Compl is between | 30% | 60% | -0.5 | 0.25 | 0.1 | XXX | XXX
[17 empty] | Dsgn % Compl is between | 95% | 100% | -1 | 0.05 | 0 | XXX | XXX | Dsgn % Compl is between | 60% | 95% | -0.42857 | 0.25 | 0.1 | XXX | XXX | Dsgn % Compl is between | 60% | 95% | -0.14286 | 0.1 | 0.05 | XXX | XXX
[25 empty] | Dsgn % Compl is between | 95% | 100% | -2 | 0.1 | 0 | XXX | XXX | Dsgn % Compl is between | 95% | 100% | -1 | 0.05 | 0 | XXX | XXX
[25 empty] | Constr. % Compl is between | 0% | 20% | -0.25 | 0.15 | 0.1 | 0 | 0.15 | Constr. % Compl is between | 0% | 20% | -0.5 | 0.2 | 0.1 | 0 | 0.2
[25 empty] | Constr. % Compl is between | 20% | 50% | -0.16667 | 0.1 | 0.05 | XXX | XXX | Constr. % Compl is between | 20% | 50% | -0.16667 | 0.1 | 0.05 | XXX | XXX
[25 empty] | Constr. % Compl is between | 50% | 100% | -0.1 | 0.05 | 0 | XXX | XXX | Constr. % Compl is between | 50% | 100% | -0.1 | 0.05 | 0 | XXX | XXX
[9 empty] | Acquisition Risk (M) |  |  |  | Acquisition (M) ∆Beta is: |  |  | 0 | Acquisition Risk |  |  |  | Acquisition (M) ∆Beta is: |  |  | 0 | Acquisition Risk |  |  |  | Acquisition (M) ∆Beta is: |  |  | 0.1 | Acquisition Risk |  |  |  | Acquisition (M) ∆Beta is: |  |  | 0.2
[9 empty] | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta: | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta: | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta: | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta:
[9 empty] | Dsgn % Compl is between | 15% | 30% | 0 | 0.05 | 0.05 | XXX | XXX | Dsgn % Compl is between | 15% | 30% | -0.66667 | 0.3 | 0.2 | XXX | XXX | Dsgn % Compl is between | 15% | 30% | -0.46667 | 0.3 | 0.23 | XXX | XXX | Dsgn % Compl is between | 15% | 60% | 0 | 0.3 | 0.3 | XXX | XXX
[9 empty] | Dsgn % Compl is between | 30% | 60% | -0.16667 | 0.05 | 0 | XXX | XXX | Dsgn % Compl is between | 60% | 95% | -0.42857 | 0.2 | 0.05 | XXX | XXX | Dsgn % Compl is between | 30% | 60% | -0.26667 | 0.23 | 0.15 | XXX | XXX | Dsgn % Compl is between | 60% | 95% | -0.71429 | 0.3 | 0.05 | XXX | XXX
[9 empty] | Dsgn % Compl is between | 60% | 100% | 0 | 0 | 0 | XXX | XXX | Dsgn % Compl is between | 95% | 100% | 0 | 0 | 0 | XXX | XXX | Dsgn % Compl is between | 60% | 95% | -0.28571 | 0.15 | 0.05 | XXX | XXX | Dsgn % Compl is between | 95% | 100% | -1 | 0.05 | 0 | XXX | XXX
[25 empty] | Dsgn % Compl is between | 95% | 100% | -1 | 0.05 | 0 | XXX | XXX | Constr. % Compl is between | 0% | 20% | -0.25 | 0.2 | 0.15 | 0 | 0.2
[25 empty] | Constr. % Compl is between | 0% | 20% | -0.25 | 0.1 | 0.05 | 0 | 0.1 | Constr. % Compl is between | 20% | 50% | -0.33333 | 0.15 | 0.05 | XXX | XXX
[25 empty] | Constr. % Compl is between | 20% | 50% | 0 | 0.05 | 0.05 | XXX | XXX | Constr. % Compl is between | 50% | 100% | -0.1 | 0.05 | 0 | XXX | XXX
[25 empty] | Constr. % Compl is between | 50% | 100% | -0.1 | 0.05 | 0 | XXX | XXX
[9 empty] | Execution Risk (C) |  |  |  | Execution (C) ∆Beta is: |  |  | 0 | Execution Risk |  |  |  | Execution (C) ∆Beta is: |  |  | 0.1 | Execution Risk |  |  |  | Execution (C) ∆Beta is: |  |  | 0.2 | Execution Risk |  |  |  | Execution (C) ∆Beta is: |  |  | 0.35
[9 empty] | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta: | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta: | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta: | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta:
[9 empty] | Dsgn % Compl is between | 15% | 30% | -0.33333 | 0.2 | 0.15 | XXX | XXX | Dsgn % Compl is between | 15% | 60% | 0 | 0.25 | 0.25 | XXX | XXX | Dsgn % Compl is between | 15% | 30% | -0.33333 | 0.15 | 0.1 | XXX | XXX | Constr. % Compl is between | 0% | 20% | -0.25 | 0.25 | 0.2 | 0 | 0.25
[9 empty] | Dsgn % Compl is between | 30% | 60% | -0.5 | 0.15 | 0 | XXX | XXX | Dsgn % Compl is between | 60% | 95% | -0.71429 | 0.25 | 0 | XXX | XXX | Dsgn % Compl is between | 30% | 60% | -0.16667 | 0.1 | 0.05 | XXX | XXX | Constr. % Compl is between | 20% | 50% | -0.16667 | 0.2 | 0.15 | XXX | XXX
[9 empty] | Dsgn % Compl is between | 60% | 100% | 0 | 0 | 0 | XXX | XXX | Dsgn % Compl is between | 95% | 100% | 0 | 0 | 0 | XXX | XXX | Dsgn % Compl is between | 60% | 95% | -0.14286 | 0.05 | 0 | XXX | XXX | Constr. % Compl is between | 50% | 100% | -0.3 | 0.15 | 0 | XXX | XXX
[17 empty] | Constr. % Compl is between | 0% | 20% | -0.5 | 0.1 | 0 | 0 | 0.1 | Dsgn % Compl is between | 95% | 100% | 0 | 0 | 0 | XXX | XXX | Post-RSD % Compl is between | 0% | 100% | -0.1 | 0.1 | 0 | 0 | 0.1
[17 empty] | Constr. % Compl is between | 20% | 100% | 0 | 0 | 0 | XXX | XXX | Constr. % Compl is between | 0% | 20% | 0 | 0.2 | 0.2 | 0 | 0.2
[25 empty] | Constr. % Compl is between | 20% | 50% | -0.16667 | 0.2 | 0.15 | XXX | XXX
[25 empty] | Constr. % Compl is between | 50% | 100% | -0.3 | 0.15 | 0 | XXX | XXX
[9 empty] | Closeout Risk |  |  |  | Closeout (P) ∆Beta is: |  |  | 0.05 | Closeout Risk |  |  |  | Closeout (P) ∆Beta is: |  |  | 0.05 | Closeout Risk |  |  |  | Closeout (P) ∆Beta is: |  |  | 0.05 | Closeout Risk |  |  |  | Closeout (P) ∆Beta is: |  |  | 0.05
[9 empty] | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta: | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta: | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta: | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta:
[9 empty] | Post-RSD % Compl is between | 0% | 100% | -0.05 | 0.05 | 0 | 0 | 0.05 | Post-RSD % Compl is between | 0% | 100% | -0.05 | 0.05 | 0 | 0 | 0.05 | Post-RSD % Compl is between | 0% | 100% | -0.05 | 0.05 | 0 | 0 | 0.05 | Post-RSD % Compl is between | 0% | 100% | -0.05 | 0.05 | 0 | 0 | 0.05
[9 empty] | SCCs 80.05 ∆Beta general uncertainty drawdown calculations | [7 empty] | SCCs 80.06 ∆Beta general uncertainty drawdown calculations | [7 empty] | SCCs 80.07 ∆Beta general uncertainty drawdown calculations | [7 empty] | SCCs 80.08 ∆Beta general uncertainty drawdown calculations
[9 empty] | Requirements Risk |  |  |  | Requirements (R) ∆Beta is: |  |  | 0 | Requirements Risk |  |  |  | Requirements (R) ∆Beta is: |  |  | 0 | Requirements Risk |  |  |  | Requirements (R) ∆Beta is: |  |  | 0 | Requirements Risk |  |  |  | Requirements (R) ∆Beta is: |  |  | 0
[9 empty] | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta: | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta: | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta: | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta:
[9 empty] | Dsgn % Compl is between | 15% | 100% | 0 | 0 | 0 | XXX | XXX | Dsgn % Compl is between | 15% | 100% | 0 | 0 | 0 | XXX | XXX | Dsgn % Compl is between | 15% | 100% | 0 | 0 | 0 | XXX | XXX | Dsgn % Compl is between | 15% | 100% | 0 | 0 | 0 | XXX | XXX
[9 empty] | Planning Risk |  |  |  | Planning (D) ∆Beta is: |  |  | 0 | Planning Risk |  |  |  | Planning (D) ∆Beta is: |  |  | 0.1 | Planning Risk |  |  |  | Planning (D) ∆Beta is: |  |  | 0.1 | Planning Risk |  |  |  | Planning (D) ∆Beta is: |  |  | 0.4
[9 empty] | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta: | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta: | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta: | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta:
[9 empty] | Dsgn % Compl is between | 15% | 30% | -0.46667 | 0.3 | 0.23 | XXX | XXX | Dsgn % Compl is between | 15% | 30% | -1 | 0.5 | 0.35 | XXX | XXX | Dsgn % Compl is between | 15% | 30% | -0.66667 | 0.3 | 0.2 | XXX | XXX | Dsgn % Compl is between | 15% | 60% | 0 | 0.2 | 0.2 | XXX | XXX
[9 empty] | Dsgn % Compl is between | 30% | 60% | -0.26667 | 0.23 | 0.15 | XXX | XXX | Dsgn % Compl is between | 30% | 60% | -0.5 | 0.35 | 0.2 | XXX | XXX | Dsgn % Compl is between | 30% | 60% | -0.33333 | 0.2 | 0.1 | XXX | XXX | Dsgn % Compl is between | 30% | 60% | -0.66667 | 0.2 | 0 | XXX | XXX
[9 empty] | Dsgn % Compl is between | 60% | 95% | -0.28571 | 0.15 | 0.05 | XXX | XXX | Dsgn % Compl is between | 60% | 95% | -0.28571 | 0.2 | 0.1 | XXX | XXX | Dsgn % Compl is between | 60% | 95% | 0 | 0.1 | 0.1 | XXX | XXX | Dsgn % Compl is between | 60% | 100% | 0 | 0 | 0 | XXX | XXX
[17 empty] | Dsgn % Compl is between | 95% | 100% | -2 | 0.1 | 0 | XXX | XXX | Dsgn % Compl is between | 95% | 100% | -2 | 0.1 | 0 | XXX | XXX | Constr. % Compl is between | 0% | 20% | -1 | 0.4 | 0.2 | 0 | 0.4
[17 empty] | Constr. % Compl is between | 0% | 20% | -0.25 | 0.1 | 0.05 | 0 | 0.1 | Constr. % Compl is between | 0% | 20% | 0 | 0.1 | 0.1 | 0 | 0.1 | Constr. % Compl is between | 20% | 50% | -0.16667 | 0.2 | 0.15 | XXX | XXX
[17 empty] | Constr. % Compl is between | 20% | 50% | -0.16667 | 0.05 | 0 | XXX | XXX | Constr. % Compl is between | 20% | 50% | -0.16667 | 0.1 | 0.05 | XXX | XXX | Constr. % Compl is between | 50% | 100% | -0.3 | 0.15 | 0 | XXX | XXX
[17 empty] | Constr. % Compl is between | 50% | 100% | 0 | 0 | 0 | XXX | XXX | Constr. % Compl is between | 50% | 100% | -0.1 | 0.05 | 0 | XXX | XXX
[9 empty] | Acquisition Risk |  |  |  | Acquisition (M) ∆Beta is: |  |  | 0 | Acquisition Risk |  |  |  | Acquisition (M) ∆Beta is: |  |  | 0.05 | Acquisition Risk |  |  |  | Acquisition (M) ∆Beta is: |  |  | 0.15 | Acquisition Risk |  |  |  | Acquisition (M) ∆Beta is: |  |  | 0.25
[9 empty] | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta: | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta: | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta: | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta:
[9 empty] | Dsgn % Compl is between | 15% | 30% | -0.46667 | 0.25 | 0.18 | XXX | XXX | Dsgn % Compl is between | 15% | 30% | -0.8 | 0.45 | 0.33 | XXX | XXX | Dsgn % Compl is between | 15% | 30% | -0.66667 | 0.3 | 0.2 | XXX | XXX | Constr. % Compl is between | 0% | 20% | 0 | 0.25 | 0.25 | 0 | 0.25
[9 empty] | Dsgn % Compl is between | 30% | 60% | -0.26667 | 0.18 | 0.1 | XXX | XXX | Dsgn % Compl is between | 30% | 60% | -0.43333 | 0.33 | 0.2 | XXX | XXX | Dsgn % Compl is between | 30% | 60% | -0.33333 | 0.2 | 0.1 | XXX | XXX | Constr. % Compl is between | 20% | 50% | -0.33333 | 0.25 | 0.15 | XXX | XXX
[9 empty] | Dsgn % Compl is between | 60% | 95% | -0.14286 | 0.1 | 0.05 | XXX | XXX | Dsgn % Compl is between | 60% | 95% | -0.42857 | 0.2 | 0.05 | XXX | XXX | Dsgn % Compl is between | 60% | 95% | -0.28571 | 0.1 | 0 | XXX | XXX | Constr. % Compl is between | 50% | 100% | -0.3 | 0.15 | 0 | XXX | XXX
[9 empty] | Dsgn % Compl is between | 95% | 100% | -1 | 0.05 | 0 | XXX | XXX | Dsgn % Compl is between | 95% | 100% | -1 | 0.05 | 0 | XXX | XXX | Dsgn % Compl is between | 95% | 100% | 0 | 0 | 0 | XXX | XXX
[17 empty] | Constr. % Compl is between | 0% | 20% | -0.25 | 0.05 | 0 | 0 | 0.05 | Constr. % Compl is between | 0% | 20% | -0.25 | 0.15 | 0.1 | 0 | 0.15
[17 empty] | Constr. % Compl is between | 20% | 100% | 0 | 0 | 0 | XXX | XXX | Constr. % Compl is between | 20% | 50% | -0.16667 | 0.1 | 0.05 | XXX | XXX
[25 empty] | Constr. % Compl is between | 50% | 100% | 0 | 0 | 0 | XXX | XXX
[9 empty] | Execution Risk |  |  |  | Execution (C) ∆Beta is: |  |  | 0.15 | Execution Risk |  |  |  | Execution (C) ∆Beta is: |  |  | 0.15 | Execution Risk |  |  |  | Execution (C) ∆Beta is: |  |  | 0.3 | Execution Risk |  |  |  | Execution (C) ∆Beta is: |  |  | 0.6
[9 empty] | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta: | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta: | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta: | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta:
[9 empty] | Constr. % Compl is between | 0% | 20% | -0.25 | 0.15 | 0.1 | 0 | 0.15 | Dsgn % Compl is between | 15% | 30% | -0.13333 | 0.1 | 0.08 | XXX | XXX | Dsgn % Compl is between | 15% | 60% | 0 | 0.2 | 0.2 | XXX | XXX | Constr. % Compl is between | 0% | 50% | 0 | 0.2 | 0.2 | 0 | 0.2
[9 empty] | Constr. % Compl is between | 20% | 50% | -0.16667 | 0.1 | 0.05 | XXX | XXX | Dsgn % Compl is between | 30% | 60% | -0.1 | 0.08 | 0.05 | XXX | XXX | Dsgn % Compl is between | 60% | 95% | -0.57143 | 0.2 | 0 | XXX | XXX | Constr. % Compl is between | 50% | 100% | -0.4 | 0.2 | 0 | XXX | XXX
[9 empty] | Constr. % Compl is between | 50% | 100% | -0.1 | 0.05 | 0 | XXX | XXX | Dsgn % Compl is between | 60% | 95% | -0.14286 | 0.05 | 0 | XXX | XXX | Dsgn % Compl is between | 95% | 100% | 0 | 0 | 0 | XXX | XXX | Post-RSD % Compl is between | 0% | 100% | -0.4 | 0.4 | 0 | 0 | 0.4
[17 empty] | Dsgn % Compl is between | 95% | 100% | 0 | 0 | 0 | XXX | XXX | Constr. % Compl is between | 0% | 20% | -0.25 | 0.2 | 0.15 | 0 | 0.2
[17 empty] | Constr. % Compl is between | 0% | 20% | 0 | 0.15 | 0.15 | 0 | 0.15 | Constr. % Compl is between | 20% | 50% | -0.33333 | 0.15 | 0.05 | XXX | XXX
[17 empty] | Constr. % Compl is between | 20% | 50% | -0.16667 | 0.15 | 0.1 | XXX | XXX | Constr. % Compl is between | 50% | 100% | -0.1 | 0.05 | 0 | XXX | XXX
[17 empty] | Constr. % Compl is between | 50% | 100% | -0.2 | 0.1 | 0 | XXX | XXX | Post-RSD % Compl is between | 0% | 100% | -0.1 | 0.1 | 0 | 0 | 0.1
[9 empty] | Closeout Risk |  |  |  | Closeout (P) ∆Beta is: |  |  | 0.05 | Closeout Risk |  |  |  | Closeout (P) ∆Beta is: |  |  | 0.05 | Closeout Risk |  |  |  | Closeout (P) ∆Beta is: |  |  | 0.05 | Closeout Risk |  |  |  | Closeout (P) ∆Beta is: |  |  | 0.05
[9 empty] | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta: | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta: | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta: | If: | Lower bracket | Upper bracket | Factor | Starting value: | Ending value: | Plus % Drawdown times factor | Equals ∆Beta:
[9 empty] | Post-RSD % Compl is between | 0% | 100% | -0.05 | 0.05 | 0 | 0 | 0.05 | Post-RSD % Compl is between | 0% | 100% | -0.05 | 0.05 | 0 | 0 | 0.05 | Post-RSD % Compl is between | 0% | 100% | -0.05 | 0.05 | 0 | 0 | 0.05 | Post-RSD % Compl is between | 0% | 100% | -0.05 | 0.05 | 0 | 0 | 0.05

## Infl_Deflation Calculator
Enter BY or YOE values as indicted and read inflated or deflated values. The calculations are based on the initial Sponsor inflation values from its SCC Workbook, as included in the "Sponsor SCC Main" worksheet
M A I N W O R K S H E E T B U I L D A L T E R N A T I V E |  |  | Base Year (BY) to Year of Expenditure (YOE) Calculator (Inflator) |  | Year of Expenditure (YOE) to Base Year (BY) Calculator (Deflator)
|  | Inflation from "Sponsor SCC Main" worksheet | Enter BY value | Read YOE value | Enter YOE value | Read BY value
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 0
10.01 | Guideway: At-grade exclusive right-of-way | 0 |  | 0 |  | 0
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | 0 |  | 0 |  | 0
10.03 | Guideway: At-grade in mixed traffic | 0 |  | 0 |  | 0
10.04 | Guideway: Aerial structure | 0 |  | 0 |  | 0
10.05 | Guideway: Built-up fill | 0 |  | 0 |  | 0
10.06 | Guideway: Underground cut & cover | 0 |  | 0 |  | 0
10.07 | Guideway: Underground tunnel | 0 |  | 0 |  | 0
10.08 | Guideway: Retained cut or fill | 0 |  | 0 |  | 0
10.09 | Track: Direct fixation | 0 |  | 0 |  | 0
10.1 | Track: Embedded | 0 |  | 0 |  | 0
10.11 | Track: Ballasted | 0 |  | 0 |  | 0
10.12 | Track: Special (switches, turnouts) | 0 |  | 0 |  | 0
10.13 | Track: Vibration and noise dampening | 0 |  | 0 |  | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 0
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 0 |  | 0 |  | 0
20.02 | Aerial station, stop, shelter, mall, terminal, platform | 0 |  | 0 |  | 0
20.03 | Underground station, stop, shelter, mall, terminal, platform | 0 |  | 0 |  | 0
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. | 0 |  | 0 |  | 0
20.05 | Joint development | 0 |  | 0 |  | 0
20.06 | Automobile parking multi-story structure | 0 |  | 0 |  | 0
20.07 | Elevators, escalators | 0 |  | 0 |  | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  | 0
30.01 | Administration Building: Office, sales, storage, revenue counting | 0 |  | 0 |  | 0
30.02 | Light Maintenance Facility | 0 |  | 0 |  | 0
30.03 | Heavy Maintenance Facility | 0 |  | 0 |  | 0
30.04 | Storage or Maintenance of Way Building | 0 |  | 0 |  | 0
30.05 | Yard and Yard Track | 0 |  | 0 |  | 0
40 SITEWORK & SPECIAL CONDITIONS |  | 0
40.01 | Demolition, Clearing, Earthwork | 0 |  | 0 |  | 0
40.02 | Site Utilities, Utility Relocation | 0 |  | 0 |  | 0
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments | 0 |  | 0 |  | 0
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks | 0 |  | 0 |  | 0
40.05 | Site structures including retaining walls, sound walls | 0 |  | 0 |  | 0
40.06 | Pedestrian / bike access and accommodation, landscaping | 0 |  | 0 |  | 0
40.07 | Automobile, bus, van accessways including roads, parking lots | 0 |  | 0 |  | 0
40.08 | Temporary Facilities and other indirect costs during construction | 0 |  | 0 |  | 0
50 SYSTEMS |  | 0
50.01 | Train control and signals | 0 |  | 0 |  | 0
50.02 | Traffic signals and crossing protection | 0 |  | 0 |  | 0
50.03 | Traction power supply: substations | 0 |  | 0 |  | 0
50.04 | Traction power distribution: catenary and third rail | 0 |  | 0 |  | 0
50.05 | Communications | 0 |  | 0 |  | 0
50.06 | Fare collection system and equipment | 0 |  | 0 |  | 0
50.07 | Central Control | 0 |  | 0 |  | 0
Construction Subtotal (10 - 50)
60 ROW, LAND, EXISTING IMPROVEMENTS |  | 0
60.01 | Purchase or lease of real estate | 0 |  | 0 |  | 0
60.02 | Relocation of existing households and businesses | 0 |  | 0 |  | 0
70 VEHICLES (number) |  | 0
70.01 | Light Rail | 0 |  | 0 |  | 0
70.02 | Heavy Rail | 0 |  | 0 |  | 0
70.03 | Commuter Rail | 0 |  | 0 |  | 0
70.04 | Bus | 0 |  | 0 |  | 0
70.05 | Other | 0 |  | 0 |  | 0
70.06 | Non-revenue vehicles | 0 |  | 0 |  | 0
70.07 | Spare parts | 0 |  | 0 |  | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) |  | 0
80.01 | Project Development | 0 |  | 0 |  | 0
80.02 | Engineering (not applicable to Small Starts) | 0 |  | 0 |  | 0
80.03 | Project Management for Design and Construction | 0 |  | 0 |  | 0
80.04 | Construction Administration & Management | 0 |  | 0 |  | 0
80.05 | Professional Liability and other Non-Construction Insurance | 0 |  | 0 |  | 0
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. | 0 |  | 0 |  | 0
80.07 | Surveys, Testing, Investigation, Inspection | 0 |  | 0 |  | 0
80.08 | Start up | 0 |  | 0 |  | 0

## Cost Risk Calcs Schema
Sponsor info | [6 empty] | PMOC Pre-risk Adjustments | [7 empty] | PMOC Risk Analysis
| Base year |  | YOE |  | YOE
| (Uses SCC Wkbk) |  | (Uses SCC Wkbk) |  | (Uses SCC Wkbk) | [5 empty] | (Adjusted SCC Wkbk)
| Sponsor SCC Main |  | Sponsor SCC Inflation |  | Sponsor SCC Main |  | Sponsor SCC Main |  | PMOC BY Adj |  | PMOC Infl Adjst |  | PMOC YOE Adj |  | PMOC YOE Adj |  | Risk Assessment |  | Risk Assessment |  | Risk Assessment Analysis
| Base year cost |  |  |  |  | >>> | Base year cost | plus | PMOC adjustmts | times | PMOC adjusted Inflation | equals | Stripped, Adjusted Est | >>> | Stripped, Adjusted Est | factored by | Risk Beta factors | applied to | Risk Beta curve | reported as | Risk findings
plus | BY allocated contingency | [7 empty] | (Direct cost) | [5 empty] | (Lower Bound) |  | (Phase-related uncertainty factors)
equals | Base year total cost | times | Inflation amount | equals | YOE total cost |  |  |  | (Time-related) | [7 empty] | (Risk-specific factors)
plus | BY unallocated contingency | times | Inflation amount | equals | YOE unallocated Contingency |  |  |  | (Latent Conting.)
equals | BY Budget | times | Inflation amount | equals | YOE budget

## Change Log
Please direct questions, comments and inquiries to: Lisa Gavin Federal Transit Administration Office of Program Management 1200 New Jersey Avenue, S.E. Washington, DC 20590 lisa.gavin@dot.gov 202-366-9291
Risk Model Version Number | Date Published | Changes
5.16a | 2021 May 14 | revisions incorporated, checked and tested by David Sillars
5.16b | 2022 April 28 | added change log sheet
changed password
added model version text on several sheets
corrected spelling errors
PMOC Project Background tab - reset note spacing in cells C16, C17, C18
Sponsor SCC Main tab - added the same formula as the SCC Workbook in column K to calculate inflation factor and also the formula in rows 78 thru 84 (denoted by blue fill color)
PMOC BY Risk Profile Values tab - corrected spacing to show Column A, revised title in cells O3-R3 from "Sponsor Base Year Dollars from SCC Main" to "Sponsor Base Year Dollars w/o contingency x Inflation Factor"
PMOC Profl Infl Adj tab - reset spacing to view column A content
Base Uncertainty Instructions tab - revised spacing of text boxes in columns J and K
checked and tested by Lisa Gavin