## SCC List
Standard Cost Categories for New Starts Projects
(Rev.19, June, 2017)
10 GUIDEWAY & TRACK ELEMENTS (route miles)
10.01 | Guideway: At-grade exclusive right-of-way
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic)
10.03 | Guideway: At-grade in mixed traffic
10.04 | Guideway: Aerial structure
10.05 | Guideway: Built-up fill
10.06 | Guideway: Underground cut & cover
10.07 | Guideway: Underground tunnel
10.08 | Guideway: Retained cut or fill
10.09 | Track: Direct fixation
10.1 | Track: Embedded
10.11 | Track: Ballasted
10.12 | Track: Special (switches, turnouts)
10.13 | Track: Vibration and noise dampening
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number)
20.01 | At-grade station, stop, shelter, mall, terminal, platform
20.02 | Aerial station, stop, shelter, mall, terminal, platform
20.03 | Underground station, stop, shelter, mall, terminal, platform
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc.
20.05 | Joint development
20.06 | Automobile parking multi-story structure
20.07 | Elevators, escalators
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS
30.01 | Administration Building: Office, sales, storage, revenue counting
30.02 | Light Maintenance Facility
30.03 | Heavy Maintenance Facility
30.04 | Storage or Maintenance of Way Building
30.05 | Yard and Yard Track
40 SITEWORK & SPECIAL CONDITIONS
40.01 | Demolition, Clearing, Earthwork
40.02 | Site Utilities, Utility Relocation
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks
40.05 | Site structures including retaining walls, sound walls
40.06 | Pedestrian / bike access and accommodation, landscaping
40.07 | Automobile, bus, van accessways including roads, parking lots
40.08 | Temporary Facilities and other indirect costs during construction
50 SYSTEMS
50.01 | Train control and signals
50.02 | Traffic signals and crossing protection
50.03 | Traction power supply: substations
50.04 | Traction power distribution: catenary and third rail
50.05 | Communications
50.06 | Fare collection system and equipment
50.07 | Central Control
60 ROW, LAND, EXISTING IMPROVEMENTS
60.01 | Purchase or lease of real estate
60.02 | Relocation of existing households and businesses
70 VEHICLES (number)
70.01 | Light Rail
70.02 | Heavy Rail
70.03 | Commuter Rail
70.04 | Bus
70.05 | Other
70.06 | Non-revenue vehicles
70.07 | Spare parts
80 PROFESSIONAL SERVICES (applies to Cats. 10-50)
80.01 | Project Development
80.02 | Engineering
80.03 | Project Management for Design and Construction
80.04 | Construction Administration & Management
80.05 | Professional Liability and other Non-Construction Insurance
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc.
80.07 | Surveys, Testing, Investigation, Inspection
80.08 | Start up
90 UNALLOCATED CONTINGENCY
100 FINANCE CHARGES

## SCC Definitions
Standard Cost Categories for Capital Projects D E F I N I T I O N S |  | NOTE: The SCC cost breakdown is based on a traditional Design Bid Build model. If your project is Design Build, to the best of your ability, separate construction costs from design, administration, testing, etc. Put all construction costs in 10 through 50. Put design, administration, testing, etc. in 80 Professional Services.
(Rev.19, June, 2017)
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | Include guideway and track costs for all transit modes (heavy rail, light rail, commuter rail, BRT, rapid bus, bus, monorail, cable car, etc.) The unit of measure is route miles of guideway, regardless of width. As associated with the guideway, include costs for rough grading, excavation, and concrete base for guideway where applicable. Include all construction materials and labor regardless of whom is performing the work. In your written description of the scope, and in supporting graphic diagrams, indicate whether busway or rail track is single, double, triple, relocated, etc. Put guideway and track elements associated with yards in 30 Support Facilities below.
10.01 | Guideway: At-grade exclusive right-of-way
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic)
10.03 | Guideway: At-grade in mixed traffic
10.04 | Guideway: Aerial structure | Include foundation excavation; guideway structures including caissons, columns, bridges, viaducts, cross-overs, fly-overs.
10.05 | Guideway: Built-up fill | Include construction of earthen berms.
10.06 | Guideway: Underground cut & cover | Include excavation, retaining walls, backfill, underground guideway structure and finishes.
10.07 | Guideway: Underground tunnel | Include tunneling by means of a tunnel boring machine, drill blasting, mining, and immersed tube tunneling; tunnel structure and finishes.
10.08 | Guideway: Retained cut or fill | Include excavation, retaining walls, backfill, underground guideway structure and finishes.
10.09 | Track: Direct fixation | Include rails, connectors.
10.1 | Track: Embedded | Include rails, ties; ballast where applicable
10.11 | Track: Ballasted | Include rails, ties and ballast.
10.12 | Track: Special (switches, turnouts) | Include transitional curves.
10.13 | Track: Vibration and noise dampening | Include upcharge for vib/noise dampening to any track condition above.
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | As associated with stations, include costs for rough grading, excavation, station structures, enclosures, finishes, equipment; mechanical and electrical components including HVAC, ventilation shafts and equipment, station power, lighting, public address/customer information system, safety systems such as fire detection and prevention, security surveillance, access control, life safety systems, etc. Include all construction materials and labor regardless of whom is performing the work. NOTE: Count paired inbound/outbound boarding platforms as one station - do not report the total number of boarding platforms.
Put guideway and track associated with stations in 10 Guideway & Track Elements above.
20.01 | At-grade station, stop, shelter, mall, terminal, platform
20.02 | Aerial station, stop, shelter, mall, terminal, platform | Include station structures including caissons, columns, platforms, superstructures, etc.
20.03 | Underground station, stop, shelter, mall, terminal, platform | Include retaining walls, backfill, structure.
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc.
20.05 | Joint development | Per FTA's Joint Development Guidance, "Joint development is any income-producing activity with a transit nexus related to a real estate asset in which FTA has an interest. ...Joint development projects are commercial, residential, industrial, or mixed-use developments that are induced by or enhance the effectiveness of transit projects. . ."
20.06 | Automobile parking multi-story structure | Include retaining walls, backfill, structure.
20.07 | Elevators, escalators
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  | As associated with support facilities, include costs for rough grading, excavation, support structures, enclosures, finishes, equipment; mechanical and electrical components including HVAC, ventilation shafts and equipment, facility power, lighting, public address system, safety systems such as fire detection and prevention, security surveillance, access control, life safety systems, etc. Include fueling stations. Include all construction materials and labor regardless of whom is performing the work.
Where a support facility shares the structure with a station, its cost may be included with station cost. Identify this with a note.
Except for guideway and track associated with a yard, include all guideway and track costs associated with support facilities in 10 Guideway & Track Elements above.
30.01 | Administration Building: Office, sales, storage, revenue counting
30.02 | Light Maintenance Facility | Include service, inspection, and storage facilities and equipment.
30.03 | Heavy Maintenance Facility | Include heavy maintenance and overhaul facilities and equipment.
30.04 | Storage or Maintenance of Way Building
30.05 | Yard and Yard Track | Include yard construction, guideway and track associated with yard.
40 SITEWORK & SPECIAL CONDITIONS |  | Include all construction materials and labor regardless of whom is performing the work.
40.01 | Demolition, Clearing, Earthwork | Include project-wide clearing, demolition and fine grading.
40.02 | Site Utilities, Utility Relocation | Include all site utilities - storm, sewer, water, gas, electric.
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments | Include underground storage tanks, fuel tanks, other hazardous materials and treatments, etc.
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks | Include other environmental mitigation not listed.
40.05 | Site structures including retaining walls, sound walls
40.06 | Pedestrian / bike access and accommodation, landscaping | Include sidewalks, paths, plazas, functional landscaping, site and station furniture, site lighting, signage, bike facilities, permanent fencing.
40.07 | Automobile, bus, van accessways including roads, parking lots | Include all on-grade paving.
40.08 | Temporary Facilities and other indirect costs during construction | As a general rule and to the extent possible, appropriately allocate indirect costs among the construction costs in Categories 10 through 50. Where that is not possible, include in 40.08 Temporary Facilities costs for mobilization, demobilization, phasing; time and temporary construction associated with weather (heat, rain, freezing, etc.); temporary power and facilities; temporary construction, easements, and barriers for storm water pollution prevention, temporary access and to mitigate construction impacts; project and construction supervision; general conditions, overhead, profit. NOTE: Include contractor's general liability and other insurance related to construction such as builder's risk in Cats. 10 - 50, not in 80 Professional Services below.
50 SYSTEMS |  | Include all construction materials and labor regardless of whom is performing the work.
50.01 | Train control and signals
50.02 | Traffic signals and crossing protection | Include signal prioritization at intersections.
50.03 | Traction power supply: substations
50.04 | Traction power distribution: catenary and third rail
50.05 | Communications | Include passenger information systems at stations and on vehicles (real time travel information; static maps and schedules). Include equipment to allow communications among vehicles and with central control.
50.06 | Fare collection system and equipment | Include fare sales and swipe machines, fare counting equipment.
50.07 | Central Control
Construction Subtotal (10 - 50)
60 ROW, LAND, EXISTING IMPROVEMENTS |  | Include professional services associated with the real estate component of the project. These costs may include agency staff oversight and administration, real estate and relocation consultants, legal counsel, court expenses, insurance, etc.
60.01 | Purchase or lease of real estate | If the value of right-of-way, land, and existing improvements is to be used as local match to the Federal funding of the project, include the total cost on this line item. In backup documentation, separate cost for land from cost for improvements. Identify whether items are leased, purchased or acquired through payment or for free. Include the costs for permanent surface and subsurface easements, trackage rights, etc.
60.02 | Relocation of existing households and businesses | In compliance with Uniform Relocation Act.
70 VEHICLES (number) |  | Include professional services associated with the vehicle component of the project. These costs may include agency staff oversight and administration, vehicle consultants, design and manufacturing contractors, legal counsel, warranty and insurance costs, etc.
70.01 | Light Rail | Include light rail and streetcar rail using electric, diesel or other power supply.
70.02 | Heavy Rail
70.03 | Commuter Rail | Include locomotives (diesel, electric, or other), trailer cars, self-propelled multiple units (EMU electric or DMU diesel, or other power supply)
70.04 | Bus | Includes "rubber-tired" buses and trolleys including new, used, historic replica, articulated, using electric, diesel, dual-power, or other power supply.
70.05 | Other | Include Vans, Sedan/Station Wagon, Cable Car, People Mover, Monorail, Car/Inclined Railway, Ferry Boat, Transferred Vehicle
70.06 | Non-revenue vehicles
70.07 | Spare parts
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) |  | Cat. 80 applies to Cats. 10-50. Cat. 80 includes all professional, technical and management services related to the design and construction of fixed infrastructure (Cats. 10 - 50) during the project development, engineering, and construction phases of the project. This includes environmental work, design, engineering and architectural services; specialty services such as safety or security analyses; value engineering, risk assessment, cost estimating, scheduling, Before and After studies, ridership modeling and analyses, auditing, legal services, administration and management, etc. by agency staff or outside consultants. Include professional liability insurance and other non-construction insurance on 80.05 unless insurance for the agency and its consultants is already included in other lines. Include costs associated with professional services related to real estate and vehicles in Cats. 60 and 70. (Note that costs for planning activities and NEPA work done before FTA approval to enter project development (PD), regardless of funding source, are not included in an FFGA and therefore, should not be included in the Standard Cost Category worksheets. For example, on one and the same grant, costs incurred prior to FTA approval to enter PD should be omitted from these worksheets whereas costs incurred after FTA approval to enter PD should be included.)
80.01 | Project Development
80.02 | Engineering
80.03 | Project Management for Design and Construction
80.04 | Construction Administration & Management
80.05 | Professional Liability and other Non-Construction Insurance
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc.
80.07 | Surveys, Testing, Investigation, Inspection
80.08 | Start up | Include start up and training. Include in Cats. 10 - 50 above access and protection work by agency staff or outside contractors.
Subtotal (10 - 80)
90 UNALLOCATED CONTINGENCY |  | Includes unallocated contingency, project reserves. Document allocated contingencies for individual line items on the BUILD Main worksheet.
Subtotal (10 - 90)
100 FINANCE CHARGES |  | Include finance charges expected to be paid by the project sponsor/grantee prior to either the completion of the project or the fulfillment of the New Starts funding commitment, whichever occurs later in time. Finance charges incurred after this date should not be included in Total Project Cost. (See FFGA Circular FTA C5200.1A Chapter III for additional information.) Derive finance charges from the New Starts project's financial plan, based on an analysis of the sources and uses of funds. The amount and type of debt financing required and revenues available determine the finance charges. By year, compute finance charges in year-of-expenditure (YOE) dollars. On the Inflation worksheet enter the finance charges for the appropriate years.
Total Project Cost (10 - 100)

## TrAMS Scopes ALIs
14-Series TrAMS Scope / Activity Line Items Required for all grants that serve a Capital Project
(Rev.19, June, 2017)
1. HOW DO THE SCC AND TrAMS RELATE? TrAMS is for grants management. Many grants can serve a capital project -- e.g. CMAQ, 5307, 5309, etc. The Standard Cost Categories (SCC) are for cost management, day to day as well as at important milestones. To manage capital project costs use the SCC worksheets, back up sheets, detailed cost estimates, etc. At important milestones, "paperclip" the SCC worksheets to the applicable grants in TrAMS. TrAMS and the SCC support each other but TrAMS doesn't duplicate the level of information in the SCC. Grant budgets will have just the ten lines. 2. WHEN SHOULD I USE THE 14-SERIES? Use it for capital projects. For a New Starts project, use it from the very first grant that funds Project Development, and include all grants issued through the FFGA; these grants may be small or large and may derive funding from diverse sources such as CMAQ, 5307, 5309 New Starts, Federal Non-Transportation funding from HUD, Defense, etc. 3. HOW IS THE 14-SERIES ORGANIZED AND WHY? The 14-Series has one Scope and 10 ALIs. The organization is intentionally simple. Put guideway costs under the Guideway ALI, station costs under the Station ALI. If the costs are organized simply, the information will be consistent program-wide and will produce a reliable database. For Vehicles, use the 13-Series ALIs. | 140-00 | PROJECT NAME - (this is the one Scope)
| 14.01.10 | GUIDEWAY & TRACK ELEMENTS |  | .01 Bus STD 40 FT
.02 Bus STD 35 FT
.03 Bus 30 FT
| 14.02.20 | STATIONS, STOPS, TERMINALS, INTERMODAL |  | .04 Bus < 30 FT
.05 Bus School
.06 Bus Articulated
| 14.03.30 | SUPPORT FACILITIES: YARDS, SHOPS, ADMIN BLDGS |  | .07 Bus Commuter / Suburban
.08 Bus Intercity
.09 Bus Trolley STD
| 14.04.40 | SITEWORK & SPECIAL CONDITIONS | Engineering & Design | .10 Bus Trolley Artic.
|  |  | 13.11.XX | .11 Bus Double Deck
.12 Bus Used
| 14.05.50 | SYSTEMS | Purchase - Replacement | .13 Bus School Used
|  |  | 13.12.XX | .14 Bus Dual Mode
.15 Vans
| 14.06.60 | ROW, LAND, EXISTING IMPROVEMENTS | Purchase - Expansion | .16 Sedan / Station Wagon
|  |  | 13.13.XX | .20 Light Rail Cars
.21 Heavy Rail Cars
| 13____ | VEHICLES - use the 13-Series ALIs for vehicles. | Rehabilitation / Rebuild | .22 Commuter Rail Self Propelled Electric
|  |  | 13.14.XX | .23 Commuter Rail Car Trailer
.24 Commuter Rail Locomotive Diesel
| 14.08.80 | PROFESSIONAL SERVICES | Mid Life Rebuild (Rail) | .25 Commuter Rail Locomotive Electric
|  |  | 13.15.XX | .26 Commuter Rail Cars Used
.27 Commuter Rail Locomotive Used
| 14.09.90 | UNALLOCATED CONTINGENCY | Lease - Replacement | .28 Commuter Rail Self Propelled - Diesel
|  |  | 13.16.XX | .30 Cable Car
.31 People Mover
| 14.10.10 | FINANCE CHARGES | Lease - Expansion | .32 Car, Incline Railway
|  |  | 13.18.XX | .33 Ferry Boats
.39 Transferred Vehicles
|  |  | Vehicle Overhaul | .40 Spare Parts/Assoc.Capital
|  |  | 13.17.00 | / Maintenance Items

## BUILD Main
M A I N W O R K S H E E T - B U I L D A L T E R N A T I V E | [8 empty] | (Rev.19, June, 2017)
Insert Project Sponsor's Name here | [6 empty] | Today's Date |  | 2026-08-06 11:41
Insert Project Name and Location | [6 empty] | Yr of Base Year $ |  | 2017
Insert Current Phase (e.g. Applic. for Engineering, Engineering, Applic. for FFGA, Construction, Rev Ops) | [6 empty] | Yr of Revenue Ops |  | 2020
|  | Quantity | Base Year Dollars w/o Contingency (X000) | Base Year Dollars Allocated Contingency (X000) | Base Year Dollars TOTAL (X000) | Base Year Dollars Unit Cost (X000) | Base Year Dollars Percentage of Construction Cost | Base Year Dollars Percentage of Total Project Cost | YOE Dollars Total (X000)
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 10 | 80000000 | 20000000 | 100000000 | 10000000 | 44.77% | 25.43% | 104780125 | 1.0478
10.01 | Guideway: At-grade exclusive right-of-way | 10 | 80000000 | 20000000 | 100000000 | 10000000 |  |  | 104780125
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) |  |  |  | 0 |  |  |  | 0
10.03 | Guideway: At-grade in mixed traffic |  |  |  | 0 |  |  |  | 0
10.04 | Guideway: Aerial structure |  |  |  | 0 |  |  |  | 0
10.05 | Guideway: Built-up fill |  |  |  | 0 |  |  |  | 0
10.06 | Guideway: Underground cut & cover |  |  |  | 0 |  |  |  | 0
10.07 | Guideway: Underground tunnel |  |  |  | 0 |  |  |  | 0
10.08 | Guideway: Retained cut or fill |  |  |  | 0 |  |  |  | 0
10.09 | Track: Direct fixation |  |  |  | 0 |  |  |  | 0
10.1 | Track: Embedded |  |  |  | 0 |  |  |  | 0
10.11 | Track: Ballasted |  |  |  | 0 |  |  |  | 0
10.12 | Track: Special (switches, turnouts) |  |  |  | 0 |  |  |  | 0
10.13 | Track: Vibration and noise dampening |  |  |  | 0 |  |  |  | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 20 | 28000000 | 2000000 | 30000000 | 1500000 | 13.43% | 7.628% | 32149428.75 | 1.0716
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 20 | 28000000 | 2000000 | 30000000 | 1500000 |  |  | 32149428.75
20.02 | Aerial station, stop, shelter, mall, terminal, platform |  |  |  | 0 |  |  |  | 0
20.03 | Underground station, stop, shelter, mall, terminal, platform |  |  |  | 0 |  |  |  | 0
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. |  |  |  | 0 |  |  |  | 0
20.05 | Joint development |  |  |  | 0 |  |  |  | 0
20.06 | Automobile parking multi-story structure |  |  |  | 0 |  |  |  | 0
20.07 | Elevators, escalators |  |  |  | 0 |  |  |  | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  | 10 | 8000000 | 2000000 | 10000000 | 1000000 | 4.477% | 2.543% | 10531125 | 1.0531
30.01 | Administration Building: Office, sales, storage, revenue counting |  |  |  | 0 |  |  |  | 0
30.02 | Light Maintenance Facility |  | 8000000 | 2000000 | 10000000 |  |  |  | 10531125
30.03 | Heavy Maintenance Facility |  |  |  | 0 |  |  |  | 0
30.04 | Storage or Maintenance of Way Building |  |  |  | 0 |  |  |  | 0
30.05 | Yard and Yard Track |  |  |  | 0 |  |  |  | 0
40 SITEWORK & SPECIAL CONDITIONS |  | 10 | 44350000 | 9000000 | 53350000 | 5335000 | 23.89% | 13.56% | 54167250 | 1.0153
40.01 | Demolition, Clearing, Earthwork |  | 9000000 | 1800000 | 10800000 |  |  |  | 10965441.4246
40.02 | Site Utilities, Utility Relocation |  | 18000000 | 3600000 | 21600000 |  |  |  | 21930882.8491
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments |  |  |  | 0 |  |  |  | 0
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks |  | 9000000 | 1800000 | 10800000 |  |  |  | 10965441.4246
40.05 | Site structures including retaining walls, sound walls |  |  |  | 0 |  |  |  | 0
40.06 | Pedestrian / bike access and accommodation, landscaping |  | 8350000 | 1800000 | 10150000 |  |  |  | 10305484.3018
40.07 | Automobile, bus, van accessways including roads, parking lots |  |  |  | 0 |  |  |  | 0
40.08 | Temporary Facilities and other indirect costs during construction |  |  |  | 0 |  |  |  | 0
50 SYSTEMS |  | 10 | 25000000 | 5000000 | 30000000 | 3000000 | 13.43% | 7.628% | 32149428.75 | 1.0716
50.01 | Train control and signals |  | 9000000 | 1000000 | 10000000 |  |  |  | 10716476.25
50.02 | Traffic signals and crossing protection |  | 2000000 | 500000 | 2500000 |  |  |  | 2679119.0625
50.03 | Traction power supply: substations |  | 4000000 | 1000000 | 5000000 |  |  |  | 5358238.125
50.04 | Traction power distribution: catenary and third rail |  | 4000000 | 1000000 | 5000000 |  |  |  | 5358238.125
50.05 | Communications |  | 4000000 | 1000000 | 5000000 |  |  |  | 5358238.125
50.06 | Fare collection system and equipment |  | 2000000 | 500000 | 2500000 |  |  |  | 2679119.0625
50.07 | Central Control |  |  |  | 0 |  |  |  | 0
Construction Subtotal (10 - 50) |  | 10 | 185350000 | 38000000 | 223350000 | 22335000 | 100% | 56.79% | 233777357.5
60 ROW, LAND, EXISTING IMPROVEMENTS |  | 10 | 30175000 | 5000000 | 35175000 | 3517500 |  | 8.944% | 35350000 | 1.005
60.01 | Purchase or lease of real estate |  | 30175000 | 5000000 | 35175000 |  |  |  | 35350000
60.02 | Relocation of existing households and businesses |  |  |  | 0 |  |  |  | 0
70 VEHICLES (number) |  | 15 | 27000000 | 3000000 | 30000000 | 2000000 |  | 7.628% | 31593375 | 1.0531
70.01 | Light Rail | 15 | 27000000 | 3000000 | 30000000 | 2000000 |  |  | 31593375
70.02 | Heavy Rail |  |  |  | 0 |  |  |  | 0
70.03 | Commuter Rail |  |  |  | 0 |  |  |  | 0
70.04 | Bus |  |  |  | 0 |  |  |  | 0
70.05 | Other |  |  |  | 0 |  |  |  | 0
70.06 | Non-revenue vehicles |  |  |  | 0 |  |  |  | 0
70.07 | Spare parts |  |  |  | 0 |  |  |  | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) |  | 10 | 70000000 | 7168000 | 77168000 | 7716800 | 34.55% | 19.62% | 77423560.75 | 1.0033
80.01 | Project Development |  | 5000000 | 668000 | 5668000 |  |  |  | 5686770.9715
80.02 | Engineering |  | 20000000 | 2000000 | 22000000 |  |  |  | 22072858.3934
80.03 | Project Management for Design and Construction |  | 5000000 | 500000 | 5500000 |  |  |  | 5518214.5983
80.04 | Construction Administration & Management |  | 20000000 | 2000000 | 22000000 |  |  |  | 22072858.3934
80.05 | Professional Liability and other Non-Construction Insurance |  | 5000000 | 500000 | 5500000 |  |  |  | 5518214.5983
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. |  | 5000000 | 500000 | 5500000 |  |  |  | 5518214.5983
80.07 | Surveys, Testing, Investigation, Inspection |  | 5000000 | 500000 | 5500000 |  |  |  | 5518214.5983
80.08 | Start up |  | 5000000 | 500000 | 5500000 |  |  |  | 5518214.5983
Subtotal (10 - 80) |  | 10 | 312525000 | 53168000 | 365693000 | 36569300 |  | 92.98% | 378144293.25
90 UNALLOCATED CONTINGENCY |  |  |  |  | 20000000 |  |  | 5.085% | 21074714.375 | 1.0537
Subtotal (10 - 90) |  | 10 |  |  | 385693000 | 38569300 |  | 98.07% | 399219007.625
100 FINANCE CHARGES |  |  |  |  | 7599635.2916 |  |  | 1.932% | 9499500 | 1.25
Total Project Cost (10 - 100) |  | 10 |  |  | 393292635.2916 | 39329263.5292 |  | 100% | 408718507.625 | 1.0392
Allocated Contingency as % of Base Yr Dollars w/o Contingency |  |  |  |  | 17.01%
Unallocated Contingency as % of Base Yr Dollars w/o Contingency |  |  |  |  | 6.399%
Total Contingency as % of Base Yr Dollars w/o Contingency |  |  |  |  | 23.41%
Unallocated Contingency as % of Subtotal (10 - 80) |  |  |  |  | 5.469%
YOE Construction Cost per Mile (X000) | [8 empty] | 23377735.75
YOE Total Project Cost per Mile Not Including Vehicles (X000) | [8 empty] | 37712513.2625
YOE Total Project Cost per Mile (X000) | [8 empty] | 40871850.7625
Note on D8: For all cells, enter costs to the $1. Note, all costs will be displayed to the nearest $1,000!
Note on F76: Enter finance charges on Inflation Worksheet.
Note on I19: Preparing for bid: For each separate contract package generate a Main Worksheet and an Inflation Worksheet. In the Special Conditions of the Contract, require the construction contractor to update these worksheets and submit them with the monthly pay application. This should make it easy to track costs in the SCC format throughout construction, and make it easy to submit the final costs to FTA at contract closeout and at the two-year post-rev ops date required by the Before and After Study.
Note on J3: Year of Base Year Dollars should match the year in "Today's Date."
Note on J6: YOE Dollars automatically arrive from Inflation Worksheet.
Note on J8: YOE costs for individual line items within a Category are derived as a percentage of the YOE cost of the Category.

## Inflation
I N F L A T I O N W O R K S H E E T |  |  |  | (Rev.19, June, 2017)
Insert Project Sponsor's Name here | Today's Date |  |  | 2026-08-06 11:41
Insert Project Name and Location | Yr of Base Year $ |  |  | 2017
Insert Current Phase (e.g. Applic. for Engineering, Engineering, Applic. for FFGA, Construction, Rev Ops) | Yr of Revenue Ops |  |  | 2020
Insert comments, notes, etc.
BASE YEAR DOLLARS (X$000) | Base Yr Dollars | Double-Check Total | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 100000000 | 100000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 45000000 | 45000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 30000000 | 30000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 10000000 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 10000000 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 SITEWORK & SPECIAL CONDITIONS | 53350000 | 53350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10350000 | 20000000 | 13000000 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 SYSTEMS | 30000000 | 30000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 10000000 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 ROW, LAND, EXISTING IMPROVEMENTS | 35175000 | 35175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5175000 | 20000000 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 VEHICLES (number) | 30000000 | 30000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000000 | 15000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) | 77168000 | 77167534.0284 | 0 | 0 | 0 | 0 | 0 | 593843.1528 | 1147523.0006 | 1108717.875 | 2142450 | 5175000 | 50000000 | 10000000 | 5000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 UNALLOCATED CONTINGENCY | 20000000 | 20000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5000000 | 5000000 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 FINANCE CHARGES | 7599635.2916 | 7599635.2916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 535076.8875 | 517500 | 500000 | 483091.7874 | 466755.3502 | 450971.3528 | 435721.1138 | 420986.5834 | 406750.3222 | 392995.4803 | 379705.7781 | 366865.4861 | 354459.4069 | 342472.8569 | 330891.6491 | 319702.0765 | 308890.8951 | 298445.3093 | 288352.9559 | 0 | 0 | 0 | 0
Total Project Cost (10 - 100) | 393292635.2916 | 393292169.32 | 0 | 0 | 0 | 0 | 0 | 593843.1528 | 1147523.0006 | 1108717.875 | 2677526.8875 | 21217500 | 105500000 | 123483091.7874 | 105466755.3502 | 27450971.3528 | 435721.1138 | 420986.5834 | 406750.3222 | 392995.4803 | 379705.7781 | 366865.4861 | 354459.4069 | 342472.8569 | 330891.6491 | 319702.0765 | 308890.8951 | 298445.3093 | 288352.9559 | 0 | 0 | 0 | 0
Inflation Rate |  |  | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 1.035 | 2.035 | 3.035 | 4.035
Compounded Inflation Factor |  |  | 1.4106 | 1.3629 | 1.3168 | 1.2723 | 1.2293 | 1.1877 | 1.1475 | 1.1087 | 1.0712 | 1.035 | 1 | 1.035 | 1.0712 | 1.1087 | 1.1475 | 1.1877 | 1.2293 | 1.2723 | 1.3168 | 1.3629 | 1.4106 | 1.46 | 1.5111 | 1.564 | 1.6187 | 1.6753 | 1.734 | 3.5287 | 10.7095 | 43.2128 | 217.5764
YEAR OF EXPENDITURE DOLLARS (X$000) | YOE Dollars |  | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 104780125 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 46575000 | 48205125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 32149428.75 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10350000 | 10712250 | 11087178.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 10531125 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5175000 | 5356125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 SITEWORK & SPECIAL CONDITIONS | 54167250 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 10000000 | 20000000 | 13455000 | 10712250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 SYSTEMS | 32149428.75 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10350000 | 10712250 | 11087178.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 ROW, LAND, EXISTING IMPROVEMENTS | 35350000 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 5000000 | 20000000 | 10350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 VEHICLES (number) | 31593375 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15525000 | 16068375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) | 77423560.75 |  | 0 | 0 | 0 | 0 | 0 | 500000 | 1000000 | 1000000 | 2000000 | 5000000 | 50000000 | 10350000 | 5356125 | 2217435.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 UNALLOCATED CONTINGENCY | 21074714.375 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5175000 | 5356125 | 5543589.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 FINANCE CHARGES | 9499500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499500 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 0 | 0 | 0 | 0
Total Project Cost (10 - 100) | 408718507.625 |  | 0 | 0 | 0 | 0 | 0 | 500000 | 1000000 | 1000000 | 2499500 | 20500000 | 105500000 | 127805000 | 112978625 | 30435382.625 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 0 | 0 | 0 | 0
Note on E24: For past years, enter the actual dollars spent in each year. The dollars will inflate when converted to the current base year.
Note on E33: Enter Finance Charges on this line.
Note on K8: Because of inflation, it costs more to buy the same goods and services today than it would have cost in previous years. The total base year dollar cost is a concept that represents the total project cost if the project were planned, designed and built in only one year, the designated base year.
Note on O8: In the white cells, insert project costs in the year in which they occurred (lower rows) or are planned to occur (upper rows) through the completion of the project or the fulfillment of the New Starts funding commitment, whichever is expected to occur later in time.
Note on O21: In the Base Year no inflation multiplier is used.

## Project Description
P R O J E C T D E S C R I P T I O N - B U I L D A L T E R N A T I V E |  |  | (Rev.19, June, 2017)
Insert Project Sponsor's Name here |  | Today's Date | 2026-08-06 11:41
Insert Project Name and Location
Insert Current Phase (e.g. Applic. for Engineering, Engineering, Applic. for FFGA, Construction, Rev Ops)
Describe the project elements to explain the unit costs shown on the Main Worksheet. Example: A 20-mile new light rail project has its guideway entirely on grade except for a one-eighth mile bridge over a river. The bridge or aerial structure may have a relatively high unit cost because there is little economy of scale. Mention precedents and reference points used in the development of costs for this project. Mention other aspects of this project that were important considerations in estimating costs. These could include the physical context, site constraints; design parameters; institutional, contracting and procurement conditions; project schedule, etc.
10 GUIDEWAY & TRACK ELEMENTS (route miles)
10.01 | Guideway: At-grade exclusive right-of-way
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic)
10.03 | Guideway: At-grade in mixed traffic
10.04 | Guideway: Aerial structure
10.05 | Guideway: Built-up fill
10.06 | Guideway: Underground cut & cover
10.07 | Guideway: Underground tunnel
10.08 | Guideway: Retained cut or fill
10.09 | Track: Direct fixation
10.1 | Track: Embedded
10.11 | Track: Ballasted
10.12 | Track: Special (switches, turnouts)
10.13 | Track: Vibration and noise dampening
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number)
20.01 | At-grade station, stop, shelter, mall, terminal, platform
20.02 | Aerial station, stop, shelter, mall, terminal, platform
20.03 | Underground station, stop, shelter, mall, terminal, platform
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc.
20.05 | Joint development
20.06 | Automobile parking multi-story structure
20.07 | Elevators, escalators
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS
30.01 | Administration Building: Office, sales, storage, revenue counting
30.02 | Light Maintenance Facility
30.03 | Heavy Maintenance Facility
30.04 | Storage or Maintenance of Way Building
30.05 | Yard and Yard Track
40 SITEWORK & SPECIAL CONDITIONS
40.01 | Demolition, Clearing, Earthwork
40.02 | Site Utilities, Utility Relocation
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks
40.05 | Site structures including retaining walls, sound walls
40.06 | Pedestrian / bike access and accommodation, landscaping
40.07 | Automobile, bus, van accessways including roads, parking lots
40.08 | Temporary Facilities and other indirect costs during construction
50 SYSTEMS
50.01 | Train control and signals
50.02 | Traffic signals and crossing protection
50.03 | Traction power supply: substations
50.04 | Traction power distribution: catenary and third rail
50.05 | Communications
50.06 | Fare collection system and equipment
50.07 | Central Control
Construction Subtotal (10 - 50)
60 ROW, LAND, EXISTING IMPROVEMENTS
60.01 | Purchase or lease of real estate
60.02 | Relocation of existing households and businesses
70 VEHICLES (number)
70.01 | Light Rail
70.02 | Heavy Rail
70.03 | Commuter Rail
70.04 | Bus
70.05 | Other
70.06 | Non-revenue vehicles
70.07 | Spare parts
80 PROFESSIONAL SERVICES (applies to Cats. 10-50)
80.01 | Project Development
80.02 | Engineering
80.03 | Project Management for Design and Construction
80.04 | Construction Administration & Management
80.05 | Professional Liability and other Non-Construction Insurance
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc.
80.07 | Surveys, Testing, Investigation, Inspection
80.08 | Start up
Subtotal (10 - 80)
90 UNALLOCATED CONTINGENCY
Subtotal (10 - 90)
100 FINANCE CHARGES
Total Project Cost (10 - 100)
Note on C8: These rows can be expanded to fit your narrative. Delete lines that are not needed.
Note on C27: For each garage, list station name, number of floors above and below grade, and number of spaces in each garage
Note on C42: For each parking lot, list station name and number of spaces

## Schedule
S C H E D U L E |  |  | (Rev.19, June, 2017)
Insert Project Sponsor's Name here | Today's Date |  | 2026-08-06 11:41
Insert Project Name and Location | Yr of Base Year $ |  | 2017
Insert Current Phase (e.g. Applic. for Engineering, Engineering, Applic. for FFGA, Construction, Rev Ops) | Yr of Revenue Ops |  | 2020
Insert comments, notes, etc. |  | Start Date | End Date | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035
Project Development |  | 2009-01-01 | 2011-01-01
Design
Develop cost estimate, schedule, ridership forecast
Conduct reviews
Develop NEPA document (DCE/EA/FEIS) and receive determination (CE/FONSI/ROD)
Submit request / receive FTA approval to enter Engineering
Engineering |  | 2011-01-02 | 2013-01-01
Develop the contract documents for the Build Alternative
Develop cost estimate, schedule
Acquire real estate; relocate households and businesses
Conduct reviews
Submit request / receive FTA approval for FFGA
Issue requests for bids, make awards of construction contracts
Construction |  | 2013-01-02 | 2017-01-01
Construct fixed infrastructure
Insert Contract Package Number and Description (i.e. Guideway, Stations, Systems, etc.)
Insert Contract Package Number and Description (i.e. Guideway, Stations, Systems, etc.)
Finalize real estate acquisitions and relocations
Acquire and test vehicles
Revenue Ops / Closeout of Project |  | 2017-01-02 | 2019-03-01
Revenue Service Date |  | 2017-01-02
Revenue Operations
Before and After Study: Two years post Rev Ops
Fulfillment of the New Starts funding commitment
Completion of project close-out, resolution of claims
Note on C7: On this Schedule and on the Inflation Worksheet, indicate the start of PD with the date of FTA's letter granting entry into PD. Delete any rows that are not needed.
Note on E6: Delete years that are not applicable.

## BUILD Annualized - Current
A N N U A L I Z E D C O S T - B U I L D A L T E R N A T I V E (Current Year) | [12 empty] | (Rev.19, June, 2017)
Insert Project Sponsor's Name here | [10 empty] | Today's Date |  | 2026-08-06 11:41
Insert Project Name and Location | [10 empty] | Yr of Base Year $ |  | 2017
Insert Current Phase (e.g. Applic. for Engineering, Engineering, Applic. for FFGA, Construction, Rev Ops) | [10 empty] | Yr of Revenue Ops |  | 2020
|  | Quantity | Total Base Year Dollars (X000) | Cat. 80 Prof. Svc. spread proportionally over Cats. 10 - 50 (X000) | Spread Cat. 90 Unalloc. Cont. according to perceived risks (X000) | Revised Total Base Year Dollars (X000) | Years of Useful Life | Annualization Factor (based on 2% rate) [.02/1 - (1.02)^-no. yrs] | Annualized Cost (X000) | Claiming Enrichment? | Portion of Base Year Cost that Qualifies for Enrichment (X000) | Portion of Annualized Cost that Qualifies for Enrichment (X000) | Name of Applicable Enrichment (further description provided in New Starts and Small Starts Policy Guidance)
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 10 | 100000000 | 34550257.4435 | 0 | 134550257.4435 |  |  | 2938212.718
10.01 | Guideway: At-grade exclusive right-of-way | 10 | 100000000 | 34550257.4435 |  | 134550257.4435 | 125 | 0.021837 | 2938212.718
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | 0 | 0 | 0 |  | 0 | 30 | 0.04465 | 0
10.03 | Guideway: At-grade in mixed traffic | 0 | 0 | 0 |  | 0 | 20 | 0.061157 | 0
10.04 | Guideway: Aerial structure | 0 | 0 | 0 |  | 0 | 80 | 0.025161 | 0
10.05 | Guideway: Built-up fill | 0 | 0 | 0 |  | 0 | 80 | 0.025161 | 0
10.06 | Guideway: Underground cut & cover | 0 | 0 | 0 |  | 0 | 125 | 0.021837 | 0
10.07 | Guideway: Underground tunnel | 0 | 0 | 0 |  | 0 | 125 | 0.021837 | 0
10.08 | Guideway: Retained cut or fill | 0 | 0 | 0 |  | 0 | 125 | 0.021837 | 0
10.09 | Track: Direct fixation |  | 0 | 0 |  | 0 | 30 | 0.04465 | 0
10.1 | Track: Embedded |  | 0 | 0 |  | 0 | 20 | 0.061157 | 0
10.11 | Track: Ballasted |  | 0 | 0 |  | 0 | 35 | 0.040002 | 0
10.12 | Track: Special (switches, turnouts) |  | 0 | 0 |  | 0 | 30 | 0.04465 | 0
10.13 | Track: Vibration and noise dampening |  | 0 | 0 |  | 0 | 30 | 0.04465 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 20 | 30000000 | 10365077.233 | 10000000 | 50365077.233 |  |  | 1343118.1783
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 20 | 30000000 | 10365077.233 | 10000000 | 50365077.233 | 70 | 0.026668 | 1343118.1783 | No |  | 0 | Sustainable Building Design Features
20.02 | Aerial station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 |  | 0 | 70 | 0.026668 | 0 | No |  | 0 | Sustainable Building Design Features
20.03 | Underground station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 |  | 0 | 125 | 0.021837 | 0 | No |  | 0 | Sustainable Building Design Features
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. | 0 | 0 | 0 |  | 0 | 70 | 0.026668 | 0 | No |  | 0 | Sustainable Building Design Features
20.05 | Joint development |  | 0 | 0 |  | 0 | 70 | 0.026668 | 0 | No |  | 0 | Joint Development
20.06 | Automobile parking multi-story structure |  | 0 | 0 |  | 0 | 50 | 0.031823 | 0
20.07 | Elevators, escalators |  | 0 | 0 |  | 0 | 30 | 0.04465 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  |  | 10000000 | 3455025.7443 | 0 | 13455025.7443 |  |  | 428182.1058
30.01 | Administration Building: Office, sales, storage, revenue counting |  | 0 | 0 |  | 0 | 50 | 0.031823 | 0 | No |  | 0 | Sustainable Building Design Features
30.02 | Light Maintenance Facility |  | 10000000 | 3455025.7443 |  | 13455025.7443 | 50 | 0.031823 | 428182.1058 | No |  | 0 | Sustainable Building Design Features
30.03 | Heavy Maintenance Facility |  | 0 | 0 |  | 0 | 50 | 0.031823 | 0 | No |  | 0 | Sustainable Building Design Features
30.04 | Storage or Maintenance of Way Building |  | 0 | 0 |  | 0 | 50 | 0.031823 | 0 | No |  | 0 | Sustainable Building Design Features
30.05 | Yard and Yard Track |  | 0 | 0 |  | 0 | 80 | 0.025161 | 0
40 SITEWORK & SPECIAL CONDITIONS |  |  | 53350000 | 18432562.3461 | 500000 | 72282562.3461 |  |  | 2135094.4483
40.01 | Demolition, Clearing, Earthwork |  | 10800000 | 3731427.8039 |  | 14531427.8039 | 125 | 0.021837 | 317326.9735
40.02 | Site Utilities, Utility Relocation |  | 21600000 | 7462855.6078 |  | 29062855.6078 | 125 | 0.021837 | 634653.9471
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments |  | 0 | 0 |  | 0 | 125 | 0.021837 | 0
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks |  | 10800000 | 3731427.8039 |  | 14531427.8039 | 125 | 0.021837 | 317326.9735
40.05 | Site structures including retaining walls, sound walls |  | 0 | 0 |  | 0 | 80 | 0.025161 | 0
40.06 | Pedestrian / bike access and accommodation, landscaping |  | 10150000 | 3506851.1305 | 500000 | 14156851.1305 | 20 | 0.061157 | 865786.5541 | No |  | 0 | Functional Landscaping, and Bicycle and Pedestrian Improvements
40.07 | Automobile, bus, van accessways including roads, parking lots |  | 0 | 0 |  | 0 | 20 | 0.061157 | 0
40.08 | Temporary Facilities and other indirect costs during construction |  | 0 | 0 |  | 0 | 100 | 0.023203 | 0
50 SYSTEMS |  |  | 30000000 | 10365077.233 | 500000 | 40865077.233 |  |  | 1871481.9463
50.01 | Train control and signals |  | 10000000 | 3455025.7443 | 500000 | 13955025.7443 | 30 | 0.04465 | 623090.8151
50.02 | Traffic signals and crossing protection |  | 2500000 | 863756.4361 |  | 3363756.4361 | 30 | 0.04465 | 150191.4635
50.03 | Traction power supply: substations |  | 5000000 | 1727512.8722 |  | 6727512.8722 | 50 | 0.031823 | 214091.0529
50.04 | Traction power distribution: catenary and third rail |  | 5000000 | 1727512.8722 |  | 6727512.8722 | 30 | 0.04465 | 300382.927
50.05 | Communications |  | 5000000 | 1727512.8722 |  | 6727512.8722 | 20 | 0.061157 | 411432.6084
50.06 | Fare collection system and equipment |  | 2500000 | 863756.4361 |  | 3363756.4361 | 25 | 0.05122 | 172293.0794
50.07 | Central Control |  | 0 | 0 |  | 0 | 30 | 0.04465 | 0
Construction Subtotal (10 - 50) |  |  | 223350000 | 77168000 | 11000000 | 311518000 |  |  | 8716089.3966
60 ROW, LAND, EXISTING IMPROVEMENTS |  |  | 35175000 |  | 1000000 | 36175000 |  |  | 789963.8922
60.01 | Purchase or lease of real estate |  | 35175000 |  | 1000000 | 36175000 | 125 | 0.021837 | 789963.8922
60.02 | Relocation of existing households and businesses |  | 0 |  |  | 0 | 125 | 0.021837 | 0
70 VEHICLES (number) |  | 15 | 30000000 |  | 1000000 | 31000000 |  |  | 1587833.5909
70.01 | Light Rail | 15 | 30000000 |  | 1000000 | 31000000 | 25 | 0.05122 | 1587833.5909
70.02 | Heavy Rail | 0 | 0 |  |  | 0 | 25 | 0.05122 | 0
70.03 | Commuter Rail | 0 | 0 |  |  | 0 | 25 | 0.05122 | 0
70.04 | Bus | 0 | 0 |  |  | 0 | 12 | 0.09456 | 0 | No |  | 0 | Alternative Energy Bus Vehicles
70.05 | Other | 0 | 0 |  |  | 0 | 12 | 0.09456 | 0
70.06 | Non-revenue vehicles | 0 | 0 |  |  | 0 | 12 | 0.09456 | 0
70.07 | Spare parts | 0 | 0 |  |  | 0 | 12 | 0.09456 | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) |  |  | 77168000
80.01 | Project Development |  | 5668000
80.02 | Engineering |  | 22000000
80.03 | Project Management for Design and Construction |  | 5500000
80.04 | Construction Administration & Management |  | 22000000
80.05 | Professional Liability and other Non-Construction Insurance |  | 5500000
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. |  | 5500000
80.07 | Surveys, Testing, Investigation, Inspection |  | 5500000
80.08 | Start up |  | 5500000
Subtotal (10 - 80) |  |  | 365693000
90 UNALLOCATED CONTINGENCY |  |  | 20000000
TOTAL |  |  | 385693000 | 77168000 | 13000000 | 378693000 |  |  | 11093886.8798
NEW STARTS ENRICHMENTS |  | Calculation | [6 empty] | Amount
Functional Landscaping, and Bicycle and Pedestrian Improvements |  | 100 percent of the annualized cost of SCC ALI 40.06, if enrichment is claimed | [6 empty] | 0
Sustainable Building Design Features |  | 2.5 percent of the total qualifying annualized cost of the following SCC ALIs for which enrichment is claimed: 20.01, 20.02, 20.03, 20.04, 30.01, 30.02, 30.03, 30.04 | [6 empty] | 0
Alternative Energy Bus Vehicles |  | 50 percent of the qualifying annualized cost of SCC ALI 70.04, if enrichment is claimed | [6 empty] | 0
Joint Development |  | 100 percent of the annualized cost of SCC ALI 20.05, if enrichment is claimed | [6 empty] | 0
ANNUALIZED CAPITAL COST EXCLUDING ENRICHMENTS |  | Enter this figure in the New Starts Mobility and Cost Effectiveness template (this figure is not rounded to the nearest thousand) --> | [6 empty] | 11093886.8798
Note on E75: E75 and F75 are double-checks
Note on H60: The range for buses is 12 to 18 years. Provide supporting documentation for an estimated useful life of more than 12 years.
Note on L6: Amounts should reflect only the portion of each line item's cost in column D (Total Base Year Dollars) that is eligible for the enrichments credit. See the New Starts and Small Starts Final Policy Guidance for more information. Do not include any costs associated with professional services or contingency.

## BUILD Annualized - Horizon
A N N U A L I Z E D C O S T - B U I L D A L T E R N A T I V E (Optional Horizon Year) | [12 empty] | (Rev.19, June, 2017)
Insert Project Sponsor's Name here | [10 empty] | Today's Date |  | 2026-08-06 11:41
Insert Project Name and Location | [10 empty] | Yr of Base Year $ |  | 2017
Insert Current Phase (e.g. Applic. for Engineering, Engineering, Applic. for FFGA, Construction, Rev Ops) | [10 empty] | Yr of Revenue Ops |  | 2020
|  | Quantity | Total Base Year Dollars (X000) | Cat. 80 Prof. Svc. spread proportionally over Cats. 10 - 50 (X000) | Spread Cat. 90 Unalloc. Cont. according to perceived risks (X000) | Revised Total Base Year Dollars (X000) | Years of Useful Life | Annualization Factor (based on 2% rate) [.02/1 - (1.02)^-no. yrs] | Annualized Cost (X000) | Claiming Enrichment? | Portion of Base Year Cost that Qualifies for Enrichment (X000) | Portion of Annualized Cost that Qualifies for Enrichment (X000) | Name of Applicable Enrichment (further description provided in New Starts and Small Starts Policy Guidance)
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 10 | 100000000 | 34550257.4435 | 7000000 | 141550257.4435 |  |  | 3091073.7337
10.01 | Guideway: At-grade exclusive right-of-way | 10 | 100000000 | 34550257.4435 | 7000000 | 141550257.4435 | 125 | 0.021837 | 3091073.7337
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | 0 | 0 | 0 |  | 0 | 30 | 0.04465 | 0
10.03 | Guideway: At-grade in mixed traffic | 0 | 0 | 0 |  | 0 | 20 | 0.061157 | 0
10.04 | Guideway: Aerial structure | 0 | 0 | 0 |  | 0 | 80 | 0.025161 | 0
10.05 | Guideway: Built-up fill | 0 | 0 | 0 |  | 0 | 80 | 0.025161 | 0
10.06 | Guideway: Underground cut & cover | 0 | 0 | 0 |  | 0 | 125 | 0.021837 | 0
10.07 | Guideway: Underground tunnel | 0 | 0 | 0 |  | 0 | 125 | 0.021837 | 0
10.08 | Guideway: Retained cut or fill | 0 | 0 | 0 |  | 0 | 125 | 0.021837 | 0
10.09 | Track: Direct fixation |  | 0 | 0 |  | 0 | 30 | 0.04465 | 0
10.1 | Track: Embedded |  | 0 | 0 |  | 0 | 20 | 0.061157 | 0
10.11 | Track: Ballasted |  | 0 | 0 |  | 0 | 35 | 0.040002 | 0
10.12 | Track: Special (switches, turnouts) |  | 0 | 0 |  | 0 | 30 | 0.04465 | 0
10.13 | Track: Vibration and noise dampening |  | 0 | 0 |  | 0 | 30 | 0.04465 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 20 | 30000000 | 10365077.233 | 10000000 | 50365077.233 |  |  | 1343118.1783
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 20 | 30000000 | 10365077.233 | 10000000 | 50365077.233 | 70 | 0.026668 | 1343118.1783 | No |  | 0 | Sustainable Building Design Features
20.02 | Aerial station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 |  | 0 | 70 | 0.026668 | 0 | No |  | 0 | Sustainable Building Design Features
20.03 | Underground station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 |  | 0 | 125 | 0.021837 | 0 | No |  | 0 | Sustainable Building Design Features
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. | 0 | 0 | 0 |  | 0 | 70 | 0.026668 | 0 | No |  | 0 | Sustainable Building Design Features
20.05 | Joint development |  | 0 | 0 |  | 0 | 70 | 0.026668 | 0 | No |  | 0 | Joint Development
20.06 | Automobile parking multi-story structure |  | 0 | 0 |  | 0 | 50 | 0.031823 | 0
20.07 | Elevators, escalators |  | 0 | 0 |  | 0 | 30 | 0.04465 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  |  | 10000000 | 3455025.7443 | 0 | 13455025.7443 |  |  | 428182.1058
30.01 | Administration Building: Office, sales, storage, revenue counting |  | 0 | 0 |  | 0 | 50 | 0.031823 | 0 | No |  | 0 | Sustainable Building Design Features
30.02 | Light Maintenance Facility |  | 10000000 | 3455025.7443 |  | 13455025.7443 | 50 | 0.031823 | 428182.1058 | No |  | 0 | Sustainable Building Design Features
30.03 | Heavy Maintenance Facility |  | 0 | 0 |  | 0 | 50 | 0.031823 | 0 | No |  | 0 | Sustainable Building Design Features
30.04 | Storage or Maintenance of Way Building |  | 0 | 0 |  | 0 | 50 | 0.031823 | 0 | No |  | 0 | Sustainable Building Design Features
30.05 | Yard and Yard Track |  | 0 | 0 |  | 0 | 80 | 0.025161 | 0
40 SITEWORK & SPECIAL CONDITIONS |  |  | 53350000 | 18432562.3461 | 500000 | 72282562.3461 |  |  | 2135094.4483
40.01 | Demolition, Clearing, Earthwork |  | 10800000 | 3731427.8039 |  | 14531427.8039 | 125 | 0.021837 | 317326.9735
40.02 | Site Utilities, Utility Relocation |  | 21600000 | 7462855.6078 |  | 29062855.6078 | 125 | 0.021837 | 634653.9471
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments |  | 0 | 0 |  | 0 | 125 | 0.021837 | 0
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks |  | 10800000 | 3731427.8039 |  | 14531427.8039 | 125 | 0.021837 | 317326.9735
40.05 | Site structures including retaining walls, sound walls |  | 0 | 0 |  | 0 | 80 | 0.025161 | 0
40.06 | Pedestrian / bike access and accommodation, landscaping |  | 10150000 | 3506851.1305 | 500000 | 14156851.1305 | 20 | 0.061157 | 865786.5541 | No |  | 0 | Functional Landscaping, and Bicycle and Pedestrian Improvements
40.07 | Automobile, bus, van accessways including roads, parking lots |  | 0 | 0 |  | 0 | 20 | 0.061157 | 0
40.08 | Temporary Facilities and other indirect costs during construction |  | 0 | 0 |  | 0 | 100 | 0.023203 | 0
50 SYSTEMS |  |  | 30000000 | 10365077.233 | 500000 | 40865077.233 |  |  | 1871481.9463
50.01 | Train control and signals |  | 10000000 | 3455025.7443 | 500000 | 13955025.7443 | 30 | 0.04465 | 623090.8151
50.02 | Traffic signals and crossing protection |  | 2500000 | 863756.4361 |  | 3363756.4361 | 30 | 0.04465 | 150191.4635
50.03 | Traction power supply: substations |  | 5000000 | 1727512.8722 |  | 6727512.8722 | 50 | 0.031823 | 214091.0529
50.04 | Traction power distribution: catenary and third rail |  | 5000000 | 1727512.8722 |  | 6727512.8722 | 30 | 0.04465 | 300382.927
50.05 | Communications |  | 5000000 | 1727512.8722 |  | 6727512.8722 | 20 | 0.061157 | 411432.6084
50.06 | Fare collection system and equipment |  | 2500000 | 863756.4361 |  | 3363756.4361 | 25 | 0.05122 | 172293.0794
50.07 | Central Control |  | 0 | 0 |  | 0 | 30 | 0.04465 | 0
Construction Subtotal (10 - 50) |  |  | 223350000 | 77168000 | 18000000 | 318518000 |  |  | 8868950.4124
60 ROW, LAND, EXISTING IMPROVEMENTS |  |  | 35175000 |  | 1000000 | 36175000 |  |  | 789963.8922
60.01 | Purchase or lease of real estate |  | 35175000 |  | 1000000 | 36175000 | 125 | 0.021837 | 789963.8922
60.02 | Relocation of existing households and businesses |  | 0 |  |  | 0 | 125 | 0.021837 | 0
70 VEHICLES (number) |  | 15 | 30000000 |  | 1000000 | 31000000 |  |  | 1587833.5909
70.01 | Light Rail | 15 | 30000000 |  | 1000000 | 31000000 | 25 | 0.05122 | 1587833.5909
70.02 | Heavy Rail | 0 | 0 |  |  | 0 | 25 | 0.05122 | 0
70.03 | Commuter Rail | 0 | 0 |  |  | 0 | 25 | 0.05122 | 0
70.04 | Bus | 0 | 0 |  |  | 0 | 12 | 0.09456 | 0 | No |  | 0 | Alternative Energy Bus Vehicles
70.05 | Other | 0 | 0 |  |  | 0 | 12 | 0.09456 | 0
70.06 | Non-revenue vehicles | 0 | 0 |  |  | 0 | 12 | 0.09456 | 0
70.07 | Spare parts | 0 | 0 |  |  | 0 | 12 | 0.09456 | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) |  |  | 77168000
80.01 | Project Development |  | 5668000
80.02 | Engineering |  | 22000000
80.03 | Project Management for Design and Construction |  | 5500000
80.04 | Construction Administration & Management |  | 22000000
80.05 | Professional Liability and other Non-Construction Insurance |  | 5500000
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. |  | 5500000
80.07 | Surveys, Testing, Investigation, Inspection |  | 5500000
80.08 | Start up |  | 5500000
Subtotal (10 - 80) |  |  | 365693000
90 UNALLOCATED CONTINGENCY |  |  | 20000000
TOTAL |  |  | 385693000 | 77168000 | 20000000 | 385693000 |  |  | 11246747.8955
NEW STARTS ENRICHMENTS |  | Calculation | [6 empty] | Amount
Functional Landscaping, and Bicycle and Pedestrian Improvements |  | 100 percent of the annualized cost of SCC ALI 40.06, if enrichment is claimed | [6 empty] | 0
Sustainable Building Design Features |  | 2.5 percent of the total qualifying annualized cost of the following SCC ALIs for which enrichment is claimed: 20.01, 20.02, 20.03, 20.04, 30.01, 30.02, 30.03, 30.04 | [6 empty] | 0
Alternative Energy Bus Vehicles |  | 50 percent of the qualifying annualized cost of SCC ALI 70.04, if enrichment is claimed | [6 empty] | 0
Joint Development |  | 100 percent of the annualized cost of SCC ALI 20.05, if enrichment is claimed | [6 empty] | 0
ANNUALIZED CAPITAL COST EXCLUDING ENRICHMENTS |  | Enter this figure in the New Starts Mobility and Cost Effectiveness template (this figure is not rounded to the nearest thousand) --> | [6 empty] | 11246747.8955
Note on E75: E75 and F75 are double-checks
Note on H60: The range for buses is 12 to 18 years. Provide supporting documentation for an estimated useful life of more than 12 years.
Note on I1: Additional project components may need to be included in the Annualized Cost if the project sponsor chooses to do a horizon year analysis, such as additional vehicles or parking facilities needed for a horizon year service plan. Insert vehicle additions in Cat. 70. Insert costs associated with additional parking in the following lines as appropriate: 20.06, 20.07, 40.02, 40.03, 40.04, 40.06, 40.07, 40.08, 60.01 and/or 80.
Note on L6: Amounts should reflect only the portion of each line item's cost in column D (Total Base Year Dollars) that is eligible for the enrichments credit. See the New Starts and Small Starts Final Policy Guidance for more information. Do not include any costs associated with professional services or contingency.

## Fund Source by Cat
F U N D I N G S O U R C E S B Y C A T E G O R Y | [11 empty] | (Rev.19, June, 2017)
Insert Project Sponsor's Name here | [9 empty] | Today's Date |  | 2026-08-06 11:41
Insert Project Name and Location
Insert Current Phase (e.g. Applic. for Engineering, Engineering, Applic. for FFGA, Construction, Rev Ops)
| Cost |  | Funding Summary |  |  | Federal Sources |  |  |  |  | Local Sources
| YOE Cost (X000) | Double- check Total | Federal 5309 New Starts Funds | Federal Other Funds | Local Funds | Federal 5309 New Starts | Other (e.g., CMAQ) | Other | Other | Other | Sales Tax | Other | Other
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 104780125 | 104780125 | 50000000 | 4780125 | 50000000 | 50000000 | 4780125 |  |  |  | 50000000 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 32149428.75 | 32149428.75 | 5000000 | 2149428.75 | 25000000 | 5000000 | 2149428.75 |  |  |  | 5000000 | 20000000
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 10531125 | 10531125 | 5000000 | 531125 | 5000000 | 5000000 | 531125 |  |  |  | 5000000 | 0
40 SITEWORK & SPECIAL CONDITIONS | 54167250 | 54167250 | 20000000 | 14167250 | 20000000 | 20000000 | 14167250 |  |  |  | 20000000 | 0
50 SYSTEMS | 32149428.75 | 32149429 | 15000000 | 2149429 | 15000000 | 15000000 | 2149429 |  |  |  | 15000000 | 0
60 ROW, LAND, EXISTING IMPROVEMENTS | 35350000 | 35350000 | 15000000 | 350000 | 20000000 | 15000000 | 350000 |  |  |  | 15000000 | 5000000
70 VEHICLES (number) | 31593375 | 31593375 | 15000000 | 1593375 | 15000000 | 15000000 | 1593375 |  |  |  | 15000000 | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) | 77423560.75 | 77423561 | 25000000 | 2423561 | 50000000 | 25000000 | 2423561 |  |  |  | 25000000 | 25000000
90 UNALLOCATED CONTINGENCY | 21074714.375 | 21074714 | 10000000 | 1074714 | 10000000 | 10000000 | 1074714 |  |  |  | 10000000 | 0
100 FINANCE CHARGES | 9499500 | 9500000 | 4500000 | 0 | 5000000 | 4500000 | 0 |  |  |  | 4999500 | 500
Total Project Cost (10 - 100) | 408718507.625 | 408719007.75 | 164500000 | 29219007.75 | 215000000 | 164500000 | 29219007.75 | 0 | 0 | 0 | 164999500 | 50000500 | 0
Percentage of Total Project Cost | 100% |  | 40.25% | 7.149% | 52.6% | 40.25% | 7.149% | 0% | 0% | 0% | 40.37% | 12.23% | 0%
|  |  | 40.25% | 59.75%
100%
Note on O7: Insert additional columns as required.

## Fund Source by Year
F U N D I N G S O U R C E S B Y Y E A R |  |  |  | (Rev.19, June, 2017)
Insert Project Sponsor's Name here |  |  | Today's Date |  | 2026-08-06 11:41
Insert Project Name and Location
Insert Current Phase (e.g. Applic. for Engineering, Engineering, Applic. for FFGA, Construction, Rev Ops)
| Total, All Years |  | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036
Total Project Cost In YOE Dollars (X000) Below insert funding sources and amounts for each year. | 408718507.625 | Double-check total | 0 | 0 | 0 | 0 | 0 | 500000 | 1000000 | 1000000 | 2499500 | 20500000 | 105500000 | 127805000 | 112978625 | 30435382.625 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 0 | 0 | 0
Federal 5309 New Starts | 164500000 | 164500000 | [8 empty] | 13500000 | 85435000 | 27805000 | 30760000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 0 | 0 | 0 | 0
Local | 215000000 | 214000000 | 2007: 500000; 2008: 0; 2009: 0; 2010: 0; 2013: 1000000; 2014: 2500000; 2015: 3000000; 2016: 16065000; 2017: 90000000; 2018: 71000000; 2019: 29935000
Federal Other | 29219007.75 | 29219000 | 2015: 4000000; 2016: 4000000; 2017: 10000000; 2018: 11219000
Total Project Cost (10 - 100) | 408719007.75 | 407719000 | 500000 | 0 | 0 | 0 | 0 | 0 | 1000000 | 2500000 | 20500000 | 105500000 | 127805000 | 112979000 | 30435000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 0 | 0 | 0 | 0
Note on N6: The information reported below should match what is reported in the financial plan. FTA uses this data to get an understanding of future demand for Section 5309 funds. The inputs should not assume Section 5309 funding in fiscal years for which appropriations have already occurred and the project did not receive anything.

## FFGA A3T1
Table 1 - BCE by Standard Cost Category
Applicable Line Items Only |  | YOE Dollars Total (X000)
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 104780125
10.01 | Guideway: At-grade exclusive right-of-way | 104780125
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | 0
10.03 | Guideway: At-grade in mixed traffic | 0
10.04 | Guideway: Aerial structure | 0
10.05 | Guideway: Built-up fill | 0
10.06 | Guideway: Underground cut & cover | 0
10.07 | Guideway: Underground tunnel | 0
10.08 | Guideway: Retained cut or fill | 0
10.09 | Track: Direct fixation | 0
10.1 | Track: Embedded | 0
10.11 | Track: Ballasted | 0
10.12 | Track: Special (switches, turnouts) | 0
10.13 | Track: Vibration and noise dampening | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 32149428.75
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 32149428.75
20.02 | Aerial station, stop, shelter, mall, terminal, platform | 0
20.03 | Underground station, stop, shelter, mall, terminal, platform | 0
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. | 0
20.05 | Joint development | 0
20.06 | Automobile parking multi-story structure | 0
20.07 | Elevators, escalators | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  | 10531125
30.01 | Administration Building: Office, sales, storage, revenue counting | 0
30.02 | Light Maintenance Facility | 10531125
30.03 | Heavy Maintenance Facility | 0
30.04 | Storage or Maintenance of Way Building | 0
30.05 | Yard and Yard Track | 0
40 SITEWORK & SPECIAL CONDITIONS |  | 54167250
40.01 | Demolition, Clearing, Earthwork | 10965441.4246
40.02 | Site Utilities, Utility Relocation | 21930882.8491
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments | 0
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks | 10965441.4246
40.05 | Site structures including retaining walls, sound walls | 0
40.06 | Pedestrian / bike access and accommodation, landscaping | 10305484.3018
40.07 | Automobile, bus, van accessways including roads, parking lots | 0
40.08 | Temporary Facilities and other indirect costs during construction | 0
50 SYSTEMS |  | 32149428.75
50.01 | Train control and signals | 10716476.25
50.02 | Traffic signals and crossing protection | 2679119.0625
50.03 | Traction power supply: substations | 5358238.125
50.04 | Traction power distribution: catenary and third rail | 5358238.125
50.05 | Communications | 5358238.125
50.06 | Fare collection system and equipment | 2679119.0625
50.07 | Central Control | 0
Construction Subtotal (10 - 50) |  | 233777357.5
60 ROW, LAND, EXISTING IMPROVEMENTS |  | 35350000
60.01 | Purchase or lease of real estate | 35350000
60.02 | Relocation of existing households and businesses | 0
70 VEHICLES (number) |  | 31593375
70.01 | Light Rail | 31593375
70.02 | Heavy Rail | 0
70.03 | Commuter Rail | 0
70.04 | Bus | 0
70.05 | Other | 0
70.06 | Non-revenue vehicles | 0
70.07 | Spare parts | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) |  | 77423560.75
80.01 | Project Development | 5686770.9715
80.02 | Engineering | 22072858.3934
80.03 | Project Management for Design and Construction | 5518214.5983
80.04 | Construction Administration & Management | 22072858.3934
80.05 | Professional Liability and other Non-Construction Insurance | 5518214.5983
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. | 5518214.5983
80.07 | Surveys, Testing, Investigation, Inspection | 5518214.5983
80.08 | Start up | 5518214.5983
Subtotal (10 - 80) |  | 378144293.25
90 UNALLOCATED CONTINGENCY |  | 21074714.375
Subtotal (10 - 90) |  | 399219007.625
100 FINANCE CHARGES |  | 9499500
Total Project Cost (10 - 100) |  | 408718507.625
Note on B1: This sheet, FFGA A3T1, and the sheets that follow become Attachments to the FFGA
Note on B3: Delete rows that are not needed.

## FFGA A3T2
Table 2 - Inflated Cost to Year of Expenditure
| Base Year Dollars w/o Contingency (X000) | Base Year Dollars Allocated Contingency (X000) | Base Year Dollars TOTAL (X000) | Inflation Factor | YOE Dollars TOTAL (X000)
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 80000000 | 20000000 | 100000000 | 1.0478 | 104780125
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 28000000 | 2000000 | 30000000 | 1.0716 | 32149428.75
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 8000000 | 2000000 | 10000000 | 1.0531 | 10531125
40 SITEWORK & SPECIAL CONDITIONS | 44350000 | 9000000 | 53350000 | 1.0153 | 54167250
50 SYSTEMS | 25000000 | 5000000 | 30000000 | 1.0716 | 32149428.75
60 ROW, LAND, EXISTING IMPROVEMENTS | 30175000 | 5000000 | 35175000 | 1.005 | 35350000
70 VEHICLES (number) | 27000000 | 3000000 | 30000000 | 1.0531 | 31593375
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) | 70000000 | 7168000 | 77168000 | 1.0033 | 77423560.75
90 UNALLOCATED CONTINGENCY |  |  | 20000000 | 1.0537 | 21074714.375
100 FINANCE CHARGES |  |  | 7599635.2916 | 1.25 | 9499500
Total Project Cost (10 - 100) |  |  | 393292635.2916 | 1.0392 | 408718507.625
Note on G3: Delete rows that are not needed.

## A3T3
Table 3 - BCE by Source of Funding
| Total Project Cost in YOE Dollars (X000) | Double Check Total (X000) | Federal 5309 New Starts | Federal Other | Local
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 104780125 | 104780125 | 50000000 | 4780125 | 50000000
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 32149428.75 | 32149428.75 | 5000000 | 2149428.75 | 25000000
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 10531125 | 10531125 | 5000000 | 531125 | 5000000
40 SITEWORK & SPECIAL CONDITIONS | 54167250 | 54167250 | 20000000 | 14167250 | 20000000
50 SYSTEMS | 32149428.75 | 32149429 | 15000000 | 2149429 | 15000000
60 ROW, LAND, EXISTING IMPROVEMENTS | 35350000 | 35350000 | 15000000 | 350000 | 20000000
70 VEHICLES (number) | 31593375 | 31593375 | 15000000 | 1593375 | 15000000
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) | 77423560.75 | 77423561 | 25000000 | 2423561 | 50000000
90 UNALLOCATED CONTINGENCY | 21074714.375 | 21074714 | 10000000 | 1074714 | 10000000
100 FINANCE CHARGES | 9499500 | 9499500 | 4499500 | 0 | 5000000
Total Project Cost (10 - 100) | 408718507.625 | 408718507.75 | 164499500 | 29219007.75 | 215000000
Sources of Federal Funding and Matching Share Ratios
| Costs Attributed to Source of Funds (X000) | Federal/ Local Matching Ratio within Source | All Federal Funds (X000) | Local Funds (X000)
Federal 5309 New Starts | 165000000 | 50/50 | 164999500 | 164999500
Federal Other (please specify sources...) | 29219007.75 | 37/63 | 29219007.75 | 50000500
Total | 194219007.75 |  | 194218507.75 | 215000000
Overall Federal Share of Project |  |  | 100%
New Starts Share of Project |  |  | 40.25%
Note on A3: Delete rows that are not needed.
Note on A19: Add rows as needed to show all federal funding.
Note on F2: Add columns as required to show all federal funding.

## A3A
Scope and Activity Description
Scope Code | ALI Code | Scope and Activity Line Item Descriptions | Qty |  | Federal 5309 New Starts |  |  | Federal Other |  |  | Project Totals |  |  | Check Total Project Cost in YOE Dollars (X000)
|  |  |  | Total Federal % | Federal | Local | Total | Federal | Local | Total | Federal | Local | Total
14010 | 140110 | GUIDEWAY & TRACK ELEMENTS | 10 | 52.28% | 50000000 | 50000000 | 100000000 | 4780125 | 0 | 4780125 | 54780125 | 50000000 | 104780125 | 104780125
14020 | 140220 | STATIONS, STOPS, TERMINALS, INTERMODAL | 20 | 22.24% | 5000000 | 5000000 | 10000000 | 2149428.75 | 20000000 | 22149428.75 | 7149428.75 | 25000000 | 32149428.75 | 32149428.75
14030 | 140330 | SUPPORT FACILITIES, YARDS, SHOPS, ADMIN. BLDGS. |  | 52.52% | 5000000 | 5000000 | 10000000 | 531125 | 0 | 531125 | 5531125 | 5000000 | 10531125 | 10531125
14040 | 140440 | SITEWORK & SPECIAL CONDITIONS |  | 63.08% | 20000000 | 20000000 | 40000000 | 14167250 | 0 | 14167250 | 34167250 | 20000000 | 54167250 | 54167250
14050 | 140550 | SYSTEMS |  | 53.34% | 15000000 | 15000000 | 30000000 | 2149429 | 0 | 2149429 | 17149429 | 15000000 | 32149429 | 32149428.75
14060 | 140660 | ROW, LAND, EXISTING IMPROVEMENTS |  | 43.42% | 15000000 | 15000000 | 30000000 | 350000 | 5000000 | 5350000 | 15350000 | 20000000 | 35350000 | 35350000
14070 |  | VEHICLES | 15 | 52.52% | 15000000 | 15000000 | 30000000 | 1593375 | 0 | 1593375 | 16593375 | 15000000 | 31593375 | 31593375
| 13.13.20 | Light Rail Cars | 15
13.__.__
14080 | 140880 | PROFESSIONAL SERVICES |  | 35.42% | 25000000 | 25000000 | 50000000 | 2423561 | 25000000 | 27423561 | 27423561 | 50000000 | 77423561 | 77423560.75
14090 | 140990 | UNALLOCATED CONTINGENCY |  | 52.55% | 10000000 | 10000000 | 20000000 | 1074714 | 0 | 1074714 | 11074714 | 10000000 | 21074714 | 21074714.375
14100 | 141010 | FINANCE CHARGES |  | 47.37% | 4499500 | 4999500 | 9499000 | 0 | 500 | 500 | 4499500 | 5000000 | 9499500 | 9499500
Total Project Cost (10 - 100) |  |  |  | 47.4% | 164499500 | 164999500 | 329499000 | 29219007.75 | 50000500 | 79219507.75 | 193718507.75 | 215000000 | 408718507.75 | 408718507.625
Note on C4: Delete rows that are not needed.
Note on I2: Add more tri-columns as required to show all funding.

## A4
SCHEDULE | Start Date | End Date | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035
10 GUIDEWAY & TRACK ELEMENTS (route miles)
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number)
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS
40 SITEWORK & SPECIAL CONDITIONS
50 SYSTEMS
60 ROW, LAND, EXISTING IMPROVEMENTS
70 VEHICLES (number)
80 PROFESSIONAL SERVICES (applies to Cats. 10-50)
90 UNALLOCATED CONTINGENCY
100 FINANCE CHARGES
Revenue Ops / Closeout of Project
Revenue Service Date
Before and After Study: Two years post Rev Ops
Fulfillment of the New Starts funding commitment
Completion of project close-out, resolution of claims
Note on A2: Delete rows that are not needed.
Note on D1: Delete unnecessary columns.