## Slide 1
RULEMAKING
Notice of Proposed Rulemaking (NPRM) PROJECT MANAGEMENT OVERSIGHT (PMO) RULE
October 2019

## Slide 2: PUBLICATION INFO
NPRM for PMO Published: August 26, 2019
Federal Register Volume 84, Pages 44590-44596
Agency/Docket Number: FTA-2019-0016
Document Number: 2019-18286
Regulatory Information Number (RIN):2132-AB35
Comments Period Ends: 10/25/2019

## Slide 3: BACKGROUND
UMTA issued the PMO rule for the first time in September 1989
FTA issued an NPRM for a new PMO rule on September 2011 but withdrew it in March 2013, due to the passage of MAP 21 in July 2012, which made significant changes to the program including:
  Repealed the Fixed Guideway Modernization Program
  Created the State of Good Repair Program
  Amended the Capital Investment Grants program to add Core Capacity Improvement projects
  Streamlined the New and Small Starts project development process

## Slide 4: BACKGROUND
The Fixing America’s Surface Transportation (FAST) Act which passed on December 4, 2015, further amended the Oversight Statute by limiting project management oversight to quarterly reviews.
  However, the Statute does allow for more frequent oversight other than quarterly if the Secretary determines that it is warranted based on criteria specified in the law

## Slide 5: FOCUS OF THE NEW RULE
FTA’s new NPRM published on August 26, 2019, is proposing to change the current rule for PMO (49 C.F.R. Part 633) primarily by:
  Changing the applicability of the regulation by changing the definition of a major capital project
  Amending the regulation to bring it into compliance with recent statutory changes
  Applying project management oversight to major capital projects receiving Federal financial assistance under any provision of Federal law

## Slide 6: STRUCTURE OF PROPOSED RULE
Subpart A: General Provisions
  Purpose, Scope and Definitions
Subpart B: Project Management Oversight Services
  Covered Projects, Initiation of PMO Services, Information Access, PMO Contractor Eligibility, and Exclusion from PMO Program
Subpart C: Project Management Plans
  Basic requirements, FTA review of PMP, Contents of PMP and Implementation of PMP

## Slide 7: Subpart A: General Provisions
633.1 Purpose
  Updated to reflect the mandate in 49 U.S.C. 5327(a) to perform program management oversight of major capital projects for public transportation under Chapter 53 of Title 49, or any other provision of Federal law
  633.3 Scope
  Updated to reflect the mandate in 49 U.S.C. 5327(a) that the regulation applies to recipients of Federal assistance undertaking a major capital project for public transportation under Chapter 53 of Title 49, or any other provision of Federal law

## Slide 8: Subpart A: General Provisions
633.5 Definitions
  Current Rule -Definition of Major Capital Project
    All construction projects for new fixed guideways or extensions of existing fixed guideways regardless of project cost
    Rehabilitation and modernization of projects with total project costs over $100 million
    As determined by the Administrator

## Slide 9: Subpart A: General Provisions
633.5 Definitions (cont’d)
  Proposed Rule -Definition of Major Capital Project
    Applies to construction, expansion, rehabilitation and modernization of fixed guideway projects with $300 million or more in total project cost AND $100 million or more in Federal financial assistance (regardless of source) AND is not exclusively for the acquisition, maintenance or rehabilitation of vehicles or other rolling stock
    As determined by the Administrator

## Slide 10: Subpart A: General Provisions
633.5 Definitions (cont’d)
  Fixed Guideway – is defined as any public transportation facility using and occupying a separate right-of-way for the exclusive use of public transportation; using rail; using fixed catenary system; for a passenger ferry system or for a bus rapid transit system.
  Project Development – is defined as a project phase where engineering and design work is undertaken to reasonably define the project by scope, cost, schedule, management plan etc.

## Slide 11: Subpart A: General Provisions
633.5 Definitions (cont’d)
  Project Management Oversight is defined as: Monitoring of recipient’s management of a project during engineering, design and construction to determine if it is meeting performance and regulatory requirements.
  Project management plan is defined as: A document that defines the tasks for managing a project (could have many sub plans based on project size).
  Recipient is defined as: A direct recipient of Federal financial assistance or the project sponsor of a major capital project.

## Slide 12: Subpart B: Project Management Oversight Services
633.11 Covered Projects
  Project must be a major capital project as defined in Subpart A and
  Project must be using funds made available under Chapter 53 of Title 49 of United States Code or any other provision of Federal law (e.g. BUILD, Sandy).
  633.13 Initiation of Project Management Oversight Activities
  Will generally be initiated during Project Development OR
  As determined by the Administrator

## Slide 13: Subpart B: Project Management Oversight Services
633.15 Access to Information
  Recipient shall provide access to its records to the Administrator or the Administrator’s representatives as may be reasonably required
633.17 PMO Contractor Eligibility
  Any person/entity may provide PMO services EXCEPT for their own project or if there exists a conflict of interest

## Slide 14: Subpart B: Project Management Oversight Services
  633.19 Exclusion from the PMO Program
  Projects which meet the cost threshold for oversight as defined in Subpart A, may still be excluded from PMO by the Administrator based on the recipient’s past record, or based on the financial risk to the recipient compared to the Federal government.

## Slide 15: Subpart C: Project Management Plans
633.21 Basic Requirement
  Recipients shall submit a PMP as a condition of Federal financial assistance for major capital projects
  Recipients will be notified by the Administrator as to when to submit the PMP (usually at the project development phase)
  Recipients will have a minimum of 90 days to submit a PMP after being notified
    633.23 FTA Review of a Project Management Plan
  Within 60 days of PMP submittal, the Administrator shall notify a recipient of the approval or disapproval of the plan or any required modification before approval of the plan
  Also, within 60 days, the Administrator shall notify the recipient if the review of the PMP is not completed and indicate when the review will be completed

## Slide 16: Subpart C: Project Management Plans
633.25 Contents of a Project Management Plan
  Must be tailored based on type and complexity of the project
  Must be developed to a level of detail to enable the Administrator to assess the adequacy of the plan
  May be a single document or a series of documents or sub plans integrated into the PMP either directly or by reference

## Slide 17: Subpart C: Project Management Plans
633.25 Contents of a Project Management Plan (cont’d) – Minimum elements of a PMP:
  Adequate staff organization with well-defined reporting relationships
  A budget covering the project management organization and all elements of the project
  A construction schedule
  A document control procedure and recordkeeping system
  A change order management process
  Description of organizational structures, management skills and staffing required throughout the project life cycle
  Quality control and quality assurance functions throughout the project life cycle
  Material testing policies and procedures

## Slide 18: Subpart C: Project Management Plans
633.25 Contents of a Project Management Plan (cont’d) – Minimum elements of a PMP:
  Internal plan implementation and reporting requirements including cost and schedule control procedures
  Criteria and procedures for testing the operational system or its major components
  Periodic updates to the plan (e.g. budget, schedule, financing, ridership estimates)
  Safety and security management procedures
  Risk, insurance and contingency management procedures
  Commitment to submit budget and schedule to the Administrator quarterly or when requested by the Administrator

## Slide 19: Subpart C: Project Management Plans
633.27 Implementation of a Project Management Plan - Upon approval of the PMP, a recipient must implement the PMP by, at a minimum, doing the following:
  Modifying the PMP at new phases
  Submitting updates of the PMP to the Administrator quarterly or whenever required by the Administrator
  Ensuring updated PMPs shall include budget, schedule, financing (capital and operating), ridership estimates etc.

## Slide 20
Projects seeking CIG funding that do not meet the major capital project definition are still subject to reviews to inform FTA’s investment decision
  For example, FTA may conduct PMP, cost, schedule, scope and risk reviews prior to grant award
Applicability to Capital Investment Grant Program

## Slide 21: How to Comment
Four Options for Submitting Comments
  By going to: www.regulations.gov and following the instructions
  By mailing to: Docket Management Facility, USDOT, 1200 New Jersey Ave. SE, West Building, Room W12-140, Washington DC 20590
  By hand delivery or courier to: West Building Ground Floor, USDOT, Room W12-140, 1200 New Jersey Ave. SE, between 9 a.m. and 5 p.m. weekdays, except holidays
  By fax to: (202) 493-2251

## Slide 22: How to Comment
All submissions received must include Agency Name/Docket Number or Regulatory Information Number
  Agency/Docket Number: FTA-2019-0016
  Regulatory Information Number (RIN):2132-AB35
Comments period ends on: 10/25/2019
All comments received will be posted without change to www.regulations.gov including any personal information provided

## Slide 23: Who to Contact
For program matters, contact: Corey Walker, Office of Program Management, (202) 366-0826 or corey.walker@dot.gov
For legal matters, contact: Mark Montgomery, Office of Chief Counsel, (202) 366-4011 or mark.montgomery@dot.gov

## Slide 24: Next Steps
Review of Comments
Summary, Analysis, Issues, and Options for FTA and USDOT Leadership
Development of Final Rule
Executive Branch Review
Promulgation of Final Rule